## Dashboard
Project: | SharePoint Migration
Capacity | [5 empty] | Task Status
Phase | Planned | Analysis | Execution | Validation | Total | On Time | 0
WIP Limit | 3 | 3 | 1 | 1 | 8 | Due Today | 0
Current WIP | 2 | 3 | 2 | 1 | 8 | Blocked | 1
[6 empty] | Late | 8
Throughput |  |  | Project Completion (Est.) |  |  | Cycle Time
Average per Week | 1.25 |  | Likelihood | Date |  | Per Week | 1.75
Last Week | 0 |  | 100% | 2017-09-30 |  | Last Week
Average per Month | 5 |  | 95% | 2017-07-08 |  | Per Month | 1.75
Last Month | 1.75 |  | 90% | 2017-06-24 |  | Last Month | 1.75
This Month | 5 |  | 85% | 2017-06-17 |  | This Month | 1.75
This is automatically generated. Do not edit.
DAPS Kanban Template
ver 1.2.0
https://github.com/USDepartmentofLabor/Kanban

## Tracking Data
| State |  | ID |  | Task |  | Class of Service |  | Date Added | Size | Planned | Analysis | 3 | Execution | 1 | Validation | 1 | Done | Cycle Time | Reason For Aborting (If applicable) | Notes
|  | Status | ID | Type |  |  |  | Size Label |  |  | 3 | In | Out | In | Out | In | Out
1 | Planned | Blocked | SPM1 |  | Sample Task 1 | Blocked - Sample Task 1 | Standard | S | 2017-03-08 | 2 days | 2017-03-08
2 | Execution Out | Late | SPM2 |  | Sample Task 2 | Sample Task 2 | Standard | S | 2017-03-08 | 2 days | 2017-03-08 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-15
3 | Analysis In | Late | SPM3 |  | Sample Task 3 | Sample Task 3 | Standard | S | 2017-03-08 | 2 days | 2017-03-08 | 2017-03-14
4 | Validation In | Late | SPM4 |  | Sample Task 4 | Sample Task 4 | Standard | L | 2017-03-08 | <= 1 week | 2017-03-03 | 2017-03-03 | 2017-03-03 | 2017-03-03 | 2017-03-07 | 2017-03-10
5 | Done | Done | SPM5 |  | Sample Task 5 | Sample Task 5 | Standard | M | 2017-03-08 | 3 days | 2017-03-03 | 2017-03-03 | 2017-03-03 | 2017-03-03 | 2017-03-07 | 2017-03-07 | 2017-03-08 | 2017-03-08 | 5
6 | Done | Done | SPM6 |  | Sample Task 6 | Sample Task 6 | Standard | XS | 2017-03-08 | <= 1 day | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 0
7 | Aborted | Aborted | SPM7 |  | Sample Task 7 | Sample Task 7 | Standard | M | 2017-03-08 | 3 days | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 |  | sdfds
8 | Execution In | Late | SPM8 |  | Sample Task 8 | Sample Task 8 | Standard | M | 2017-03-08 | 3 days | 2017-03-09 | 2017-03-14 | 2017-03-15 | 2017-03-15
9 | Planned | Late | SPM9 |  | Sample Task 9 | Sample Task 9 | Standard | XL | 2017-03-08 | <= 2 weeks | 2017-03-14
10 | Analysis In | Late | SPM10 |  | Sample Task 10 | Sample Task 10 | Standard | L | 2017-03-10 | <= 1 week | 2017-03-14 | 2017-03-14
11 | Planned | Late | SPM11 |  | Sample Task 11 | Sample Task 11 | Standard | M | 2017-03-10 | 3 days | 2017-03-14
12 | Aborted | Aborted | SPM12 |  | Sample Task 12 | Sample Task 12 | Fixed Date | L | 2017-03-10 | <= 1 week | 2017-03-14 | [8 empty] | ddd
13 |  |  | SPM13 |  | Sample Task 13 | Sample Task 13 |  | XL | 2017-03-14 | <= 2 weeks
14 |  |  | SPM14 |  | Sample Task 14 | Sample Task 14 |  | XL | 2017-03-14 | <= 2 weeks
15 |  |  | SPM15 |  | Sample Task 15 | Sample Task 15 |  | L | 2017-03-14 | <= 1 week
16 |  |  | SPM16 |  | Sample Task 16 | Sample Task 16 |  | L | 2017-03-14 | <= 1 week
17 |  |  | SPM17 |  | Sample Task 17 | Sample Task 17 |  | XL | 2017-03-14 | <= 2 weeks
18 | Analysis In | Late | SPM18 |  | Sample Task 18 | Sample Task 18 | Standard | XL | 2017-03-14 | <= 2 weeks | 2017-03-15 | 2017-03-15
19 |  |  | SPM19 |  | Sample Task 19 | Sample Task 19 |  | L | 2017-03-14 | <= 1 week
20 | Done | Done | SPM20 |  | Sample Task 20 | Sample Task 20 | Expedite | S | 2017-03-14 | 2 days | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-15 | 2017-03-15 | 2017-03-15 | 2017-03-15 | 1
21 | Done | Done | SPM21 |  | Sample Task 21 | Sample Task 21 | Expedite | S | 2017-03-14 | 2 days | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-15 | 2017-03-15 | 2017-03-15 | 2017-03-15 | 1
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998

## Forecast
Forecast Completion Date | [7 empty] | Results
Duration in
1. Start Date |  |  | 2017-03-11 |  |  |  |  | Likelihood | Week's | Date
[8 empty] | 100% | 29 | 2017-09-30
2. How many stories are remaining to be completed? | [7 empty] | 95% | 17 | 2017-07-08
(enter the range estimate of stories. Tip: start wide and narrow as certainty increases) | [7 empty] | 90% | 15 | 2017-06-24
| Low guess |  | 9 |  | Highest guess |  | 15 | 85% | 14 | 2017-06-17
[8 empty] | 80% | 13 | 2017-06-10
3. Stories are often split before and whilst being worked on. Estimate the split rate low and high bounds. | [7 empty] | 75% | 12 | 2017-06-03
(often the throughput in the backlog is pre-split, but captured throughput post-split. Adjust for this here) | [7 empty] | 70% | 12 | 2017-06-03
| Low guess |  | 1 |  | Highest guess |  | 1 | 65% | 11 | 2017-05-27
[8 empty] | 60% | 11 | 2017-05-27
4. Throughput. How many completed stories per week or sprint do you estimate low and high bounds? | [7 empty] | 55% | 10 | 2017-05-20
[8 empty] | 50% | 10 | 2017-05-20
Throughput estimate/samples are per |  |  |  | Week | 7 | days |  | 45% | 9 | 2017-05-13
[8 empty] | 40% | 9 | 2017-05-13
Use historical throughput data OR enter a low and high estimate below. Use: | [6 empty] | Data | 35% | 8 | 2017-05-06
[8 empty] | 30% | 8 | 2017-05-06
| Low guess |  | 1 |  | Highest guess |  | 5 | 25% | 8 | 2017-05-06
[8 empty] | 20% | 7 | 2017-04-29
[8 empty] | 15% | 6 | 2017-04-22
[8 empty] | 10% | 6 | 2017-04-22
[8 empty] | 5% | 5 | 2017-04-15
[8 empty] | 0% | 4 | 2017-04-08
Forecast Story Count Completion by Time Period
5. How long? |  | 6 | Weeks |  | Result: Total Pre-split Stories in 6 Weeks
(To forecast story counts, enter the how long. |  |  |  |  | (Pre-split means, splitting IS accounted for)
To change unit, change input 4. above.) |  |  |  |  | 95% | 7
[5 empty] | 85% | 8 | <--- Tip: This is your forecasted # storiess for this period at 85% confidence
[5 empty] | 5% | 14
Almost certain
Somewhat certain
Less than coin-toss odds. But if you are game?
Read forecast from this table.
Can I use velocity rather than throughput?
Yes. If you do have estimates in story points, then you can sume all of the estimates and use that for input 2 and estimate or use historical team velocity for input 4. The benefit of using throughput (count of completed stories per week/sprint) is that the individual stories don't require estimation in story points.
Enter data in Orange cells
Please Remember: This forecast is only as good as the estimates you enter into it. Always look for multiple ways to forecast your project and compare the outcomes, especially if making a financially critical decision. In the end - any decision to proceed with a project is YOURS.
How do I use this story count forecast?
This forecast aims to show how many stories might be completed given the team data or estimates entered above. Enter all data for inputs 3. and 4. above. This forecast simulates 500 times to determine what number of stories will be completed for the period you entered for input 5. It also creates a chart view of this forecast in the charts tab. This forecast ignores risk data, and un-necessary inputs 1 and 2 from above.

## Settings
Duration name | days
Week | 7
Sprint (2 week) | 14
Sprint (3 week) | 21
Sprint (4 week) | 28
Start Day (Sun) | 2017-03-11
Project Prefix | SPM
WIP Limits |  | Swimlane WIP Limits
Planned | 3 | Expedited | 1
Analysis | 3 | Fixed Date | 1
Execution | 1 | Standard | 5
Validation | 1 | Intangible | 1
Sum | 8 | Sum | 8
This table converts throughput duration name to number of days. Add more or edit these here. The days is used to increment forecasting periods. Resolution of forecast will also be in increments of this value.

## Defects
| Ticket ID | Defect ID | Defect | Class of Service | Planned | Analysis |  | Execution |  | Validation |  | Done | Status | Cycle Time
| ID |  |  |  |  | In | Out | In | Out | In | Out
1 | SPM1 | def-SPM1-1 | Sample Defect 1 | Standard | 2017-03-08 | 2017-03-09 | 2017-03-10 | 2017-03-13 | 2017-03-14 | 2017-03-15 | 2017-03-16 | 2017-03-17 | Done | 8
2 | SPM2 | def-SPM2-2 | Sample Defect 2 | Standard | 2017-03-08 | 2017-03-09 | [6 empty] | Analysis In | FALSE
3 | [13 empty] | FALSE
4 | [13 empty] | FALSE
5 | [13 empty] | FALSE
6 | [13 empty] | FALSE
7 | [13 empty] | FALSE
8 | [13 empty] | FALSE
9 | [13 empty] | FALSE
10 | [13 empty] | FALSE
11 | [13 empty] | FALSE
12 | [13 empty] | FALSE
13 | [13 empty] | FALSE
14 | [13 empty] | FALSE
15 | [13 empty] | FALSE
16 | [13 empty] | FALSE
17 | [13 empty] | FALSE
18 | [13 empty] | FALSE
19 | [13 empty] | FALSE
20 | [13 empty] | FALSE
21 | [13 empty] | FALSE
22 | [13 empty] | FALSE
23 | [13 empty] | FALSE
24 | [13 empty] | FALSE
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369

## Blocks
| Ticket ID | Block ID | Block | Class of Service | Planned | Analysis |  | Execution |  | Validation |  | Done | Status | Cycle Time
| ID |  |  |  |  | In | Out | In | Out | In | Out
1 | SPM1 | blk-SPM1-1 | Procurement of Software | Standard | 2017-03-08 | [7 empty] | Planned | FALSE
2 | [13 empty] | FALSE
3 | [13 empty] | FALSE
4 | [13 empty] | FALSE
5 | [13 empty] | FALSE
6 | [13 empty] | FALSE
7 | [13 empty] | FALSE
8 | [13 empty] | FALSE
9 | [13 empty] | FALSE
10 | [13 empty] | FALSE
11 | [13 empty] | FALSE
12 | [13 empty] | FALSE
13 | [13 empty] | FALSE
14 | [13 empty] | FALSE
15 | [13 empty] | FALSE
16 | [13 empty] | FALSE
17 | [13 empty] | FALSE
18 | [13 empty] | FALSE
19 | [13 empty] | FALSE
20 | [13 empty] | FALSE
21 | [13 empty] | FALSE
22 | [13 empty] | FALSE
23 | [13 empty] | FALSE
24 | [13 empty] | FALSE
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
Set up purely to identify blocks and allow for future additions of metrics around blocks.

## Risks
Likelihood | Impact Low | Impact High | Description
For example:
Likelihood | Impact Low | Impact High | Description
20% | 10 | 20 | Performance tuning if we fail load testing.
Why would I use risks?
Risks allow you to put a probability on work being expanded because of something more than plan. For eample, there might be a chance that more work is needed to improve performance characteristics. If you think there is a 20% chance, put 20 in the likelihood column. Have the team estimate the low and high story count to rectify and add these to the low and high impact columns.

## Kanban Board
|  | Planned | Analysis |  | Execution |  | Validation |  | Done
|  |  | In | Out | In | Out | In | Out
|  | 3 | 3 |  | 1 |  | 1
Expedite | 1 | [8 empty] | 2 | 0
2
Fixed Date | 1 | [8 empty] | 2 | 1
2
2
Standard | 5 | Sample Task 1 | Sample Task 3 |  | Sample Task 8 | Sample Task 2 | Sample Task 4 |  |  | 2 | 10
|  | Sample Task 9 | Sample Task 10 | [6 empty] | 2
|  | Sample Task 11 | Sample Task 18 | [6 empty] | 2
Intangible | 1 | [8 empty] | 2 | 0
This is automatically generated. Do not edit.

## Throughput Samples (hidden)
Enter Samples Below
3 | [7 empty] | Weeks Completed
2 | [7 empty] | 4
0 | [7 empty] | Offset
0 | [7 empty] | 0
| Total Count |  | 4
| Data |  | 0 | 2 | 0 | 0 | 3
| Estimate |  | 2 | 2 | 3 | 1 | 5
| Samples Or Data |  | 3 | 0 | 0 | 3 | 2
Transportable data formats
| CSV | 3,2,0,0
| SIP 2.0 | <sip name="dist" type="CSV" ver="1.0" count="4" average="1.25" median="1">3,2,0,0</sip>
| Distribution | <distribution name="dist" shape="fromSamples">3,2,0,0</distribution>
Instructions.
If you have team historic throughput samples, you can use them when forecasting forward. If not, estimate the range in the forecast sheet. When actual data becomes available, add it here and your forecast will become more indicative.
Add seven (7) minimum, and twenty five (25) maximum recent throughput samples for your team. These samples will be used as throughput values picked at random. By using your teams data, the forecast will follow the patterns your teams throughput historically follows.
Remember to set the unit of throughput measure.
No blank rows within sample range, leave rows after the last sample blank.
Data beyond 24 weeks is most likely out of date. When adding, add most recent samples to the top and remove older samples from the bottom.
These are for testing the formulas that return random ssamples from data or between the estimates. They are included here for education and reference.
These formats are to help share throughput samples with others or teams should the need arise.
CSV = simple comma separated value list
SIP 2.0 = ProbabilityManagement.org's SIP standard for sharing data
Distribution = FocusedObjective.com's distribution format for sharing and creating random data from samples in their simulation software
What is throughput? Where do I get that data? Throughput is the number of DONE stories completed by a team per week or per sprint (you choose in this spreadsheet, default is per week). Also see our Throughput and Cycle Time Calculator spreadsheet for convertinf story/item data to throughput values. Also see our tutorials on how to use Excel to calculate throughput rates.
This has been updated to enter the "Samples" automatically from real data.
These are calculated based on actual data and used in the table to the left.

## Weekly Summary
Week Of | Week Start | Week End | Planned | Analysis In | Analysis Out | Analysis | Execution In | Execution Out | Execution | Validation In | Validation Out | Validation | Done | Done | Average Cycle Time | Incomplete | Backlog
2017-03-05 | 2017-03-05 | 2017-03-11 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 3 | 3 | 2.5 | 8 | 0
2017-03-12 | 2017-03-12 | 2017-03-18 | 4 | 3 | 0 | 3 | 1 | 1 | 2 | 1 | 0 | 1 | 2 | 5 | 1 | 15 | 6
2017-03-19 | 2017-03-19 | 2017-03-25 | 4 | 3 | 0 | 3 | 1 | 1 | 2 | 1 | 0 | 1 | 0 | 5 |  | 15 | 6
2017-03-26 | 2017-03-26 | 2017-04-01 | 4 | 3 | 0 | 3 | 1 | 1 | 2 | 1 | 0 | 1 | 0 | 5 |  | 15 | 6
2017-04-02 | 2017-04-02 | 2017-04-08
2017-04-09 | 2017-04-09 | 2017-04-15
2017-04-16 | 2017-04-16 | 2017-04-22
2017-04-23 | 2017-04-23 | 2017-04-29
2017-04-30 | 2017-04-30 | 2017-05-06
2017-05-07 | 2017-05-07 | 2017-05-13
2017-05-14 | 2017-05-14 | 2017-05-20
2017-05-21 | 2017-05-21 | 2017-05-27
2017-05-28 | 2017-05-28 | 2017-06-03
2017-06-04 | 2017-06-04 | 2017-06-10
2017-06-11 | 2017-06-11 | 2017-06-17
2017-06-18 | 2017-06-18 | 2017-06-24
2017-06-25 | 2017-06-25 | 2017-07-01
2017-07-02 | 2017-07-02 | 2017-07-08
2017-07-09 | 2017-07-09 | 2017-07-15
2017-07-16 | 2017-07-16 | 2017-07-22
2017-07-23 | 2017-07-23 | 2017-07-29
2017-07-30 | 2017-07-30 | 2017-08-05
2017-08-06 | 2017-08-06 | 2017-08-12
2017-08-13 | 2017-08-13 | 2017-08-19
2017-08-20 | 2017-08-20 | 2017-08-26
2017-08-27 | 2017-08-27 | 2017-09-02
2017-09-03 | 2017-09-03 | 2017-09-09
2017-09-10 | 2017-09-10 | 2017-09-16
2017-09-17 | 2017-09-17 | 2017-09-23
2017-09-24 | 2017-09-24 | 2017-09-30
2017-10-01 | 2017-10-01 | 2017-10-07
2017-10-08 | 2017-10-08 | 2017-10-14
2017-10-15 | 2017-10-15 | 2017-10-21
2017-10-22 | 2017-10-22 | 2017-10-28
2017-10-29 | 2017-10-29 | 2017-11-04
2017-11-05 | 2017-11-05 | 2017-11-11
2017-11-12 | 2017-11-12 | 2017-11-18
2017-11-19 | 2017-11-19 | 2017-11-25
2017-11-26 | 2017-11-26 | 2017-12-02
2017-12-03 | 2017-12-03 | 2017-12-09
2017-12-10 | 2017-12-10 | 2017-12-16
2017-12-17 | 2017-12-17 | 2017-12-23
2017-12-24 | 2017-12-24 | 2017-12-30
2017-12-31 | 2017-12-31 | 2018-01-06
2018-01-07 | 2018-01-07 | 2018-01-13
2018-01-14 | 2018-01-14 | 2018-01-20
2018-01-21 | 2018-01-21 | 2018-01-27
2018-01-28 | 2018-01-28 | 2018-02-03
2018-02-04 | 2018-02-04 | 2018-02-10
2018-02-11 | 2018-02-11 | 2018-02-17
2018-02-18 | 2018-02-18 | 2018-02-24
2018-02-25 | 2018-02-25 | 2018-03-03
2018-03-04 | 2018-03-04 | 2018-03-10
2018-03-11 | 2018-03-11 | 2018-03-17
2018-03-18 | 2018-03-18 | 2018-03-24
2018-03-25 | 2018-03-25 | 2018-03-31
2018-04-01 | 2018-04-01 | 2018-04-07
2018-04-08 | 2018-04-08 | 2018-04-14
2018-04-15 | 2018-04-15 | 2018-04-21
2018-04-22 | 2018-04-22 | 2018-04-28
2018-04-29 | 2018-04-29 | 2018-05-05
2018-05-06 | 2018-05-06 | 2018-05-12
2018-05-13 | 2018-05-13 | 2018-05-19
2018-05-20 | 2018-05-20 | 2018-05-26
2018-05-27 | 2018-05-27 | 2018-06-02
2018-06-03 | 2018-06-03 | 2018-06-09
2018-06-10 | 2018-06-10 | 2018-06-16
2018-06-17 | 2018-06-17 | 2018-06-23
2018-06-24 | 2018-06-24 | 2018-06-30
2018-07-01 | 2018-07-01 | 2018-07-07
2018-07-08 | 2018-07-08 | 2018-07-14
2018-07-15 | 2018-07-15 | 2018-07-21
2018-07-22 | 2018-07-22 | 2018-07-28
2018-07-29 | 2018-07-29 | 2018-08-04
2018-08-05 | 2018-08-05 | 2018-08-11
2018-08-12 | 2018-08-12 | 2018-08-18
2018-08-19 | 2018-08-19 | 2018-08-25
2018-08-26 | 2018-08-26 | 2018-09-01
2018-09-02 | 2018-09-02 | 2018-09-08
2018-09-09 | 2018-09-09 | 2018-09-15
2018-09-16 | 2018-09-16 | 2018-09-22
2018-09-23 | 2018-09-23 | 2018-09-29
2018-09-30 | 2018-09-30 | 2018-10-06
2018-10-07 | 2018-10-07 | 2018-10-13
2018-10-14 | 2018-10-14 | 2018-10-20
2018-10-21 | 2018-10-21 | 2018-10-27
2018-10-28 | 2018-10-28 | 2018-11-03
2018-11-04 | 2018-11-04 | 2018-11-10
2018-11-11 | 2018-11-11 | 2018-11-17
2018-11-18 | 2018-11-18 | 2018-11-24
2018-11-25 | 2018-11-25 | 2018-12-01
2018-12-02 | 2018-12-02 | 2018-12-08
2018-12-09 | 2018-12-09 | 2018-12-15
2018-12-16 | 2018-12-16 | 2018-12-22
2018-12-23 | 2018-12-23 | 2018-12-29
2018-12-30 | 2018-12-30 | 2019-01-05
2019-01-06 | 2019-01-06 | 2019-01-12
2019-01-13 | 2019-01-13 | 2019-01-19
2019-01-20 | 2019-01-20 | 2019-01-26
2019-01-27 | 2019-01-27 | 2019-02-02
2019-02-03 | 2019-02-03 | 2019-02-09
2019-02-10 | 2019-02-10 | 2019-02-16
2019-02-17 | 2019-02-17 | 2019-02-23
2019-02-24 | 2019-02-24 | 2019-03-02
2019-03-03 | 2019-03-03 | 2019-03-09
2019-03-10 | 2019-03-10 | 2019-03-16
2019-03-17 | 2019-03-17 | 2019-03-23
2019-03-24 | 2019-03-24 | 2019-03-30
2019-03-31 | 2019-03-31 | 2019-04-06
2019-04-07 | 2019-04-07 | 2019-04-13
2019-04-14 | 2019-04-14 | 2019-04-20
2019-04-21 | 2019-04-21 | 2019-04-27
2019-04-28 | 2019-04-28 | 2019-05-04
2019-05-05 | 2019-05-05 | 2019-05-11
2019-05-12 | 2019-05-12 | 2019-05-18
2019-05-19 | 2019-05-19 | 2019-05-25
2019-05-26 | 2019-05-26 | 2019-06-01
2019-06-02 | 2019-06-02 | 2019-06-08
2019-06-09 | 2019-06-09 | 2019-06-15
2019-06-16 | 2019-06-16 | 2019-06-22
2019-06-23 | 2019-06-23 | 2019-06-29
2019-06-30 | 2019-06-30 | 2019-07-06
2019-07-07 | 2019-07-07 | 2019-07-13
2019-07-14 | 2019-07-14 | 2019-07-20
2019-07-21 | 2019-07-21 | 2019-07-27
2019-07-28 | 2019-07-28 | 2019-08-03
2019-08-04 | 2019-08-04 | 2019-08-10
2019-08-11 | 2019-08-11 | 2019-08-17
2019-08-18 | 2019-08-18 | 2019-08-24
2019-08-25 | 2019-08-25 | 2019-08-31
2019-09-01 | 2019-09-01 | 2019-09-07
2019-09-08 | 2019-09-08 | 2019-09-14
2019-09-15 | 2019-09-15 | 2019-09-21
2019-09-22 | 2019-09-22 | 2019-09-28
2019-09-29 | 2019-09-29 | 2019-10-05
2019-10-06 | 2019-10-06 | 2019-10-12
2019-10-13 | 2019-10-13 | 2019-10-19
2019-10-20 | 2019-10-20 | 2019-10-26
2019-10-27 | 2019-10-27 | 2019-11-02
2019-11-03 | 2019-11-03 | 2019-11-09
2019-11-10 | 2019-11-10 | 2019-11-16
2019-11-17 | 2019-11-17 | 2019-11-23
2019-11-24 | 2019-11-24 | 2019-11-30
2019-12-01 | 2019-12-01 | 2019-12-07
2019-12-08 | 2019-12-08 | 2019-12-14
2019-12-15 | 2019-12-15 | 2019-12-21
2019-12-22 | 2019-12-22 | 2019-12-28
2019-12-29 | 2019-12-29 | 2020-01-04
2020-01-05 | 2020-01-05 | 2020-01-11
2020-01-12 | 2020-01-12 | 2020-01-18
2020-01-19 | 2020-01-19 | 2020-01-25
2020-01-26 | 2020-01-26 | 2020-02-01
2020-02-02 | 2020-02-02 | 2020-02-08
2020-02-09 | 2020-02-09 | 2020-02-15
2020-02-16 | 2020-02-16 | 2020-02-22
2020-02-23 | 2020-02-23 | 2020-02-29
2020-03-01 | 2020-03-01 | 2020-03-07
2020-03-08 | 2020-03-08 | 2020-03-14
2020-03-15 | 2020-03-15 | 2020-03-21
2020-03-22 | 2020-03-22 | 2020-03-28
2020-03-29 | 2020-03-29 | 2020-04-04
2020-04-05 | 2020-04-05 | 2020-04-11
2020-04-12 | 2020-04-12 | 2020-04-18
2020-04-19 | 2020-04-19 | 2020-04-25
2020-04-26 | 2020-04-26 | 2020-05-02
2020-05-03 | 2020-05-03 | 2020-05-09
2020-05-10 | 2020-05-10 | 2020-05-16
2020-05-17 | 2020-05-17 | 2020-05-23
2020-05-24 | 2020-05-24 | 2020-05-30
2020-05-31 | 2020-05-31 | 2020-06-06
2020-06-07 | 2020-06-07 | 2020-06-13
2020-06-14 | 2020-06-14 | 2020-06-20
2020-06-21 | 2020-06-21 | 2020-06-27
2020-06-28 | 2020-06-28 | 2020-07-04
2020-07-05 | 2020-07-05 | 2020-07-11
2020-07-12 | 2020-07-12 | 2020-07-18
2020-07-19 | 2020-07-19 | 2020-07-25
2020-07-26 | 2020-07-26 | 2020-08-01
2020-08-02 | 2020-08-02 | 2020-08-08
2020-08-09 | 2020-08-09 | 2020-08-15
2020-08-16 | 2020-08-16 | 2020-08-22
2020-08-23 | 2020-08-23 | 2020-08-29
2020-08-30 | 2020-08-30 | 2020-09-05
2020-09-06 | 2020-09-06 | 2020-09-12
2020-09-13 | 2020-09-13 | 2020-09-19
2020-09-20 | 2020-09-20 | 2020-09-26
2020-09-27 | 2020-09-27 | 2020-10-03
2020-10-04 | 2020-10-04 | 2020-10-10
2020-10-11 | 2020-10-11 | 2020-10-17
2020-10-18 | 2020-10-18 | 2020-10-24
2020-10-25 | 2020-10-25 | 2020-10-31
2020-11-01 | 2020-11-01 | 2020-11-07
2020-11-08 | 2020-11-08 | 2020-11-14
2020-11-15 | 2020-11-15 | 2020-11-21
2020-11-22 | 2020-11-22 | 2020-11-28
2020-11-29 | 2020-11-29 | 2020-12-05
2020-12-06 | 2020-12-06 | 2020-12-12
2020-12-13 | 2020-12-13 | 2020-12-19
2020-12-20 | 2020-12-20 | 2020-12-26
2020-12-27 | 2020-12-27 | 2021-01-02
2021-01-03 | 2021-01-03 | 2021-01-09
2021-01-10 | 2021-01-10 | 2021-01-16
2021-01-17 | 2021-01-17 | 2021-01-23
2021-01-24 | 2021-01-24 | 2021-01-30
2021-01-31 | 2021-01-31 | 2021-02-06
2021-02-07 | 2021-02-07 | 2021-02-13
2021-02-14 | 2021-02-14 | 2021-02-20
2021-02-21 | 2021-02-21 | 2021-02-27
2021-02-28 | 2021-02-28 | 2021-03-06
2021-03-07 | 2021-03-07 | 2021-03-13
2021-03-14 | 2021-03-14 | 2021-03-20
2021-03-21 | 2021-03-21 | 2021-03-27
2021-03-28 | 2021-03-28 | 2021-04-03
2021-04-04 | 2021-04-04 | 2021-04-10
2021-04-11 | 2021-04-11 | 2021-04-17
2021-04-18 | 2021-04-18 | 2021-04-24
2021-04-25 | 2021-04-25 | 2021-05-01
2021-05-02 | 2021-05-02 | 2021-05-08
2021-05-09 | 2021-05-09 | 2021-05-15
2021-05-16 | 2021-05-16 | 2021-05-22
2021-05-23 | 2021-05-23 | 2021-05-29
2021-05-30 | 2021-05-30 | 2021-06-05
2021-06-06 | 2021-06-06 | 2021-06-12
2021-06-13 | 2021-06-13 | 2021-06-19
2021-06-20 | 2021-06-20 | 2021-06-26
2021-06-27 | 2021-06-27 | 2021-07-03
2021-07-04 | 2021-07-04 | 2021-07-10
2021-07-11 | 2021-07-11 | 2021-07-17
2021-07-18 | 2021-07-18 | 2021-07-24
2021-07-25 | 2021-07-25 | 2021-07-31
2021-08-01 | 2021-08-01 | 2021-08-07
2021-08-08 | 2021-08-08 | 2021-08-14
2021-08-15 | 2021-08-15 | 2021-08-21
2021-08-22 | 2021-08-22 | 2021-08-28
2021-08-29 | 2021-08-29 | 2021-09-04
2021-09-05 | 2021-09-05 | 2021-09-11
2021-09-12 | 2021-09-12 | 2021-09-18
2021-09-19 | 2021-09-19 | 2021-09-25
2021-09-26 | 2021-09-26 | 2021-10-02
2021-10-03 | 2021-10-03 | 2021-10-09
2021-10-10 | 2021-10-10 | 2021-10-16
2021-10-17 | 2021-10-17 | 2021-10-23
2021-10-24 | 2021-10-24 | 2021-10-30
2021-10-31 | 2021-10-31 | 2021-11-06
2021-11-07 | 2021-11-07 | 2021-11-13
2021-11-14 | 2021-11-14 | 2021-11-20
2021-11-21 | 2021-11-21 | 2021-11-27
2021-11-28 | 2021-11-28 | 2021-12-04
2021-12-05 | 2021-12-05 | 2021-12-11
2021-12-12 | 2021-12-12 | 2021-12-18
2021-12-19 | 2021-12-19 | 2021-12-25
2021-12-26 | 2021-12-26 | 2022-01-01
2022-01-02 | 2022-01-02 | 2022-01-08
2022-01-09 | 2022-01-09 | 2022-01-15
2022-01-16 | 2022-01-16 | 2022-01-22
2022-01-23 | 2022-01-23 | 2022-01-29
2022-01-30 | 2022-01-30 | 2022-02-05
2022-02-06 | 2022-02-06 | 2022-02-12
2022-02-13 | 2022-02-13 | 2022-02-19
2022-02-20 | 2022-02-20 | 2022-02-26
2022-02-27 | 2022-02-27 | 2022-03-05
2022-03-06 | 2022-03-06 | 2022-03-12
2022-03-13 | 2022-03-13 | 2022-03-19
2022-03-20 | 2022-03-20 | 2022-03-26
2022-03-27 | 2022-03-27 | 2022-04-02
2022-04-03 | 2022-04-03 | 2022-04-09
2022-04-10 | 2022-04-10 | 2022-04-16
Formulas:
Week Of = [Week Start]
Planned = IF(TODAY()>=[Week Of],COUNTIFS('Tracking Data'!L$3:L1000,"<="&[Week End],'Tracking Data'!M$3:M1000,"="&""),"")
Analysis In = IF(TODAY()>=[Week Of],COUNTIFS('Tracking Data'!M$3:M1000,"<="&[Week End],'Tracking Data'!N$3:N1000,"="&""),"")
Analysis Out = IF(TODAY()>=[Week Of],COUNTIFS('Tracking Data'!N$3:N1000,"<="&[Week End],'Tracking Data'!O$3:O1000,"="&""),"")
Execution In = IF(TODAY()>=[Week Of],COUNTIFS('Tracking Data'!O$3:O1000,"<="&[Week End],'Tracking Data'!P$3:P1000,"="&""),"")
Execution Out = IF(TODAY()>=[Week Of],COUNTIFS('Tracking Data'!P$3:P1000,"<="&[Week End],'Tracking Data'!Q$3:Q1000,"="&""),"")
Validation In = IF(TODAY()>=[Week Of],COUNTIFS('Tracking Data'!Q$3:Q1000,"<="&[Week End],'Tracking Data'!R$3:R1000,"="&""),"")
Validation Out = IF(TODAY()>=[Week Of],COUNTIFS('Tracking Data'!R$3:R1000,"<="&[Week End],'Tracking Data'!S$3:S1000,"="&""),"")

## Board Active (hidden)
ID | Task | Class of Service | Size | Planned | Analysis | 3 | Execution | 2 | Validation | 1 | Done | Planned Duration | Planned Done
ID |  |  |  | 2 | In | Out | In | Out | In | Out |  |  |  | Alert Status
SPM1 | Sample Task 1 | Standard | 2 days | [8 empty] | 2 | 2017-03-10 | 2017-03-10
SPM2 | Sample Task 2 | Standard | 2 days |  |  |  |  | 1 |  |  |  | 2 | 2017-03-10 | 2017-03-10
SPM3 | Sample Task 3 | Standard | 2 days |  | 1 | [6 empty] | 2 | 2017-03-10 | 2017-03-10
SPM4 | Sample Task 4 | Standard | <= 1 week | [5 empty] | 1 |  |  | 5 | 2017-03-10 | 2017-03-10
SPM5 | Sample Task 5 | Standard | 3 days | [7 empty] | 1 | 3 | 2017-03-08 | 2017-03-08
SPM6 | Sample Task 6 | Standard | <= 1 day | [7 empty] | 1 | 0 | 2017-03-06 | 2017-03-06
SPM7 | Sample Task 7 | Standard | 3 days | [7 empty] | 1 | 3 | 2017-03-07 | 2017-03-05
SPM8 | Sample Task 8 | Standard | 3 days |  |  |  | 1 |  |  |  |  | 3 | 2017-03-14 | 2017-03-14
SPM9 | Sample Task 9 | Standard | <= 2 weeks | 1 | [7 empty] | 10 | 2017-03-28 | 2017-03-28
SPM10 | Sample Task 10 | Standard | <= 1 week |  | 1 | [6 empty] | 5 | 2017-03-21 | 2017-03-21
SPM11 | Sample Task 11 | Standard | 3 days | 1 | [7 empty] | 3 | 2017-03-17 | 2017-03-17
SPM12 | Sample Task 12 | Fixed Date | <= 1 week | [8 empty] | 5 | 2017-03-21 | 2017-03-21
SPM13 | Sample Task 13 |  | <= 2 weeks | [8 empty] | 10 | 1900-01-12 | 1900-01-12
SPM14 | Sample Task 14 |  | <= 2 weeks | [8 empty] | 10 | 1900-01-12 | 1900-01-12
SPM15 | Sample Task 15 |  | <= 1 week | [8 empty] | 5 | 1900-01-05 | 1900-01-05
SPM16 | Sample Task 16 |  | <= 1 week | [8 empty] | 5 | 1900-01-05 | 1900-01-05
SPM17 | Sample Task 17 |  | <= 2 weeks | [8 empty] | 10 | 1900-01-12 | 1900-01-12
SPM18 | Sample Task 18 | Standard | <= 2 weeks |  | 1 | [6 empty] | 10 | 2017-03-29 | 2017-03-29
SPM19 | Sample Task 19 |  | <= 1 week | [8 empty] | 5 | 1900-01-05 | 1900-01-05
SPM20 | Sample Task 20 | Expedite | 2 days | [7 empty] | 1 | 2 | 2017-03-16 | 2017-03-15
SPM21 | Sample Task 21 | Expedite | 2 days | [7 empty] | 1 | 2 | 2017-03-16 | 2017-03-15
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!
[12 empty] | FALSE | #VALUE! | #VALUE!

## Daily Tracking (hidden)
Day | Planned | Analysis In | Analysis Out | Analysis | Execution In | Execution Out | Execution | Validation In | Validation Out | Validation | Done | Daily WIP
2017-03-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
2017-03-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1
2017-03-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
2017-03-08 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2
2017-03-09 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1
2017-03-10 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 3 | 2
2017-03-11 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 3 | 2
2017-03-12 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 3 | 2
2017-03-13 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 3 | 2
2017-03-14 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 3 | 5
2017-03-15 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 5 | 8
2017-03-16 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 5 | 6
2017-03-17 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 5 | 6
2017-03-18 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 5 | 6
2017-03-19 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 5 | 6
2017-03-20 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 5 | 6
2017-03-21 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 5 | 6
2017-03-22 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 5 | 6
2017-03-23 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 5 | 6
2017-03-24 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 5 | 6
2017-03-25 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 5 | 6
2017-03-26 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 5 | 6
2017-03-27 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 5 | 6
2017-03-28 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 5 | 6
2017-03-29 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 5 | 6
2017-03-30 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 5 | 6
2017-03-31 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 5 | 6
2017-04-01
2017-04-02
2017-04-03
2017-04-04
2017-04-05
2017-04-06
2017-04-07
2017-04-08
2017-04-09
2017-04-10
2017-04-11
2017-04-12
2017-04-13
2017-04-14
2017-04-15
2017-04-16
2017-04-17
2017-04-18
2017-04-19
2017-04-20
2017-04-21
2017-04-22
2017-04-23
2017-04-24
2017-04-25
2017-04-26
2017-04-27
2017-04-28
2017-04-29
2017-04-30
2017-05-01
2017-05-02
2017-05-03
2017-05-04
2017-05-05
2017-05-06
2017-05-07
2017-05-08
2017-05-09
2017-05-10
2017-05-11
2017-05-12
2017-05-13
2017-05-14
2017-05-15
2017-05-16
2017-05-17
2017-05-18
2017-05-19
2017-05-20
2017-05-21
2017-05-22
2017-05-23
2017-05-24
2017-05-25
2017-05-26
2017-05-27
2017-05-28
2017-05-29
2017-05-30
2017-05-31
2017-06-01
2017-06-02
2017-06-03
2017-06-04
2017-06-05
2017-06-06
2017-06-07
2017-06-08
2017-06-09
2017-06-10
2017-06-11
2017-06-12
2017-06-13
2017-06-14
2017-06-15
2017-06-16
2017-06-17
2017-06-18
2017-06-19
2017-06-20
2017-06-21
2017-06-22
2017-06-23
2017-06-24
2017-06-25
2017-06-26
2017-06-27
2017-06-28
2017-06-29
2017-06-30
2017-07-01
2017-07-02
2017-07-03
2017-07-04
2017-07-05
2017-07-06
2017-07-07
2017-07-08
2017-07-09
2017-07-10
2017-07-11
2017-07-12
2017-07-13
2017-07-14
2017-07-15
2017-07-16
2017-07-17
2017-07-18
2017-07-19
2017-07-20
2017-07-21
2017-07-22
2017-07-23
2017-07-24
2017-07-25
2017-07-26
2017-07-27
2017-07-28
2017-07-29
2017-07-30
2017-07-31
2017-08-01
2017-08-02
2017-08-03
2017-08-04
2017-08-05
2017-08-06
2017-08-07
2017-08-08
2017-08-09
2017-08-10
2017-08-11
2017-08-12
2017-08-13
2017-08-14
2017-08-15
2017-08-16
2017-08-17
2017-08-18
2017-08-19
2017-08-20
2017-08-21
2017-08-22
2017-08-23
2017-08-24
2017-08-25
2017-08-26
2017-08-27
2017-08-28
2017-08-29
2017-08-30
2017-08-31
2017-09-01
2017-09-02
2017-09-03
2017-09-04
2017-09-05
2017-09-06
2017-09-07
2017-09-08
2017-09-09
2017-09-10
2017-09-11
2017-09-12
2017-09-13
2017-09-14
2017-09-15
2017-09-16
2017-09-17
2017-09-18
2017-09-19
2017-09-20
2017-09-21
2017-09-22
2017-09-23
2017-09-24
2017-09-25
2017-09-26
2017-09-27
2017-09-28
2017-09-29
2017-09-30
2017-10-01
2017-10-02
2017-10-03
2017-10-04
2017-10-05
2017-10-06
2017-10-07
2017-10-08
2017-10-09
2017-10-10
2017-10-11
2017-10-12
2017-10-13
2017-10-14
2017-10-15
2017-10-16
2017-10-17
2017-10-18
2017-10-19
2017-10-20
2017-10-21
2017-10-22
2017-10-23
2017-10-24
2017-10-25
2017-10-26
2017-10-27
2017-10-28
2017-10-29
2017-10-30
2017-10-31
2017-11-01
2017-11-02
2017-11-03
2017-11-04
2017-11-05
2017-11-06
2017-11-07
2017-11-08
2017-11-09
2017-11-10
2017-11-11
2017-11-12
2017-11-13
2017-11-14
2017-11-15
2017-11-16
2017-11-17
2017-11-18
2017-11-19
2017-11-20
2017-11-21
2017-11-22
2017-11-23
2017-11-24
2017-11-25
2017-11-26
2017-11-27
2017-11-28
2017-11-29
2017-11-30
2017-12-01
2017-12-02
2017-12-03
2017-12-04
2017-12-05
2017-12-06
2017-12-07
2017-12-08
2017-12-09
2017-12-10
2017-12-11
2017-12-12
2017-12-13
2017-12-14
2017-12-15
2017-12-16
2017-12-17
2017-12-18
2017-12-19
2017-12-20
2017-12-21
2017-12-22
2017-12-23
2017-12-24
2017-12-25
2017-12-26
2017-12-27
2017-12-28
2017-12-29
2017-12-30
2017-12-31
2018-01-01
2018-01-02
2018-01-03
2018-01-04
2018-01-05
2018-01-06
2018-01-07
2018-01-08
2018-01-09
2018-01-10
2018-01-11
2018-01-12
2018-01-13
2018-01-14
2018-01-15
2018-01-16
2018-01-17
2018-01-18
2018-01-19
2018-01-20
2018-01-21
2018-01-22
2018-01-23
2018-01-24
2018-01-25
2018-01-26
2018-01-27
2018-01-28
2018-01-29
2018-01-30
2018-01-31
2018-02-01
2018-02-02
2018-02-03
2018-02-04
2018-02-05
2018-02-06
2018-02-07
2018-02-08
2018-02-09
2018-02-10
2018-02-11
2018-02-12
2018-02-13
2018-02-14
2018-02-15
2018-02-16
2018-02-17
2018-02-18
2018-02-19
2018-02-20
2018-02-21
2018-02-22
2018-02-23
2018-02-24
2018-02-25
2018-02-26
2018-02-27
2018-02-28
2018-03-01
2018-03-02
2018-03-03
2018-03-04
2018-03-05
2018-03-06
2018-03-07
2018-03-08
2018-03-09
2018-03-10
2018-03-11
2018-03-12
2018-03-13
2018-03-14
2018-03-15
2018-03-16
2018-03-17
2018-03-18
2018-03-19
2018-03-20
2018-03-21
2018-03-22
2018-03-23
2018-03-24
2018-03-25
2018-03-26
2018-03-27
2018-03-28
2018-03-29
2018-03-30
2018-03-31
2018-04-01
2018-04-02
2018-04-03
2018-04-04
2018-04-05
2018-04-06
2018-04-07
2018-04-08
2018-04-09
2018-04-10
2018-04-11
2018-04-12
2018-04-13
2018-04-14
2018-04-15
2018-04-16
2018-04-17
2018-04-18
2018-04-19
2018-04-20
2018-04-21
2018-04-22
2018-04-23
2018-04-24
2018-04-25
2018-04-26
2018-04-27
2018-04-28
2018-04-29
2018-04-30
2018-05-01
2018-05-02
2018-05-03
2018-05-04
2018-05-05
2018-05-06
2018-05-07
2018-05-08
2018-05-09
2018-05-10
2018-05-11
2018-05-12
2018-05-13
2018-05-14
2018-05-15
2018-05-16
2018-05-17
2018-05-18
2018-05-19
2018-05-20
2018-05-21
2018-05-22
2018-05-23
2018-05-24
2018-05-25
2018-05-26
2018-05-27
2018-05-28
2018-05-29
2018-05-30
2018-05-31
2018-06-01
2018-06-02
2018-06-03
2018-06-04
2018-06-05
2018-06-06
2018-06-07
2018-06-08
2018-06-09
2018-06-10
2018-06-11
2018-06-12
2018-06-13
2018-06-14
2018-06-15
2018-06-16
2018-06-17
2018-06-18
2018-06-19
2018-06-20
2018-06-21
2018-06-22
2018-06-23
2018-06-24
2018-06-25
2018-06-26
2018-06-27
2018-06-28
2018-06-29
2018-06-30
2018-07-01
2018-07-02
2018-07-03
2018-07-04
2018-07-05
2018-07-06
2018-07-07
2018-07-08
2018-07-09
2018-07-10
2018-07-11
2018-07-12
2018-07-13
2018-07-14
2018-07-15
2018-07-16
2018-07-17
2018-07-18
2018-07-19
2018-07-20
2018-07-21
2018-07-22
2018-07-23
2018-07-24
2018-07-25
2018-07-26
2018-07-27
2018-07-28
2018-07-29
2018-07-30
2018-07-31
2018-08-01
2018-08-02
2018-08-03
2018-08-04
2018-08-05
2018-08-06
2018-08-07
2018-08-08
2018-08-09
2018-08-10
2018-08-11
2018-08-12
2018-08-13
2018-08-14
2018-08-15
2018-08-16
2018-08-17
2018-08-18
2018-08-19
2018-08-20
2018-08-21
2018-08-22
2018-08-23
2018-08-24
2018-08-25
2018-08-26
2018-08-27
2018-08-28
2018-08-29
2018-08-30
2018-08-31
2018-09-01
2018-09-02
2018-09-03
2018-09-04
2018-09-05
2018-09-06
2018-09-07
2018-09-08
2018-09-09
2018-09-10
2018-09-11
2018-09-12
2018-09-13
2018-09-14
2018-09-15
2018-09-16
2018-09-17
2018-09-18
2018-09-19
2018-09-20
2018-09-21
2018-09-22
2018-09-23
2018-09-24
2018-09-25
2018-09-26
2018-09-27
2018-09-28
2018-09-29
2018-09-30
2018-10-01
2018-10-02
2018-10-03
2018-10-04
2018-10-05
2018-10-06
2018-10-07
2018-10-08
2018-10-09
2018-10-10
2018-10-11
2018-10-12
2018-10-13
2018-10-14
2018-10-15
2018-10-16
2018-10-17
2018-10-18
2018-10-19
2018-10-20
2018-10-21
2018-10-22
2018-10-23
2018-10-24
2018-10-25
2018-10-26
2018-10-27
2018-10-28
2018-10-29
2018-10-30
2018-10-31
2018-11-01
2018-11-02
2018-11-03
2018-11-04
2018-11-05
2018-11-06
2018-11-07
2018-11-08
2018-11-09
2018-11-10
2018-11-11
2018-11-12
2018-11-13
2018-11-14
2018-11-15
2018-11-16
2018-11-17
2018-11-18
2018-11-19
2018-11-20
2018-11-21
2018-11-22
2018-11-23
2018-11-24
2018-11-25
2018-11-26
2018-11-27
Formulas:
Planned = IF(TODAY()>=[Day],COUNTIFS('Tracking Data'!L$3:L1000,"<="&[Day],'Tracking Data'!M$3:M1000,"="&""),"")
Analysis In = IF(TODAY()>=[Day],COUNTIFS('Tracking Data'!M$3:M1000,"<="&[Planned],'Tracking Data'!N$3:N1000,"="&""),"")
Analysis Out = IF(TODAY()>=[Day],COUNTIFS('Tracking Data'!N$3:N1000,"<="&[Analysis In],'Tracking Data'!O$3:O1000,"="&""),"")
Execution In = IF(TODAY()>=[Day],COUNTIFS('Tracking Data'!O$3:O1000,"<="&[Day],'Tracking Data'!P$3:P1000,"="&""),"")
Execution Out = IF(TODAY()>=[Day],COUNTIFS('Tracking Data'!P$3:P1000,"<="&[Planned],'Tracking Data'!Q$3:Q1000,"="&""),"")
Validation In = IF(TODAY()>=[Day],COUNTIFS('Tracking Data'!Q$3:Q1000,"<="&[Day],'Tracking Data'!R$3:R1000,"="&""),"")
Validation Out = IF(TODAY()>=[Day],COUNTIFS('Tracking Data'!R$3:R1000,"<="&[Planned],'Tracking Data'!S$3:S1000,"="&""),"")
Done = IF(TODAY()>=[Day],COUNTIFS('Tracking Data'!S$3:S1000,"<="&[Day]),"")
Daily WIP = IF(TODAY()>=[Day],[Planned]+[Analysis]+[Execution]+[Validation]+[Done],"")
Daily WIP = IF(TODAY()>=[Day],[Planned]+[Analysis]+[Execution]+[Validation]+[Done]-[Done, row above],"")

## Monthly Summary
Month Of | Month Start | Month End | Planned | Analysis In | Analysis Out | Analysis | Execution In | Execution Out | Execution | Validation In | Validation Out | Validation | Done | Done | Average Cycle Time
2017-03-01 | 2017-03-01 | 2017-03-31 | 4 | 3 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 5 | 5 | 1.75
2017-04-01 | 2017-04-01 | 2017-04-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-05-01 | 2017-05-01 | 2017-05-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-06-01 | 2017-06-01 | 2017-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-07-01 | 2017-07-01 | 2017-07-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-08-01 | 2017-08-01 | 2017-08-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-09-01 | 2017-09-01 | 2017-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-10-01 | 2017-10-01 | 2017-10-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-11-01 | 2017-11-01 | 2017-11-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-01 | 2017-12-01 | 2017-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-01-01 | 2018-01-01 | 2018-01-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-02-01 | 2018-02-01 | 2018-02-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-03-01 | 2018-03-01 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-04-01 | 2018-04-01 | 2018-04-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-05-01 | 2018-05-01 | 2018-05-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-06-01 | 2018-06-01 | 2018-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-07-01 | 2018-07-01 | 2018-07-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-08-01 | 2018-08-01 | 2018-08-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-09-01 | 2018-09-01 | 2018-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-10-01 | 2018-10-01 | 2018-10-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-11-01 | 2018-11-01 | 2018-11-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-12-01 | 2018-12-01 | 2018-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2019-01-01 | 2019-01-01 | 2019-01-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2019-02-01 | 2019-02-01 | 2019-02-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2019-03-01 | 2019-03-01 | 2019-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2019-04-01 | 2019-04-01 | 2019-04-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2019-05-01 | 2019-05-01 | 2019-05-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2019-06-01 | 2019-06-01 | 2019-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2019-07-01 | 2019-07-01 | 2019-07-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2019-08-01 | 2019-08-01 | 2019-08-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2019-09-01 | 2019-09-01 | 2019-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2019-10-01 | 2019-10-01 | 2019-10-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2019-11-01 | 2019-11-01 | 2019-11-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2019-12-01 | 2019-12-01 | 2019-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020-01-01 | 2020-01-01 | 2020-01-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020-02-01 | 2020-02-01 | 2020-02-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020-03-01 | 2020-03-01 | 2020-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020-04-01 | 2020-04-01 | 2020-04-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020-05-01 | 2020-05-01 | 2020-05-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020-06-01 | 2020-06-01 | 2020-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020-07-01 | 2020-07-01 | 2020-07-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020-08-01 | 2020-08-01 | 2020-08-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020-09-01 | 2020-09-01 | 2020-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
Month End = [Month Start, row below]-1
Done = IF(TODAY()>=[Month Start],COUNTIFS('Tracking Data'!S$3:S1000,">"&'Monthly Summary'!$[Month Start],'Tracking Data'!S$3:S1000,"<"&'Monthly Summary'!$[Month End]),"")

## Days To Done (hidden)
ID | Task | Class of Service | Size | Planned | Planned Days to Done | Planned Done | Minimum Done | Days to Done
ID
SPM1 | Sample Task 1 | Standard | S | 2017-03-08 | 2 | 2017-03-10 | 2017-03-31 | 18
SPM2 | Sample Task 2 | Standard | S | 2017-03-08 | 2 | 2017-03-10 | 2017-03-31 | 18
SPM3 | Sample Task 3 | Standard | S | 2017-03-08 | 2 | 2017-03-10 | 2017-03-31 | 18
SPM4 | Sample Task 4 | Standard | L | 2017-03-03 | 5 | 2017-03-10 | 2017-03-31 | 21
SPM5 | Sample Task 5 | Standard | M | 2017-03-03 | 3 | 2017-03-08 | 2017-03-08 | 4
SPM6 | Sample Task 6 | Standard | XS | 2017-03-06 | 1 | 2017-03-07 | 2017-03-06 | 1
SPM7 | Sample Task 7 | Standard | M | 2017-03-02 | 3 | 2017-03-07 | 2017-03-05 | 2
SPM8 | Sample Task 8 | Standard | M | 2017-03-09 | 3 | 2017-03-14 | 2017-03-31 | 17
SPM9 | Sample Task 9 | Standard | XL | 2017-03-14 | 10 | 2017-03-28 | 2017-03-31 | 14
SPM10 | Sample Task 10 | Standard | L | 2017-03-14 | 5 | 2017-03-21 | 2017-03-31 | 14
SPM11 | Sample Task 11 | Standard | M | 2017-03-14 | 3 | 2017-03-17 | 2017-03-31 | 14
SPM12 | Sample Task 12 | Fixed Date | L | 2017-03-14 | 5 | 2017-03-21 | 2017-03-31 | 14
SPM13 | Sample Task 13 |  | XL
SPM14 | Sample Task 14 |  | XL
SPM15 | Sample Task 15 |  | L
SPM16 | Sample Task 16 |  | L
SPM17 | Sample Task 17 |  | XL
SPM18 | Sample Task 18 | Standard | XL | 2017-03-15 |  |  | 2017-03-31 | 13
SPM19 | Sample Task 19 |  | L
SPM20 | Sample Task 20 | Expedite | S | 2017-03-14 |  |  | 2017-03-15 | 2
SPM21 | Sample Task 21 | Expedite | S | 2017-03-14 |  |  | 2017-03-15 | 2
Formulas:
Planned Done = WORKDAY([Planned],[Planned Days to Done])
Minimum Done = IF([Planned]<>"",IF('Tracking Data'!S3<>"",'Tracking Data'!S3,TODAY()),"")
Days to Done = IF([Minimum Done]<>"",NETWORKDAYS([Planned],[Minimum Done]),"")

## Weekly Done (hidden)
Week Of | Week Start | Week End | Σ XS | XS | Σ S | S | Σ M | M | Σ L | L | Σ XL | XL
2017-03-05 | 2017-03-05 | 2017-03-11 | 1 | 1 | 0 | 0 | 6 | 3 | 0 | 0 | 0 | 0
2017-03-12 | 2017-03-12 | 2017-03-18 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0
2017-03-19 | 2017-03-19 | 2017-03-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-03-26 | 2017-03-26 | 2017-04-01 | 0 | 0 | 54 | 18 | 31 | 15.5 | 49 | 16.3333 | 27 | 13.5
2017-04-02 | 2017-04-02 | 2017-04-08
2017-04-09 | 2017-04-09 | 2017-04-15
2017-04-16 | 2017-04-16 | 2017-04-22
2017-04-23 | 2017-04-23 | 2017-04-29
2017-04-30 | 2017-04-30 | 2017-05-06
2017-05-07 | 2017-05-07 | 2017-05-13
2017-05-14 | 2017-05-14 | 2017-05-20
2017-05-21 | 2017-05-21 | 2017-05-27
2017-05-28 | 2017-05-28 | 2017-06-03
2017-06-04 | 2017-06-04 | 2017-06-10
2017-06-11 | 2017-06-11 | 2017-06-17
2017-06-18 | 2017-06-18 | 2017-06-24
2017-06-25 | 2017-06-25 | 2017-07-01
2017-07-02 | 2017-07-02 | 2017-07-08
2017-07-09 | 2017-07-09 | 2017-07-15
2017-07-16 | 2017-07-16 | 2017-07-22
2017-07-23 | 2017-07-23 | 2017-07-29
2017-07-30 | 2017-07-30 | 2017-08-05
2017-08-06 | 2017-08-06 | 2017-08-12
2017-08-13 | 2017-08-13 | 2017-08-19
2017-08-20 | 2017-08-20 | 2017-08-26
2017-08-27 | 2017-08-27 | 2017-09-02
2017-09-03 | 2017-09-03 | 2017-09-09
2017-09-10 | 2017-09-10 | 2017-09-16
2017-09-17 | 2017-09-17 | 2017-09-23
2017-09-24 | 2017-09-24 | 2017-09-30
2017-10-01 | 2017-10-01 | 2017-10-07
2017-10-08 | 2017-10-08 | 2017-10-14
2017-10-15 | 2017-10-15 | 2017-10-21
2017-10-22 | 2017-10-22 | 2017-10-28
2017-10-29 | 2017-10-29 | 2017-11-04
2017-11-05 | 2017-11-05 | 2017-11-11
2017-11-12 | 2017-11-12 | 2017-11-18
2017-11-19 | 2017-11-19 | 2017-11-25
2017-11-26 | 2017-11-26 | 2017-12-02
2017-12-03 | 2017-12-03 | 2017-12-09
2017-12-10 | 2017-12-10 | 2017-12-16
2017-12-17 | 2017-12-17 | 2017-12-23
2017-12-24 | 2017-12-24 | 2017-12-30
2017-12-31 | 2017-12-31 | 2018-01-06
2018-01-07 | 2018-01-07 | 2018-01-13
2018-01-14 | 2018-01-14 | 2018-01-20
2018-01-21 | 2018-01-21 | 2018-01-27
2018-01-28 | 2018-01-28 | 2018-02-03
2018-02-04 | 2018-02-04 | 2018-02-10
2018-02-11 | 2018-02-11 | 2018-02-17
2018-02-18 | 2018-02-18 | 2018-02-24
2018-02-25 | 2018-02-25 | 2018-03-03
2018-03-04 | 2018-03-04 | 2018-03-10
2018-03-11 | 2018-03-11 | 2018-03-17
2018-03-18 | 2018-03-18 | 2018-03-24
2018-03-25 | 2018-03-25 | 2018-03-31
2018-04-01 | 2018-04-01 | 2018-04-07
2018-04-08 | 2018-04-08 | 2018-04-14
2018-04-15 | 2018-04-15 | 2018-04-21
2018-04-22 | 2018-04-22 | 2018-04-28
2018-04-29 | 2018-04-29 | 2018-05-05
2018-05-06 | 2018-05-06 | 2018-05-12
2018-05-13 | 2018-05-13 | 2018-05-19
2018-05-20 | 2018-05-20 | 2018-05-26
2018-05-27 | 2018-05-27 | 2018-06-02
2018-06-03 | 2018-06-03 | 2018-06-09
2018-06-10 | 2018-06-10 | 2018-06-16
2018-06-17 | 2018-06-17 | 2018-06-23
2018-06-24 | 2018-06-24 | 2018-06-30
2018-07-01 | 2018-07-01 | 2018-07-07
2018-07-08 | 2018-07-08 | 2018-07-14
2018-07-15 | 2018-07-15 | 2018-07-21
2018-07-22 | 2018-07-22 | 2018-07-28
2018-07-29 | 2018-07-29 | 2018-08-04
2018-08-05 | 2018-08-05 | 2018-08-11
2018-08-12 | 2018-08-12 | 2018-08-18
2018-08-19 | 2018-08-19 | 2018-08-25
2018-08-26 | 2018-08-26 | 2018-09-01
2018-09-02 | 2018-09-02 | 2018-09-08
2018-09-09 | 2018-09-09 | 2018-09-15
2018-09-16 | 2018-09-16 | 2018-09-22
2018-09-23 | 2018-09-23 | 2018-09-29
2018-09-30 | 2018-09-30 | 2018-10-06
2018-10-07 | 2018-10-07 | 2018-10-13
2018-10-14 | 2018-10-14 | 2018-10-20
2018-10-21 | 2018-10-21 | 2018-10-27
2018-10-28 | 2018-10-28 | 2018-11-03
2018-11-04 | 2018-11-04 | 2018-11-10
2018-11-11 | 2018-11-11 | 2018-11-17
2018-11-18 | 2018-11-18 | 2018-11-24
2018-11-25 | 2018-11-25 | 2018-12-01
2018-12-02 | 2018-12-02 | 2018-12-08
2018-12-09 | 2018-12-09 | 2018-12-15
2018-12-16 | 2018-12-16 | 2018-12-22
2018-12-23 | 2018-12-23 | 2018-12-29
2018-12-30 | 2018-12-30 | 2019-01-05
2019-01-06 | 2019-01-06 | 2019-01-12
2019-01-13 | 2019-01-13 | 2019-01-19
2019-01-20 | 2019-01-20 | 2019-01-26
2019-01-27 | 2019-01-27 | 2019-02-02
2019-02-03 | 2019-02-03 | 2019-02-09
2019-02-10 | 2019-02-10 | 2019-02-16
2019-02-17 | 2019-02-17 | 2019-02-23
2019-02-24 | 2019-02-24 | 2019-03-02
2019-03-03 | 2019-03-03 | 2019-03-09
2019-03-10 | 2019-03-10 | 2019-03-16
2019-03-17 | 2019-03-17 | 2019-03-23
2019-03-24 | 2019-03-24 | 2019-03-30
2019-03-31 | 2019-03-31 | 2019-04-06
2019-04-07 | 2019-04-07 | 2019-04-13
2019-04-14 | 2019-04-14 | 2019-04-20
2019-04-21 | 2019-04-21 | 2019-04-27
2019-04-28 | 2019-04-28 | 2019-05-04
2019-05-05 | 2019-05-05 | 2019-05-11
2019-05-12 | 2019-05-12 | 2019-05-18
2019-05-19 | 2019-05-19 | 2019-05-25
2019-05-26 | 2019-05-26 | 2019-06-01
2019-06-02 | 2019-06-02 | 2019-06-08
2019-06-09 | 2019-06-09 | 2019-06-15
2019-06-16 | 2019-06-16 | 2019-06-22
2019-06-23 | 2019-06-23 | 2019-06-29
2019-06-30 | 2019-06-30 | 2019-07-06
2019-07-07 | 2019-07-07 | 2019-07-13
2019-07-14 | 2019-07-14 | 2019-07-20
2019-07-21 | 2019-07-21 | 2019-07-27
2019-07-28 | 2019-07-28 | 2019-08-03
2019-08-04 | 2019-08-04 | 2019-08-10
2019-08-11 | 2019-08-11 | 2019-08-17
2019-08-18 | 2019-08-18 | 2019-08-24
2019-08-25 | 2019-08-25 | 2019-08-31
2019-09-01 | 2019-09-01 | 2019-09-07
2019-09-08 | 2019-09-08 | 2019-09-14
2019-09-15 | 2019-09-15 | 2019-09-21
2019-09-22 | 2019-09-22 | 2019-09-28
2019-09-29 | 2019-09-29 | 2019-10-05
2019-10-06 | 2019-10-06 | 2019-10-12
2019-10-13 | 2019-10-13 | 2019-10-19
2019-10-20 | 2019-10-20 | 2019-10-26
2019-10-27 | 2019-10-27 | 2019-11-02
2019-11-03 | 2019-11-03 | 2019-11-09
2019-11-10 | 2019-11-10 | 2019-11-16
2019-11-17 | 2019-11-17 | 2019-11-23
2019-11-24 | 2019-11-24 | 2019-11-30
2019-12-01 | 2019-12-01 | 2019-12-07
2019-12-08 | 2019-12-08 | 2019-12-14
2019-12-15 | 2019-12-15 | 2019-12-21
2019-12-22 | 2019-12-22 | 2019-12-28
2019-12-29 | 2019-12-29 | 2020-01-04
2020-01-05 | 2020-01-05 | 2020-01-11
2020-01-12 | 2020-01-12 | 2020-01-18
2020-01-19 | 2020-01-19 | 2020-01-25
2020-01-26 | 2020-01-26 | 2020-02-01
2020-02-02 | 2020-02-02 | 2020-02-08
2020-02-09 | 2020-02-09 | 2020-02-15
2020-02-16 | 2020-02-16 | 2020-02-22
2020-02-23 | 2020-02-23 | 2020-02-29
2020-03-01 | 2020-03-01 | 2020-03-07
2020-03-08 | 2020-03-08 | 2020-03-14
2020-03-15 | 2020-03-15 | 2020-03-21
2020-03-22 | 2020-03-22 | 2020-03-28
2020-03-29 | 2020-03-29 | 2020-04-04
2020-04-05 | 2020-04-05 | 2020-04-11
2020-04-12 | 2020-04-12 | 2020-04-18
2020-04-19 | 2020-04-19 | 2020-04-25
2020-04-26 | 2020-04-26 | 2020-05-02
2020-05-03 | 2020-05-03 | 2020-05-09
2020-05-10 | 2020-05-10 | 2020-05-16
2020-05-17 | 2020-05-17 | 2020-05-23
2020-05-24 | 2020-05-24 | 2020-05-30
2020-05-31 | 2020-05-31 | 2020-06-06
2020-06-07 | 2020-06-07 | 2020-06-13
2020-06-14 | 2020-06-14 | 2020-06-20
2020-06-21 | 2020-06-21 | 2020-06-27
2020-06-28 | 2020-06-28 | 2020-07-04
2020-07-05 | 2020-07-05 | 2020-07-11
2020-07-12 | 2020-07-12 | 2020-07-18
2020-07-19 | 2020-07-19 | 2020-07-25
2020-07-26 | 2020-07-26 | 2020-08-01
2020-08-02 | 2020-08-02 | 2020-08-08
2020-08-09 | 2020-08-09 | 2020-08-15
2020-08-16 | 2020-08-16 | 2020-08-22
2020-08-23 | 2020-08-23 | 2020-08-29
2020-08-30 | 2020-08-30 | 2020-09-05
2020-09-06 | 2020-09-06 | 2020-09-12
2020-09-13 | 2020-09-13 | 2020-09-19
2020-09-20 | 2020-09-20 | 2020-09-26
2020-09-27 | 2020-09-27 | 2020-10-03
2020-10-04 | 2020-10-04 | 2020-10-10
2020-10-11 | 2020-10-11 | 2020-10-17
2020-10-18 | 2020-10-18 | 2020-10-24
2020-10-25 | 2020-10-25 | 2020-10-31
2020-11-01 | 2020-11-01 | 2020-11-07
2020-11-08 | 2020-11-08 | 2020-11-14
2020-11-15 | 2020-11-15 | 2020-11-21
2020-11-22 | 2020-11-22 | 2020-11-28
2020-11-29 | 2020-11-29 | 2020-12-05
2020-12-06 | 2020-12-06 | 2020-12-12
2020-12-13 | 2020-12-13 | 2020-12-19
2020-12-20 | 2020-12-20 | 2020-12-26
2020-12-27 | 2020-12-27 | 2021-01-02
2021-01-03 | 2021-01-03 | 2021-01-09
2021-01-10 | 2021-01-10 | 2021-01-16
2021-01-17 | 2021-01-17 | 2021-01-23
2021-01-24 | 2021-01-24 | 2021-01-30
2021-01-31 | 2021-01-31 | 2021-02-06
2021-02-07 | 2021-02-07 | 2021-02-13
2021-02-14 | 2021-02-14 | 2021-02-20
2021-02-21 | 2021-02-21 | 2021-02-27
2021-02-28 | 2021-02-28 | 2021-03-06
2021-03-07 | 2021-03-07 | 2021-03-13
2021-03-14 | 2021-03-14 | 2021-03-20
2021-03-21 | 2021-03-21 | 2021-03-27
2021-03-28 | 2021-03-28 | 2021-04-03
2021-04-04 | 2021-04-04 | 2021-04-10
2021-04-11 | 2021-04-11 | 2021-04-17
2021-04-18 | 2021-04-18 | 2021-04-24
2021-04-25 | 2021-04-25 | 2021-05-01
2021-05-02 | 2021-05-02 | 2021-05-08
2021-05-09 | 2021-05-09 | 2021-05-15
2021-05-16 | 2021-05-16 | 2021-05-22
2021-05-23 | 2021-05-23 | 2021-05-29
2021-05-30 | 2021-05-30 | 2021-06-05
2021-06-06 | 2021-06-06 | 2021-06-12
2021-06-13 | 2021-06-13 | 2021-06-19
2021-06-20 | 2021-06-20 | 2021-06-26
2021-06-27 | 2021-06-27 | 2021-07-03
2021-07-04 | 2021-07-04 | 2021-07-10
2021-07-11 | 2021-07-11 | 2021-07-17
2021-07-18 | 2021-07-18 | 2021-07-24
2021-07-25 | 2021-07-25 | 2021-07-31
2021-08-01 | 2021-08-01 | 2021-08-07
2021-08-08 | 2021-08-08 | 2021-08-14
2021-08-15 | 2021-08-15 | 2021-08-21
2021-08-22 | 2021-08-22 | 2021-08-28
2021-08-29 | 2021-08-29 | 2021-09-04
2021-09-05 | 2021-09-05 | 2021-09-11
2021-09-12 | 2021-09-12 | 2021-09-18
2021-09-19 | 2021-09-19 | 2021-09-25
2021-09-26 | 2021-09-26 | 2021-10-02
2021-10-03 | 2021-10-03 | 2021-10-09
2021-10-10 | 2021-10-10 | 2021-10-16
2021-10-17 | 2021-10-17 | 2021-10-23
2021-10-24 | 2021-10-24 | 2021-10-30
2021-10-31 | 2021-10-31 | 2021-11-06
2021-11-07 | 2021-11-07 | 2021-11-13
2021-11-14 | 2021-11-14 | 2021-11-20
2021-11-21 | 2021-11-21 | 2021-11-27
2021-11-28 | 2021-11-28 | 2021-12-04
2021-12-05 | 2021-12-05 | 2021-12-11
2021-12-12 | 2021-12-12 | 2021-12-18
2021-12-19 | 2021-12-19 | 2021-12-25
2021-12-26 | 2021-12-26 | 2022-01-01
2022-01-02 | 2022-01-02 | 2022-01-08
2022-01-09 | 2022-01-09 | 2022-01-15
2022-01-16 | 2022-01-16 | 2022-01-22
2022-01-23 | 2022-01-23 | 2022-01-29
2022-01-30 | 2022-01-30 | 2022-02-05
2022-02-06 | 2022-02-06 | 2022-02-12
2022-02-13 | 2022-02-13 | 2022-02-19
2022-02-20 | 2022-02-20 | 2022-02-26
2022-02-27 | 2022-02-27 | 2022-03-05
2022-03-06 | 2022-03-06 | 2022-03-12
2022-03-13 | 2022-03-13 | 2022-03-19
2022-03-20 | 2022-03-20 | 2022-03-26
2022-03-27 | 2022-03-27 | 2022-04-02
2022-04-03 | 2022-04-03 | 2022-04-09
2022-04-10 | 2022-04-10 | 2022-04-16
Formulas:
Week Of = [Week Start]
Σ XS = IF([Week Start]<=TODAY(),SUMIFS('Days To Done'!$I3:I1000,'Days To Done'!$D3:D1000,"XS",'Days To Done'!$H3:H1000,">="&[Week Start],'Days To Done'!$H3:H1000,"<="&[Week End]),"")
Σ S = IF([Week Start]<=TODAY(),SUMIFS('Days To Done'!$I3:I1000,'Days To Done'!$D3:D1000,"S",'Days To Done'!$H3:H1000,">="&[Week Start],'Days To Done'!$H3:H1000,"<="&[Week End]),"")
Σ M = IF([Week Start]<=TODAY(),SUMIFS('Days To Done'!$I3:I1000,'Days To Done'!$D3:D1000,"M",'Days To Done'!$H3:H1000,">="&[Week Start],'Days To Done'!$H3:H1000,"<="&[Week End]),"")
Σ L = IF([Week Start]<=TODAY(),SUMIFS('Days To Done'!$I3:I1000,'Days To Done'!$D3:D1000,"L",'Days To Done'!$H3:H1000,">="&[Week Start],'Days To Done'!$H3:H1000,"<="&[Week End]),"")
Σ XL = IF([Week Start]<=TODAY(),SUMIFS('Days To Done'!$I3:I1000,'Days To Done'!$D3:D1000,"XL",'Days To Done'!$H3:H1000,">="&[Week Start],'Days To Done'!$H3:H1000,"<="&[Week End]),"")

## Look-ups
Classes of Service | Sizes |  | Types
| XS | <= 1 day
Expedite | S | 2 days | Story
Fixed Date | M | 3 days | Ticket
Standard | L | <= 1 week | Bug
Intangible | XL | <= 2 weeks

## Charts
[14 empty] | Week | Frequency
[14 empty] | 2017-04-08 | 8
[14 empty] | 2017-04-15 | 23
[14 empty] | 2017-04-22 | 45
[14 empty] | 2017-04-29 | 41
[14 empty] | 2017-05-06 | 68
[14 empty] | 2017-05-13 | 50
[14 empty] | 2017-05-20 | 52
[14 empty] | 2017-05-27 | 51
[14 empty] | 2017-06-03 | 38
[14 empty] | 2017-06-10 | 34
[14 empty] | 2017-06-17 | 20
[14 empty] | 2017-06-24 | 25
[14 empty] | 2017-07-01 | 12
[14 empty] | 2017-07-08 | 13
[14 empty] | 2017-07-15 | 4
[14 empty] | 2017-07-22 | 6
[14 empty] | 2017-07-29 | 4
[14 empty] | 2017-08-05 | 3
[14 empty] | 2017-08-12 | 2
[14 empty] | 2017-08-19 | 0
[14 empty] | 2017-08-26 | 0
[14 empty] | 2017-09-02 | 0
[14 empty] | 2017-09-09 | 0
[14 empty] | 2017-09-16 | 1
[14 empty] | 2017-09-23 | 0
[14 empty] | 2017-09-30 | 1
0
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
Story count results in table form. For the probabilities entered, how many stories for each period?
| 4 Weeks | 8 Weeks | 12 Weeks | 16 Weeks | 20 Weeks | 24 Weeks | 28 Weeks | 32 Weeks | 36 Weeks | 40 Weeks | 44 Weeks | 48 Weeks | 52 Weeks
95% | 4.95 | 10 | 17 | 23 | 29 | 36 | 42 | 49 | 55 | 62 | 68 | 75 | 81
85% | 5 | 12 | 18 | 25 | 31 | 38 | 45 | 52 | 58 | 64.85 | 71 | 78 | 84
5% | 10 | 18 | 25 | 33 | 41 | 49 | 56 | 64 | 72 | 79.05 | 87 | 94 | 101.05
What is this chart?
This chart shows how many simulated trials completed on or before the x-axis date. The higher the bar, the more likely that outcome.
What is this chart?
This chart shows the simulated burn-down trends. It shows the first 50 trials and visually shows the general hotspots and outlier dates. Enter actual stories remaining in the Reamining Stories Actual worksheet to see progress.
What is this chart?
This chart shows the number of completed (pre-split) stories for a given period. Select the time period on the forecast worksheet. The forecast is shown at three confidence intervals specified on the forecast worksheet.

## Forecaster Instructions
Single Feature Forecaster
Always get the latest version of this spreadsheet here.
Version history:
| 1 | 2015-04-07 | Initial beta release for feedback.
| 1.01 | 2015-05-22 | Fixed validation usability errors.
| 1.1 | 2015-05-26 | Added risks and charts.
| 1.2 | 2015-06-01 | Updated instructions and charts.
| 1.3 | 2016-02-12 | Added split rate inputs.
| 1.4 | 2016-06-01 | Added actual plot.
| 1.5 | 2016-06-02 | Added story count forecast by period.
What is this: This spreadsheet helps to probabilistically forecast how long it will take to complete features and stories based on range estimates.
How does it work? Given your estimates, this spreadsheet hypothetically completes all work 500 times. It calculates likelihood result as the number of simulated trials that finished on or before a given date.
Why is this better than burndowns and traditional Agile forecasting? Most forecasting techniques give a single date result and hide the likelihood of that date. Most often the date given as the result is 50% because work is divided by an average (or median). Thats the odds of a toin-coss. This method allows the reader to choose the amount of schedule risk they wish to sign-up for. 85% is a common middle ground used in the industry.
Is it reliable? It has no mathematical errors (that we know of!), and all we guarentee is its better than intuition alone and better than simple regression models. But, help us improve it by letting us know when it misses the actual results you are seeing.
How to: Fill in the orange boxes in the Forecast worksheet and read off the dates in the results table adjacent to the likelihood/certainty you think is appropriate. 85% is a common industry level of certainty used.
What is throughput? Where do I get that data? Throughput is the number of DONE stories completed by a team per week or per sprint (you choose in this spreadsheet, default is per week). We will be providing a viz that gathers this data for your team. Stay tuned.
What is this: This spreadsheet helps to probabilistically forecast how long it will take to complete features based on story count range estimates and either estimated team throughput or historical team throughput samples.
How does it work? Given your estimates, this spreadsheet hypothetically completes all work 500 times. It calculates likelihood result as the number of simulated trials that finished on or before a given date. Given your desired scenario order, features are completed in order and the dates computed based on specified likelihood.
Why is this better than burndowns and traditional Agile forecasting? Most forecasting techniques give a single date result and hide the likelihood of that date. Most often the date given as the result is 50% because work is divided by an average (or median). Thats the odds of a toin-coss. This method allows the reader to choose the amount of schedule risk they wish to sign-up for. 85% is a common middle ground used in the industry.
Is it reliable? It has no mathematical errors (that we know of!), and all we guarantee is its better than intuition alone and better than simple regression models. But, help us improve it by letting us know when it misses the actual results you are seeing.
How to: Fill in the orange boxes in the Forecast worksheet and read off the dates in the results table adjacent to the likelihood/certainty you think is appropriate. 85% is a common industry level of certainty used - a good balance of better than average but not susceptible to extreme outliers.
What is throughput? Where do I get that data? Throughput is the number of DONE stories completed by a team per week or per sprint (you choose in this spreadsheet, default is per week). Also see our Throughput and Cycle Time Calculator spreadsheet for convertinf story/item data to throughput values. Also see our tutorials on how to use Excel to calculate throughput rates.
Ideas, errors, requests? Email: troy.magennis@focusedobjective.com
Work licensed under a Creative Commons Attribution-NonCommercial-ShareAlike 4.0 International License.
Get more tools like this from: http://bit.ly/SimResources
About us: Focused Objective LLC offers tools, training and expert advice on metrics, risk and forecasting. We have more advanced tools to model Agile teams and projects that help analyze staffing options and risk, and a proven track record of positive results. We are always happy to discuss next steps and training opportunities should this tool prove useful. See our website: http://www.focusedobjective.com or email me at troy.magennis@focusedobjective.com.

## Remaining Stories Actuals (hidden)
Date (week ending) | Number of Incompleted (but in scope) stories | Notes
2017-03-11 | 9
2017-03-18 | 16
2017-03-25 | 16
2017-04-01
2017-04-08
2017-04-15
2017-04-22
2017-04-29
2017-05-06
2017-05-13
2017-05-20
2017-05-27
2017-06-03
2017-06-10
2017-06-17
2017-06-24
2017-07-01
2017-07-08
2017-07-15
2017-07-22
2017-07-29
2017-08-05
2017-08-12
2017-08-19
2017-08-26
2017-09-02
2017-09-09
2017-09-16
2017-09-23
2017-09-30
2017-10-07
2017-10-14
2017-10-21
2017-10-28
2017-11-04
2017-11-11
2017-11-18
2017-11-25
2017-12-02
2017-12-09
2017-12-16
2017-12-23
2017-12-30
2018-01-06
2018-01-13
2018-01-20
2018-01-27
2018-02-03
2018-02-10
2018-02-17
2018-02-24
Instructions.
Enter the actual number of IN-COMPLETE items in the backlog in column B for the dates shown in column A. This line will be charted on the burndown chart.

## Monte Carlo (hidden)
Trial | Weeks to Zero | End of Zero Week | TotalStories | End week 1 | End week 2 | End week 3 | End week 4 | End week 5 | End week 6 | End week 7 | End week 8 | End week 9 | End week 10 | End week 11 | End week 12 | End week 13 | End week 14 | End week 15 | End week 16 | End week 17 | End week 18 | End week 19 | End week 20 | End week 21 | End week 22 | End week 23 | End week 24 | End week 25 | End week 26 | End week 27 | End week 28 | End week 29 | End week 30 | End week 31 | End week 32 | End week 33 | End week 34 | End week 35 | End week 36 | End week 37 | End week 38 | End week 39 | End week 40 | End week 41 | End week 42 | End week 43 | End week 44 | End week 45 | End week 46 | End week 47 | End week 48 | End week 49 | End week 50 | End week 51 | End week 52
 | time axis 2017-03-11 to 2018-03-10
1 | 15 | 2017-06-24 | 15 | 13 | 11 | 8 | 6 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 5 | 2017-04-15 | 9 | 6 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 8 | 2017-05-06 | 12 | 12 | 12 | 9 | 6 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 9 | 2017-05-13 | 11 | 9 | 9 | 7 | 7 | 7 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 13 | 2017-06-10 | 13 | 13 | 11 | 9 | 7 | 5 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 7 | 2017-04-29 | 12 | 12 | 9 | 7 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 14 | 2017-06-17 | 15 | 15 | 15 | 15 | 12 | 12 | 10 | 8 | 8 | 8 | 5 | 5 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 10 | 2017-05-20 | 11 | 11 | 11 | 8 | 8 | 6 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 11 | 2017-05-27 | 11 | 11 | 8 | 6 | 6 | 6 | 4 | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 8 | 2017-05-06 | 15 | 15 | 13 | 11 | 11 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 16 | 2017-07-01 | 15 | 15 | 15 | 12 | 12 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 5 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 20 | 2017-07-29 | 11 | 11 | 9 | 9 | 9 | 9 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 6 | 2017-04-22 | 9 | 9 | 9 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 15 | 2017-06-24 | 10 | 7 | 7 | 7 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 11 | 2017-05-27 | 15 | 15 | 15 | 12 | 9 | 9 | 7 | 4 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 8 | 2017-05-06 | 12 | 12 | 10 | 8 | 8 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 13 | 2017-06-10 | 14 | 12 | 12 | 12 | 10 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 7 | 2017-04-29 | 9 | 7 | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 16 | 2017-07-01 | 10 | 10 | 10 | 8 | 8 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 6 | 2017-04-22 | 11 | 9 | 7 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 18 | 2017-07-15 | 11 | 9 | 9 | 9 | 9 | 9 | 7 | 7 | 7 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 10 | 2017-05-20 | 10 | 10 | 8 | 8 | 8 | 8 | 5 | 5 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 5 | 2017-04-15 | 12 | 10 | 8 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 13 | 2017-06-10 | 12 | 12 | 10 | 10 | 10 | 10 | 8 | 8 | 8 | 5 | 5 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 7 | 2017-04-29 | 9 | 7 | 4 | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 9 | 2017-05-13 | 15 | 13 | 11 | 11 | 8 | 5 | 5 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 16 | 2017-07-01 | 11 | 11 | 9 | 9 | 9 | 9 | 7 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 8 | 2017-05-06 | 10 | 10 | 10 | 7 | 5 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | 12 | 2017-06-03 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 7 | 5 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 14 | 2017-06-17 | 15 | 13 | 11 | 11 | 11 | 8 | 6 | 6 | 6 | 6 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | 13 | 2017-06-10 | 12 | 10 | 7 | 7 | 7 | 7 | 7 | 5 | 5 | 5 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 9 | 2017-05-13 | 14 | 12 | 12 | 10 | 7 | 7 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | 12 | 2017-06-03 | 15 | 13 | 13 | 13 | 11 | 11 | 9 | 9 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | 8 | 2017-05-06 | 11 | 9 | 9 | 6 | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | 8 | 2017-05-06 | 11 | 8 | 8 | 5 | 5 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | 6 | 2017-04-22 | 14 | 14 | 11 | 8 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 8 | 2017-05-06 | 10 | 7 | 7 | 7 | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 12 | 2017-06-03 | 15 | 13 | 13 | 13 | 13 | 11 | 9 | 6 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 15 | 2017-06-24 | 13 | 13 | 13 | 13 | 10 | 8 | 6 | 6 | 6 | 6 | 4 | 4 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 8 | 2017-05-06 | 9 | 7 | 7 | 7 | 7 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 4 | 2017-04-08 | 10 | 8 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | 9 | 2017-05-13 | 9 | 6 | 6 | 6 | 4 | 4 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 15 | 2017-06-24 | 15 | 13 | 13 | 10 | 10 | 10 | 7 | 7 | 7 | 7 | 4 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 5 | 2017-04-15 | 9 | 9 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | 22 | 2017-08-12 | 15 | 13 | 13 | 13 | 13 | 13 | 13 | 11 | 11 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 6 | 6 | 6 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | 12 | 2017-06-03 | 11 | 11 | 11 | 8 | 8 | 8 | 8 | 8 | 8 | 5 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | 8 | 2017-05-06 | 10 | 8 | 8 | 5 | 5 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 8 | 2017-05-06 | 13 | 10 | 7 | 7 | 7 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | 18 | 2017-07-15 | 13 | 10 | 10 | 10 | 10 | 7 | 7 | 7 | 5 | 5 | 5 | 5 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 10 | 2017-05-20 | 12 | 10 | 10 | 8 | 6 | 6 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | 9 | 2017-05-13 | 11 | 9 | 9 | 7 | 5 | 5 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | 5 | 2017-04-15 | 10 | 8 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | 6 | 2017-04-22 | 9 | 9 | 6 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 13 | 2017-06-10 | 13 | 13 | 10 | 10 | 7 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | 8 | 2017-05-06 | 10 | 10 | 7 | 4 | 4 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | 9 | 2017-05-13 | 12 | 12 | 12 | 12 | 9 | 9 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | 19 | 2017-07-22 | 15 | 15 | 15 | 13 | 11 | 9 | 9 | 9 | 7 | 7 | 7 | 7 | 7 | 7 | 4 | 4 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | 5 | 2017-04-15 | 11 | 9 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | 15 | 2017-06-24 | 13 | 13 | 13 | 10 | 10 | 10 | 10 | 10 | 7 | 5 | 5 | 5 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | 7 | 2017-04-29 | 11 | 8 | 5 | 5 | 5 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | 12 | 2017-06-03 | 15 | 13 | 13 | 13 | 10 | 8 | 8 | 5 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | 10 | 2017-05-20 | 10 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | 18 | 2017-07-15 | 15 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 11 | 11 | 8 | 8 | 8 | 8 | 5 | 5 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | 7 | 2017-04-29 | 10 | 8 | 8 | 8 | 8 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | 13 | 2017-06-10 | 15 | 12 | 10 | 10 | 8 | 5 | 5 | 3 | 3 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | 8 | 2017-05-06 | 13 | 13 | 10 | 10 | 10 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | 12 | 2017-06-03 | 14 | 11 | 11 | 11 | 11 | 11 | 11 | 8 | 5 | 5 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | 6 | 2017-04-22 | 14 | 11 | 8 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69 | 17 | 2017-07-08 | 15 | 13 | 13 | 13 | 13 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 8 | 6 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | 9 | 2017-05-13 | 9 | 9 | 9 | 7 | 7 | 7 | 7 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 | 7 | 2017-04-29 | 9 | 9 | 7 | 7 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 12 | 2017-06-03 | 10 | 7 | 7 | 7 | 7 | 7 | 7 | 4 | 4 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | 8 | 2017-05-06 | 10 | 7 | 4 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74 | 6 | 2017-04-22 | 10 | 10 | 8 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
75 | 7 | 2017-04-29 | 10 | 10 | 7 | 5 | 5 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 | 6 | 2017-04-22 | 10 | 8 | 5 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 | 11 | 2017-05-27 | 15 | 15 | 15 | 15 | 12 | 12 | 9 | 9 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | 10 | 2017-05-20 | 14 | 11 | 11 | 11 | 11 | 8 | 6 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | 10 | 2017-05-20 | 11 | 11 | 11 | 9 | 9 | 9 | 7 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | 7 | 2017-04-29 | 10 | 7 | 7 | 5 | 5 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | 10 | 2017-05-20 | 13 | 10 | 7 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | 9 | 2017-05-13 | 15 | 13 | 13 | 13 | 11 | 9 | 7 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | 14 | 2017-06-17 | 15 | 15 | 12 | 10 | 8 | 8 | 8 | 8 | 8 | 8 | 5 | 5 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | 6 | 2017-04-22 | 11 | 11 | 8 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | 8 | 2017-05-06 | 12 | 10 | 8 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | 9 | 2017-05-13 | 11 | 9 | 6 | 4 | 4 | 4 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | 5 | 2017-04-15 | 9 | 9 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | 11 | 2017-05-27 | 12 | 9 | 9 | 9 | 9 | 9 | 6 | 6 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | 13 | 2017-06-10 | 10 | 10 | 10 | 10 | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | 12 | 2017-06-03 | 11 | 11 | 11 | 11 | 11 | 8 | 8 | 5 | 5 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | 8 | 2017-05-06 | 12 | 10 | 8 | 8 | 8 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | 15 | 2017-06-24 | 15 | 12 | 10 | 10 | 10 | 7 | 4 | 4 | 4 | 4 | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | 6 | 2017-04-22 | 14 | 11 | 11 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | 12 | 2017-06-03 | 10 | 8 | 8 | 8 | 5 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | 10 | 2017-05-20 | 14 | 14 | 11 | 8 | 8 | 6 | 6 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | 6 | 2017-04-22 | 13 | 10 | 7 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | 10 | 2017-05-20 | 11 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | 15 | 2017-06-24 | 11 | 9 | 9 | 7 | 7 | 7 | 7 | 7 | 7 | 5 | 5 | 5 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | 11 | 2017-05-27 | 15 | 12 | 12 | 9 | 9 | 9 | 7 | 4 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | 6 | 2017-04-22 | 15 | 12 | 9 | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | 6 | 2017-04-22 | 10 | 7 | 5 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | 6 | 2017-04-22 | 12 | 12 | 9 | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 | 6 | 2017-04-22 | 11 | 11 | 8 | 5 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | 13 | 2017-06-10 | 13 | 10 | 10 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
105 | 4 | 2017-04-08 | 10 | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
106 | 11 | 2017-05-27 | 12 | 9 | 9 | 7 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
107 | 14 | 2017-06-17 | 12 | 9 | 9 | 9 | 7 | 5 | 5 | 5 | 3 | 3 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
108 | 14 | 2017-06-17 | 15 | 12 | 12 | 12 | 12 | 12 | 9 | 9 | 7 | 7 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
109 | 10 | 2017-05-20 | 9 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 | 11 | 2017-05-27 | 15 | 12 | 12 | 9 | 6 | 6 | 4 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
111 | 5 | 2017-04-15 | 11 | 8 | 5 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
112 | 17 | 2017-07-08 | 13 | 11 | 11 | 11 | 11 | 9 | 7 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
113 | 6 | 2017-04-22 | 12 | 10 | 10 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
114 | 8 | 2017-05-06 | 15 | 12 | 10 | 8 | 6 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
115 | 8 | 2017-05-06 | 9 | 9 | 6 | 4 | 4 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
116 | 11 | 2017-05-27 | 12 | 10 | 10 | 10 | 10 | 10 | 7 | 5 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
117 | 8 | 2017-05-06 | 10 | 10 | 10 | 10 | 7 | 5 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
118 | 13 | 2017-06-10 | 13 | 10 | 8 | 8 | 6 | 6 | 6 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
119 | 9 | 2017-05-13 | 12 | 10 | 7 | 5 | 5 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
120 | 12 | 2017-06-03 | 12 | 12 | 10 | 10 | 10 | 7 | 5 | 5 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
121 | 9 | 2017-05-13 | 13 | 10 | 10 | 8 | 8 | 8 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
122 | 5 | 2017-04-15 | 9 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
123 | 10 | 2017-05-20 | 9 | 9 | 9 | 6 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
124 | 5 | 2017-04-15 | 9 | 9 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
125 | 9 | 2017-05-13 | 12 | 9 | 9 | 9 | 6 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
126 | 13 | 2017-06-10 | 9 | 6 | 6 | 6 | 6 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
127 | 6 | 2017-04-22 | 11 | 11 | 11 | 8 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
128 | 8 | 2017-05-06 | 15 | 13 | 13 | 13 | 11 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
129 | 8 | 2017-05-06 | 11 | 11 | 9 | 6 | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
130 | 8 | 2017-05-06 | 12 | 12 | 9 | 9 | 6 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
131 | 12 | 2017-06-03 | 11 | 11 | 9 | 7 | 7 | 4 | 4 | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
132 | 16 | 2017-07-01 | 11 | 11 | 11 | 11 | 8 | 8 | 8 | 6 | 6 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
133 | 8 | 2017-05-06 | 13 | 11 | 8 | 8 | 8 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
134 | 9 | 2017-05-13 | 13 | 11 | 8 | 6 | 6 | 6 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
135 | 8 | 2017-05-06 | 14 | 12 | 12 | 9 | 7 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
136 | 16 | 2017-07-01 | 15 | 15 | 15 | 15 | 13 | 13 | 11 | 8 | 8 | 8 | 8 | 8 | 5 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
137 | 10 | 2017-05-20 | 15 | 15 | 13 | 11 | 9 | 9 | 6 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
138 | 14 | 2017-06-17 | 13 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 9 | 6 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
139 | 29 | 2017-09-30 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 13 | 11 | 9 | 7 | 7 | 7 | 7 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
140 | 16 | 2017-07-01 | 12 | 12 | 12 | 9 | 7 | 7 | 7 | 5 | 5 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
141 | 5 | 2017-04-15 | 9 | 6 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
142 | 8 | 2017-05-06 | 11 | 11 | 9 | 9 | 6 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
143 | 7 | 2017-04-29 | 9 | 9 | 7 | 7 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
144 | 9 | 2017-05-13 | 14 | 14 | 11 | 8 | 6 | 6 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
145 | 11 | 2017-05-27 | 14 | 14 | 14 | 12 | 10 | 8 | 6 | 6 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
146 | 12 | 2017-06-03 | 15 | 12 | 12 | 10 | 8 | 8 | 6 | 6 | 6 | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
147 | 11 | 2017-05-27 | 13 | 11 | 8 | 8 | 5 | 5 | 5 | 5 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
148 | 9 | 2017-05-13 | 9 | 7 | 7 | 7 | 5 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
149 | 6 | 2017-04-22 | 10 | 8 | 8 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
150 | 15 | 2017-06-24 | 14 | 14 | 14 | 11 | 8 | 6 | 6 | 6 | 6 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
151 | 8 | 2017-05-06 | 13 | 11 | 8 | 8 | 8 | 5 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
152 | 11 | 2017-05-27 | 15 | 12 | 12 | 12 | 12 | 9 | 9 | 7 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
153 | 8 | 2017-05-06 | 15 | 12 | 9 | 6 | 4 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
154 | 11 | 2017-05-27 | 9 | 9 | 9 | 7 | 5 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
155 | 17 | 2017-07-08 | 14 | 14 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 8 | 8 | 5 | 3 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
156 | 7 | 2017-04-29 | 9 | 9 | 7 | 7 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
157 | 10 | 2017-05-20 | 11 | 8 | 8 | 8 | 6 | 6 | 6 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
158 | 8 | 2017-05-06 | 15 | 12 | 9 | 9 | 7 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
159 | 11 | 2017-05-27 | 15 | 12 | 10 | 8 | 6 | 4 | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
160 | 10 | 2017-05-20 | 10 | 8 | 8 | 8 | 6 | 6 | 6 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
161 | 8 | 2017-05-06 | 9 | 9 | 9 | 9 | 6 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
162 | 8 | 2017-05-06 | 13 | 10 | 7 | 5 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
163 | 6 | 2017-04-22 | 9 | 9 | 9 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
164 | 8 | 2017-05-06 | 10 | 7 | 5 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
165 | 13 | 2017-06-10 | 9 | 9 | 9 | 7 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
166 | 6 | 2017-04-22 | 10 | 10 | 8 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
167 | 10 | 2017-05-20 | 15 | 13 | 11 | 11 | 8 | 5 | 5 | 5 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
168 | 10 | 2017-05-20 | 15 | 12 | 10 | 10 | 8 | 8 | 8 | 8 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
169 | 15 | 2017-06-24 | 13 | 11 | 11 | 11 | 9 | 9 | 9 | 9 | 9 | 9 | 7 | 7 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
170 | 12 | 2017-06-03 | 13 | 13 | 10 | 7 | 7 | 7 | 7 | 7 | 7 | 5 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
171 | 15 | 2017-06-24 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 10 | 10 | 10 | 7 | 4 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
172 | 10 | 2017-05-20 | 9 | 9 | 6 | 6 | 6 | 4 | 4 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
173 | 7 | 2017-04-29 | 9 | 7 | 4 | 4 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
174 | 6 | 2017-04-22 | 11 | 11 | 9 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
175 | 15 | 2017-06-24 | 14 | 14 | 11 | 9 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
176 | 10 | 2017-05-20 | 12 | 9 | 7 | 7 | 5 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
177 | 12 | 2017-06-03 | 12 | 12 | 9 | 9 | 6 | 6 | 6 | 6 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
178 | 12 | 2017-06-03 | 12 | 12 | 9 | 9 | 9 | 6 | 6 | 6 | 4 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
179 | 6 | 2017-04-22 | 11 | 8 | 8 | 5 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
180 | 10 | 2017-05-20 | 12 | 10 | 8 | 8 | 8 | 6 | 6 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
181 | 12 | 2017-06-03 | 13 | 13 | 13 | 13 | 11 | 11 | 11 | 9 | 7 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
182 | 7 | 2017-04-29 | 13 | 11 | 9 | 6 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
183 | 8 | 2017-05-06 | 12 | 9 | 9 | 7 | 4 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
184 | 11 | 2017-05-27 | 15 | 15 | 15 | 12 | 12 | 9 | 7 | 7 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
185 | 20 | 2017-07-29 | 15 | 15 | 13 | 13 | 13 | 13 | 13 | 11 | 9 | 9 | 7 | 7 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
186 | 19 | 2017-07-22 | 14 | 14 | 14 | 12 | 12 | 12 | 9 | 9 | 9 | 9 | 6 | 6 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
187 | 5 | 2017-04-15 | 9 | 6 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
188 | 9 | 2017-05-13 | 9 | 9 | 7 | 5 | 5 | 5 | 5 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
189 | 11 | 2017-05-27 | 11 | 11 | 11 | 8 | 6 | 3 | 3 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
190 | 4 | 2017-04-08 | 10 | 7 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
191 | 15 | 2017-06-24 | 15 | 15 | 13 | 10 | 10 | 10 | 8 | 5 | 5 | 5 | 5 | 5 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
192 | 9 | 2017-05-13 | 12 | 10 | 10 | 10 | 7 | 4 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
193 | 11 | 2017-05-27 | 10 | 10 | 7 | 7 | 5 | 5 | 5 | 5 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
194 | 4 | 2017-04-08 | 10 | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
195 | 8 | 2017-05-06 | 14 | 14 | 11 | 9 | 9 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
196 | 9 | 2017-05-13 | 12 | 12 | 9 | 9 | 7 | 7 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
197 | 9 | 2017-05-13 | 10 | 10 | 7 | 5 | 5 | 5 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
198 | 6 | 2017-04-22 | 9 | 6 | 6 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
199 | 9 | 2017-05-13 | 15 | 12 | 10 | 7 | 7 | 4 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
200 | 8 | 2017-05-06 | 11 | 8 | 5 | 5 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
201 | 14 | 2017-06-17 | 12 | 9 | 9 | 9 | 9 | 9 | 9 | 7 | 5 | 5 | 5 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
202 | 8 | 2017-05-06 | 13 | 13 | 13 | 10 | 7 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
203 | 8 | 2017-05-06 | 11 | 11 | 8 | 5 | 5 | 5 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
204 | 10 | 2017-05-20 | 12 | 10 | 10 | 7 | 7 | 4 | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
205 | 8 | 2017-05-06 | 11 | 11 | 8 | 6 | 6 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
206 | 11 | 2017-05-27 | 11 | 8 | 8 | 8 | 5 | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
207 | 14 | 2017-06-17 | 14 | 12 | 12 | 10 | 10 | 10 | 10 | 8 | 6 | 6 | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
208 | 14 | 2017-06-17 | 15 | 15 | 15 | 12 | 12 | 12 | 10 | 7 | 7 | 7 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
209 | 8 | 2017-05-06 | 11 | 11 | 9 | 7 | 5 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
210 | 15 | 2017-06-24 | 15 | 15 | 13 | 10 | 8 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
211 | 8 | 2017-05-06 | 12 | 9 | 9 | 9 | 9 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
212 | 13 | 2017-06-10 | 13 | 13 | 13 | 13 | 13 | 13 | 10 | 10 | 8 | 8 | 8 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
213 | 5 | 2017-04-15 | 13 | 10 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
214 | 13 | 2017-06-10 | 13 | 13 | 11 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
215 | 16 | 2017-07-01 | 9 | 7 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 | 15 | 2017-06-24 | 12 | 12 | 10 | 10 | 7 | 7 | 7 | 5 | 5 | 3 | 3 | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
217 | 8 | 2017-05-06 | 12 | 9 | 9 | 7 | 5 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
218 | 9 | 2017-05-13 | 14 | 14 | 11 | 9 | 7 | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 | 7 | 2017-04-29 | 14 | 12 | 10 | 10 | 8 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220 | 7 | 2017-04-29 | 9 | 7 | 7 | 7 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
221 | 12 | 2017-06-03 | 14 | 14 | 14 | 12 | 12 | 9 | 6 | 6 | 4 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 9 | 2017-05-13 | 13 | 11 | 9 | 9 | 7 | 7 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
223 | 11 | 2017-05-27 | 10 | 7 | 7 | 7 | 7 | 7 | 7 | 5 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 | 7 | 2017-04-29 | 10 | 10 | 8 | 8 | 8 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
225 | 8 | 2017-05-06 | 13 | 11 | 9 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
226 | 17 | 2017-07-08 | 12 | 12 | 12 | 10 | 10 | 10 | 10 | 10 | 8 | 8 | 5 | 3 | 3 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
227 | 13 | 2017-06-10 | 10 | 10 | 10 | 8 | 8 | 8 | 8 | 8 | 5 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | 11 | 2017-05-27 | 15 | 15 | 15 | 13 | 11 | 11 | 8 | 8 | 5 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | 4 | 2017-04-08 | 9 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | 10 | 2017-05-20 | 13 | 13 | 13 | 10 | 10 | 7 | 5 | 5 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | 10 | 2017-05-20 | 15 | 15 | 13 | 11 | 8 | 8 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | 16 | 2017-07-01 | 14 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 8 | 6 | 3 | 3 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233 | 6 | 2017-04-22 | 10 | 8 | 8 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
234 | 11 | 2017-05-27 | 10 | 10 | 10 | 10 | 8 | 6 | 6 | 6 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
235 | 11 | 2017-05-27 | 14 | 14 | 11 | 9 | 9 | 9 | 7 | 5 | 5 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
236 | 11 | 2017-05-27 | 9 | 9 | 9 | 9 | 9 | 9 | 6 | 6 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
237 | 6 | 2017-04-22 | 11 | 11 | 11 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
238 | 7 | 2017-04-29 | 10 | 8 | 6 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
239 | 7 | 2017-04-29 | 11 | 11 | 11 | 8 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
240 | 6 | 2017-04-22 | 12 | 9 | 9 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
241 | 14 | 2017-06-17 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 11 | 8 | 6 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
242 | 17 | 2017-07-08 | 14 | 11 | 11 | 11 | 11 | 11 | 11 | 8 | 6 | 6 | 6 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
243 | 9 | 2017-05-13 | 10 | 8 | 8 | 6 | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
244 | 11 | 2017-05-27 | 12 | 9 | 9 | 7 | 7 | 7 | 5 | 5 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
245 | 8 | 2017-05-06 | 15 | 13 | 10 | 10 | 8 | 5 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
246 | 11 | 2017-05-27 | 11 | 9 | 9 | 9 | 9 | 9 | 7 | 7 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
247 | 5 | 2017-04-15 | 12 | 9 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
248 | 5 | 2017-04-15 | 9 | 7 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
249 | 11 | 2017-05-27 | 13 | 13 | 11 | 8 | 8 | 5 | 5 | 5 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
250 | 6 | 2017-04-22 | 9 | 6 | 6 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
251 | 6 | 2017-04-22 | 9 | 9 | 9 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
252 | 6 | 2017-04-22 | 9 | 6 | 6 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
253 | 8 | 2017-05-06 | 14 | 12 | 9 | 6 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
254 | 11 | 2017-05-27 | 10 | 8 | 8 | 6 | 6 | 6 | 6 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
255 | 5 | 2017-04-15 | 9 | 6 | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
256 | 15 | 2017-06-24 | 12 | 10 | 10 | 8 | 6 | 6 | 6 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
257 | 10 | 2017-05-20 | 12 | 12 | 9 | 6 | 6 | 6 | 4 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
258 | 13 | 2017-06-10 | 15 | 15 | 12 | 12 | 12 | 12 | 9 | 9 | 7 | 5 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
259 | 9 | 2017-05-13 | 13 | 10 | 10 | 8 | 8 | 8 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
260 | 19 | 2017-07-22 | 15 | 12 | 12 | 9 | 9 | 6 | 6 | 6 | 6 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
261 | 10 | 2017-05-20 | 12 | 9 | 9 | 6 | 6 | 4 | 4 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
262 | 27 | 2017-09-16 | 11 | 11 | 11 | 11 | 11 | 9 | 7 | 7 | 7 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
263 | 6 | 2017-04-22 | 9 | 7 | 7 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
264 | 13 | 2017-06-10 | 15 | 13 | 13 | 11 | 11 | 11 | 11 | 8 | 8 | 6 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
265 | 17 | 2017-07-08 | 15 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 11 | 11 | 11 | 8 | 8 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
266 | 14 | 2017-06-17 | 10 | 10 | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
267 | 6 | 2017-04-22 | 10 | 7 | 5 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
268 | 10 | 2017-05-20 | 14 | 11 | 11 | 11 | 11 | 9 | 9 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
269 | 7 | 2017-04-29 | 9 | 9 | 6 | 4 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
270 | 10 | 2017-05-20 | 11 | 11 | 11 | 9 | 7 | 7 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 9 | 2017-05-13 | 11 | 11 | 11 | 8 | 8 | 6 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
272 | 11 | 2017-05-27 | 11 | 8 | 8 | 6 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
273 | 12 | 2017-06-03 | 11 | 9 | 7 | 7 | 5 | 5 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
274 | 13 | 2017-06-10 | 12 | 12 | 9 | 9 | 9 | 9 | 9 | 6 | 6 | 6 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
275 | 11 | 2017-05-27 | 15 | 15 | 12 | 12 | 9 | 9 | 9 | 7 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
276 | 7 | 2017-04-29 | 9 | 9 | 9 | 6 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
277 | 9 | 2017-05-13 | 9 | 7 | 7 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
278 | 7 | 2017-04-29 | 11 | 8 | 8 | 5 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
279 | 17 | 2017-07-08 | 15 | 12 | 10 | 10 | 8 | 6 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
280 | 17 | 2017-07-08 | 15 | 12 | 12 | 12 | 12 | 12 | 9 | 9 | 9 | 9 | 9 | 9 | 6 | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
281 | 12 | 2017-06-03 | 15 | 15 | 15 | 12 | 10 | 10 | 10 | 8 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
282 | 13 | 2017-06-10 | 15 | 15 | 13 | 13 | 11 | 11 | 11 | 11 | 11 | 8 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
283 | 16 | 2017-07-01 | 13 | 13 | 10 | 8 | 6 | 6 | 6 | 6 | 4 | 4 | 4 | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
284 | 21 | 2017-08-05 | 12 | 12 | 12 | 12 | 12 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 7 | 7 | 5 | 5 | 5 | 5 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
285 | 8 | 2017-05-06 | 11 | 8 | 8 | 6 | 4 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
286 | 20 | 2017-07-29 | 14 | 14 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 9 | 9 | 7 | 7 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
287 | 11 | 2017-05-27 | 14 | 14 | 14 | 14 | 12 | 9 | 9 | 7 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
288 | 9 | 2017-05-13 | 10 | 10 | 10 | 10 | 7 | 5 | 5 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
289 | 9 | 2017-05-13 | 14 | 11 | 8 | 5 | 5 | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
290 | 15 | 2017-06-24 | 14 | 14 | 14 | 14 | 11 | 9 | 9 | 6 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
291 | 12 | 2017-06-03 | 14 | 11 | 11 | 9 | 9 | 7 | 4 | 4 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
292 | 10 | 2017-05-20 | 15 | 12 | 9 | 7 | 7 | 7 | 7 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
293 | 12 | 2017-06-03 | 9 | 9 | 9 | 6 | 4 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
294 | 8 | 2017-05-06 | 10 | 10 | 10 | 8 | 6 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
295 | 9 | 2017-05-13 | 12 | 9 | 6 | 4 | 4 | 4 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
296 | 10 | 2017-05-20 | 11 | 9 | 9 | 9 | 9 | 6 | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
297 | 12 | 2017-06-03 | 9 | 6 | 6 | 6 | 6 | 6 | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
298 | 10 | 2017-05-20 | 14 | 11 | 11 | 11 | 8 | 8 | 8 | 5 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
299 | 12 | 2017-06-03 | 12 | 12 | 12 | 10 | 7 | 5 | 3 | 3 | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
300 | 10 | 2017-05-20 | 14 | 12 | 9 | 7 | 7 | 5 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
301 | 13 | 2017-06-10 | 12 | 9 | 9 | 9 | 9 | 9 | 9 | 6 | 6 | 4 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
302 | 8 | 2017-05-06 | 10 | 10 | 10 | 10 | 10 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
303 | 12 | 2017-06-03 | 15 | 15 | 15 | 13 | 13 | 13 | 13 | 11 | 8 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
304 | 7 | 2017-04-29 | 14 | 12 | 9 | 9 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
305 | 12 | 2017-06-03 | 14 | 12 | 12 | 9 | 6 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
306 | 13 | 2017-06-10 | 15 | 12 | 10 | 7 | 4 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
307 | 14 | 2017-06-17 | 14 | 11 | 11 | 11 | 8 | 6 | 6 | 6 | 6 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
308 | 17 | 2017-07-08 | 14 | 12 | 12 | 12 | 12 | 12 | 10 | 10 | 8 | 8 | 8 | 8 | 5 | 5 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
309 | 7 | 2017-04-29 | 15 | 12 | 9 | 7 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
310 | 9 | 2017-05-13 | 12 | 9 | 9 | 6 | 6 | 6 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
311 | 9 | 2017-05-13 | 10 | 7 | 7 | 5 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
312 | 13 | 2017-06-10 | 11 | 11 | 11 | 8 | 8 | 6 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
313 | 8 | 2017-05-06 | 10 | 10 | 10 | 7 | 7 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
314 | 10 | 2017-05-20 | 12 | 12 | 12 | 10 | 7 | 7 | 7 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
315 | 9 | 2017-05-13 | 10 | 10 | 10 | 8 | 8 | 8 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
316 | 16 | 2017-07-01 | 14 | 14 | 14 | 14 | 12 | 12 | 10 | 8 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
317 | 5 | 2017-04-15 | 12 | 12 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
318 | 19 | 2017-07-22 | 15 | 15 | 15 | 15 | 15 | 13 | 13 | 13 | 11 | 11 | 11 | 11 | 9 | 6 | 3 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
319 | 11 | 2017-05-27 | 13 | 13 | 10 | 10 | 10 | 10 | 10 | 7 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
320 | 8 | 2017-05-06 | 14 | 12 | 12 | 9 | 7 | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
321 | 13 | 2017-06-10 | 15 | 15 | 12 | 9 | 7 | 7 | 7 | 4 | 4 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
322 | 15 | 2017-06-24 | 11 | 8 | 8 | 8 | 6 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
323 | 11 | 2017-05-27 | 15 | 15 | 15 | 12 | 9 | 9 | 9 | 9 | 7 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
324 | 11 | 2017-05-27 | 13 | 11 | 9 | 9 | 9 | 9 | 6 | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
325 | 10 | 2017-05-20 | 11 | 11 | 11 | 9 | 9 | 6 | 6 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
326 | 10 | 2017-05-20 | 13 | 13 | 13 | 13 | 10 | 10 | 10 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
327 | 7 | 2017-04-29 | 9 | 6 | 6 | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
328 | 11 | 2017-05-27 | 15 | 13 | 13 | 13 | 13 | 10 | 7 | 4 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
329 | 10 | 2017-05-20 | 9 | 9 | 7 | 7 | 7 | 7 | 7 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
330 | 6 | 2017-04-22 | 12 | 12 | 9 | 7 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
331 | 7 | 2017-04-29 | 10 | 10 | 7 | 5 | 5 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
332 | 7 | 2017-04-29 | 9 | 9 | 7 | 5 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
333 | 14 | 2017-06-17 | 13 | 13 | 13 | 13 | 10 | 10 | 10 | 10 | 8 | 8 | 6 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
334 | 12 | 2017-06-03 | 12 | 12 | 12 | 12 | 9 | 7 | 7 | 7 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
335 | 11 | 2017-05-27 | 13 | 11 | 11 | 11 | 11 | 9 | 6 | 6 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
336 | 8 | 2017-05-06 | 12 | 12 | 10 | 8 | 6 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
337 | 6 | 2017-04-22 | 13 | 10 | 10 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
338 | 12 | 2017-06-03 | 13 | 11 | 8 | 8 | 6 | 6 | 3 | 3 | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
339 | 7 | 2017-04-29 | 12 | 12 | 10 | 7 | 5 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
340 | 8 | 2017-05-06 | 11 | 9 | 9 | 9 | 7 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
341 | 17 | 2017-07-08 | 15 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 10 | 10 | 10 | 8 | 6 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
342 | 19 | 2017-07-22 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 13 | 11 | 11 | 11 | 11 | 9 | 9 | 6 | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
343 | 10 | 2017-05-20 | 14 | 14 | 12 | 9 | 7 | 4 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
344 | 9 | 2017-05-13 | 14 | 12 | 9 | 9 | 7 | 5 | 5 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
345 | 12 | 2017-06-03 | 13 | 11 | 11 | 9 | 7 | 5 | 3 | 3 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
346 | 4 | 2017-04-08 | 11 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
347 | 7 | 2017-04-29 | 12 | 12 | 9 | 9 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
348 | 6 | 2017-04-22 | 11 | 9 | 7 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
349 | 5 | 2017-04-15 | 11 | 8 | 5 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
350 | 12 | 2017-06-03 | 14 | 14 | 11 | 11 | 8 | 6 | 6 | 6 | 4 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
351 | 7 | 2017-04-29 | 10 | 7 | 7 | 7 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
352 | 8 | 2017-05-06 | 14 | 11 | 11 | 8 | 8 | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
353 | 8 | 2017-05-06 | 10 | 8 | 5 | 3 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
354 | 7 | 2017-04-29 | 9 | 9 | 6 | 6 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
355 | 6 | 2017-04-22 | 11 | 11 | 8 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
356 | 12 | 2017-06-03 | 15 | 15 | 13 | 13 | 11 | 9 | 7 | 4 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
357 | 9 | 2017-05-13 | 11 | 11 | 8 | 5 | 5 | 5 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
358 | 15 | 2017-06-24 | 15 | 12 | 12 | 10 | 10 | 10 | 10 | 7 | 7 | 7 | 7 | 4 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
359 | 6 | 2017-04-22 | 9 | 6 | 6 | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
360 | 13 | 2017-06-10 | 11 | 11 | 11 | 8 | 5 | 5 | 5 | 5 | 3 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
361 | 11 | 2017-05-27 | 15 | 13 | 10 | 8 | 8 | 5 | 5 | 5 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
362 | 7 | 2017-04-29 | 10 | 7 | 4 | 4 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
363 | 12 | 2017-06-03 | 9 | 7 | 7 | 4 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
364 | 9 | 2017-05-13 | 15 | 12 | 9 | 9 | 6 | 6 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
365 | 8 | 2017-05-06 | 11 | 9 | 9 | 9 | 9 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
366 | 8 | 2017-05-06 | 15 | 15 | 12 | 12 | 9 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
367 | 9 | 2017-05-13 | 13 | 10 | 7 | 7 | 5 | 5 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
368 | 11 | 2017-05-27 | 11 | 11 | 9 | 7 | 7 | 5 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
369 | 8 | 2017-05-06 | 9 | 9 | 6 | 6 | 6 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
370 | 14 | 2017-06-17 | 15 | 15 | 13 | 13 | 13 | 13 | 11 | 11 | 11 | 8 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
371 | 7 | 2017-04-29 | 9 | 6 | 6 | 4 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
372 | 9 | 2017-05-13 | 13 | 11 | 9 | 6 | 6 | 6 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
373 | 10 | 2017-05-20 | 9 | 7 | 5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
374 | 13 | 2017-06-10 | 13 | 11 | 9 | 9 | 9 | 9 | 9 | 6 | 6 | 6 | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
375 | 7 | 2017-04-29 | 13 | 13 | 11 | 11 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
376 | 10 | 2017-05-20 | 12 | 12 | 12 | 12 | 9 | 6 | 6 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
377 | 12 | 2017-06-03 | 15 | 15 | 15 | 12 | 12 | 12 | 12 | 12 | 9 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
378 | 10 | 2017-05-20 | 11 | 11 | 9 | 9 | 6 | 4 | 4 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
379 | 11 | 2017-05-27 | 11 | 9 | 9 | 6 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
380 | 10 | 2017-05-20 | 9 | 9 | 9 | 7 | 7 | 4 | 4 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
381 | 10 | 2017-05-20 | 10 | 10 | 10 | 10 | 10 | 8 | 5 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
382 | 13 | 2017-06-10 | 10 | 7 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
383 | 8 | 2017-05-06 | 15 | 12 | 12 | 9 | 7 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
384 | 16 | 2017-07-01 | 14 | 14 | 12 | 12 | 12 | 12 | 9 | 7 | 7 | 7 | 7 | 4 | 4 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
385 | 9 | 2017-05-13 | 15 | 13 | 10 | 10 | 7 | 7 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
386 | 9 | 2017-05-13 | 14 | 12 | 12 | 10 | 8 | 5 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
387 | 13 | 2017-06-10 | 15 | 12 | 12 | 12 | 12 | 12 | 10 | 7 | 5 | 5 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
388 | 11 | 2017-05-27 | 14 | 12 | 9 | 7 | 7 | 5 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
389 | 14 | 2017-06-17 | 11 | 11 | 11 | 8 | 6 | 6 | 6 | 6 | 6 | 3 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
390 | 8 | 2017-05-06 | 13 | 10 | 8 | 8 | 6 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
391 | 11 | 2017-05-27 | 14 | 12 | 12 | 9 | 9 | 7 | 7 | 7 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
392 | 5 | 2017-04-15 | 9 | 7 | 5 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
393 | 6 | 2017-04-22 | 12 | 10 | 7 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
394 | 11 | 2017-05-27 | 12 | 12 | 10 | 10 | 10 | 10 | 10 | 8 | 5 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
395 | 8 | 2017-05-06 | 12 | 10 | 8 | 8 | 8 | 5 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
396 | 11 | 2017-05-27 | 13 | 13 | 13 | 11 | 8 | 8 | 8 | 5 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
397 | 17 | 2017-07-08 | 15 | 15 | 13 | 13 | 13 | 13 | 13 | 11 | 9 | 7 | 7 | 7 | 7 | 4 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
398 | 5 | 2017-04-15 | 11 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
399 | 6 | 2017-04-22 | 11 | 8 | 6 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
400 | 13 | 2017-06-10 | 13 | 13 | 13 | 10 | 7 | 7 | 7 | 7 | 7 | 7 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
401 | 9 | 2017-05-13 | 13 | 10 | 10 | 10 | 7 | 7 | 7 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
402 | 8 | 2017-05-06 | 12 | 9 | 6 | 6 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
403 | 7 | 2017-04-29 | 10 | 7 | 4 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
404 | 16 | 2017-07-01 | 14 | 14 | 12 | 12 | 12 | 12 | 10 | 8 | 8 | 8 | 5 | 3 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
405 | 7 | 2017-04-29 | 9 | 7 | 5 | 5 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
406 | 11 | 2017-05-27 | 14 | 14 | 14 | 14 | 11 | 11 | 8 | 6 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
407 | 6 | 2017-04-22 | 11 | 11 | 9 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
408 | 8 | 2017-05-06 | 12 | 12 | 10 | 8 | 8 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
409 | 21 | 2017-08-05 | 14 | 14 | 14 | 14 | 14 | 12 | 12 | 12 | 10 | 8 | 8 | 6 | 6 | 6 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
410 | 13 | 2017-06-10 | 13 | 13 | 13 | 13 | 10 | 8 | 5 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
411 | 8 | 2017-05-06 | 12 | 9 | 6 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
412 | 4 | 2017-04-08 | 10 | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
413 | 6 | 2017-04-22 | 10 | 7 | 5 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
414 | 8 | 2017-05-06 | 11 | 9 | 9 | 7 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
415 | 18 | 2017-07-15 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 11 | 11 | 9 | 9 | 6 | 3 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
416 | 8 | 2017-05-06 | 15 | 15 | 12 | 9 | 7 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
417 | 15 | 2017-06-24 | 15 | 15 | 12 | 10 | 10 | 10 | 10 | 8 | 8 | 5 | 5 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
418 | 10 | 2017-05-20 | 12 | 12 | 12 | 9 | 7 | 4 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
419 | 5 | 2017-04-15 | 11 | 8 | 5 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
420 | 9 | 2017-05-13 | 10 | 10 | 7 | 7 | 7 | 7 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
421 | 17 | 2017-07-08 | 15 | 13 | 13 | 13 | 11 | 11 | 11 | 9 | 7 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
422 | 15 | 2017-06-24 | 14 | 14 | 12 | 10 | 10 | 10 | 10 | 10 | 7 | 7 | 7 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
423 | 12 | 2017-06-03 | 9 | 9 | 9 | 9 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
424 | 11 | 2017-05-27 | 14 | 14 | 11 | 11 | 9 | 9 | 6 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
425 | 11 | 2017-05-27 | 10 | 10 | 10 | 10 | 8 | 8 | 6 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
426 | 10 | 2017-05-20 | 15 | 12 | 12 | 9 | 6 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
427 | 11 | 2017-05-27 | 14 | 14 | 14 | 14 | 11 | 11 | 11 | 8 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
428 | 9 | 2017-05-13 | 12 | 10 | 8 | 8 | 6 | 6 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
429 | 10 | 2017-05-20 | 12 | 9 | 9 | 9 | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
430 | 11 | 2017-05-27 | 14 | 12 | 10 | 10 | 10 | 10 | 10 | 8 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
431 | 8 | 2017-05-06 | 14 | 12 | 10 | 8 | 5 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
432 | 10 | 2017-05-20 | 10 | 10 | 10 | 7 | 4 | 4 | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
433 | 10 | 2017-05-20 | 15 | 12 | 9 | 7 | 7 | 7 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
434 | 19 | 2017-07-22 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 11 | 9 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
435 | 6 | 2017-04-22 | 15 | 13 | 10 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
436 | 15 | 2017-06-24 | 9 | 9 | 9 | 9 | 9 | 6 | 6 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
437 | 8 | 2017-05-06 | 13 | 10 | 8 | 6 | 6 | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
438 | 7 | 2017-04-29 | 10 | 8 | 5 | 5 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
439 | 11 | 2017-05-27 | 15 | 15 | 13 | 13 | 13 | 10 | 10 | 7 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
440 | 22 | 2017-08-12 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 12 | 12 | 12 | 10 | 8 | 6 | 6 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
441 | 6 | 2017-04-22 | 11 | 11 | 8 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
442 | 10 | 2017-05-20 | 14 | 14 | 11 | 8 | 5 | 5 | 5 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
443 | 9 | 2017-05-13 | 11 | 11 | 11 | 8 | 8 | 8 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
444 | 13 | 2017-06-10 | 13 | 13 | 13 | 11 | 11 | 8 | 8 | 5 | 5 | 5 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
445 | 11 | 2017-05-27 | 14 | 14 | 11 | 8 | 8 | 8 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
446 | 12 | 2017-06-03 | 9 | 9 | 9 | 9 | 7 | 7 | 5 | 5 | 5 | 5 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
447 | 6 | 2017-04-22 | 9 | 6 | 4 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
448 | 15 | 2017-06-24 | 11 | 11 | 8 | 8 | 6 | 6 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
449 | 6 | 2017-04-22 | 10 | 7 | 5 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
450 | 17 | 2017-07-08 | 15 | 13 | 13 | 13 | 10 | 10 | 7 | 7 | 7 | 7 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
451 | 10 | 2017-05-20 | 14 | 14 | 12 | 12 | 10 | 8 | 8 | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
452 | 11 | 2017-05-27 | 15 | 15 | 15 | 13 | 10 | 7 | 4 | 4 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
453 | 15 | 2017-06-24 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 10 | 8 | 5 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
454 | 8 | 2017-05-06 | 13 | 11 | 8 | 6 | 4 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
455 | 13 | 2017-06-10 | 9 | 9 | 9 | 9 | 9 | 7 | 7 | 7 | 7 | 7 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
456 | 12 | 2017-06-03 | 14 | 14 | 14 | 14 | 14 | 11 | 9 | 9 | 6 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
457 | 10 | 2017-05-20 | 14 | 11 | 11 | 9 | 6 | 6 | 6 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
458 | 7 | 2017-04-29 | 10 | 8 | 5 | 5 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
459 | 10 | 2017-05-20 | 13 | 13 | 13 | 13 | 13 | 11 | 8 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
460 | 9 | 2017-05-13 | 13 | 11 | 8 | 8 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
461 | 9 | 2017-05-13 | 13 | 13 | 11 | 9 | 7 | 4 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
462 | 6 | 2017-04-22 | 10 | 8 | 5 | 5 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
463 | 13 | 2017-06-10 | 13 | 11 | 9 | 9 | 9 | 9 | 6 | 6 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
464 | 14 | 2017-06-17 | 15 | 15 | 15 | 12 | 12 | 12 | 10 | 7 | 7 | 7 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
465 | 6 | 2017-04-22 | 10 | 10 | 7 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
466 | 13 | 2017-06-10 | 9 | 9 | 9 | 6 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
467 | 15 | 2017-06-24 | 11 | 11 | 11 | 11 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
468 | 8 | 2017-05-06 | 9 | 9 | 9 | 7 | 4 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
469 | 5 | 2017-04-15 | 11 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
470 | 13 | 2017-06-10 | 9 | 9 | 9 | 9 | 7 | 7 | 5 | 5 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
471 | 7 | 2017-04-29 | 11 | 11 | 11 | 9 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
472 | 20 | 2017-07-29 | 15 | 13 | 13 | 13 | 13 | 13 | 13 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 7 | 7 | 7 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
473 | 9 | 2017-05-13 | 10 | 10 | 10 | 7 | 7 | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
474 | 13 | 2017-06-10 | 12 | 12 | 10 | 7 | 7 | 5 | 5 | 5 | 3 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
475 | 10 | 2017-05-20 | 13 | 13 | 13 | 13 | 10 | 7 | 7 | 5 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
476 | 7 | 2017-04-29 | 10 | 7 | 7 | 7 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
477 | 14 | 2017-06-17 | 14 | 11 | 8 | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
478 | 7 | 2017-04-29 | 10 | 10 | 10 | 10 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
479 | 9 | 2017-05-13 | 12 | 10 | 10 | 10 | 10 | 7 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
480 | 7 | 2017-04-29 | 11 | 11 | 11 | 8 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
481 | 5 | 2017-04-15 | 9 | 9 | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
482 | 15 | 2017-06-24 | 14 | 14 | 14 | 12 | 12 | 9 | 7 | 7 | 4 | 4 | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
483 | 5 | 2017-04-15 | 10 | 7 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
484 | 10 | 2017-05-20 | 11 | 11 | 11 | 8 | 8 | 8 | 8 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
485 | 11 | 2017-05-27 | 12 | 12 | 12 | 12 | 12 | 9 | 7 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
486 | 10 | 2017-05-20 | 11 | 11 | 9 | 9 | 6 | 6 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
487 | 9 | 2017-05-13 | 11 | 11 | 9 | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
488 | 21 | 2017-08-05 | 13 | 10 | 10 | 10 | 10 | 10 | 7 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
489 | 9 | 2017-05-13 | 10 | 8 | 8 | 5 | 5 | 5 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
490 | 12 | 2017-06-03 | 14 | 14 | 14 | 11 | 8 | 6 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
491 | 7 | 2017-04-29 | 13 | 11 | 8 | 6 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
492 | 9 | 2017-05-13 | 13 | 11 | 11 | 9 | 7 | 5 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
493 | 14 | 2017-06-17 | 11 | 9 | 9 | 9 | 9 | 9 | 7 | 7 | 7 | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
494 | 11 | 2017-05-27 | 12 | 12 | 9 | 7 | 7 | 7 | 5 | 5 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
495 | 8 | 2017-05-06 | 9 | 6 | 3 | 3 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
496 | 4 | 2017-04-08 | 9 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
497 | 12 | 2017-06-03 | 12 | 9 | 9 | 9 | 9 | 9 | 6 | 6 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
498 | 12 | 2017-06-03 | 15 | 12 | 9 | 9 | 7 | 4 | 4 | 4 | 4 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
499 | 14 | 2017-06-17 | 15 | 15 | 13 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 6 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
500 | 8 | 2017-05-06 | 11 | 11 | 9 | 9 | 6 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
501 | 14 | 2017-06-17 | 12 | 12 | 12 | 12 | 9 | 9 | 9 | 9 | 7 | 7 | 4 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
End of Zero Week = INDEX(D2:BD2,1,[Weeks to Zero]+1)

## Throughput Monte Carlo Weeks (hidden)
Trial # | Sumx | Sum4 | Sum8 | Sum12 | Sum16 | Sum20 | Sum24 | Sum28 | Sum32 | Sum36 | Sum40 | Sum44 | Sum48 | Sum52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
1 | 10 | 5 | 15 | 24 | 31 | 37 | 43 | 48 | 55 | 59 | 68 | 74 | 79 | 85 | 1 | 1 | 1 | 2 | 2 | 3 | 2 | 3 | 2 | 2 | 2 | 3 | 1 | 2 | 1 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 3 | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 2
2 | 8 | 5 | 10 | 19 | 24 | 32 | 40 | 46 | 54 | 61 | 69 | 79 | 89 | 98 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 3 | 2 | 2 | 1 | 1 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 2 | 1 | 2 | 3 | 2 | 2 | 1 | 2 | 3 | 1 | 3 | 1 | 2 | 3 | 2 | 3 | 1 | 3 | 3 | 3 | 3 | 3 | 1 | 2
3 | 10 | 7 | 12 | 18 | 27 | 34 | 42 | 47 | 55 | 63 | 70 | 75 | 81 | 85 | 1 | 2 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 3 | 1 | 3 | 1 | 2 | 3 | 1 | 2 | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 2 | 1 | 2 | 3 | 3 | 2 | 1 | 2 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1
4 | 11 | 8 | 15 | 24 | 32 | 37 | 46 | 55 | 61 | 69 | 73 | 82 | 87 | 94 | 1 | 3 | 1 | 3 | 1 | 2 | 1 | 3 | 3 | 3 | 1 | 2 | 2 | 2 | 1 | 3 | 1 | 1 | 2 | 1 | 2 | 2 | 3 | 2 | 3 | 1 | 3 | 2 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | 3 | 1
5 | 13 | 9 | 15 | 20 | 26 | 33 | 40 | 47 | 56 | 67 | 72 | 80 | 86 | 95 | 3 | 2 | 3 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 3 | 2 | 2 | 2 | 1 | 3 | 2 | 1 | 1 | 2 | 2 | 3 | 2 | 3 | 2 | 3 | 3 | 2 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 3 | 3
6 | 11 | 8 | 15 | 21 | 29 | 35 | 43 | 49 | 56 | 65 | 74 | 80 | 89 | 95 | 3 | 2 | 2 | 1 | 1 | 2 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 2 | 2 | 1 | 3 | 1 | 3 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 2 | 1 | 3 | 2 | 2 | 2 | 2 | 2 | 3 | 2 | 2 | 1 | 1 | 2 | 1 | 3 | 3 | 2 | 1 | 2 | 2 | 1
7 | 9 | 6 | 13 | 22 | 29 | 36 | 43 | 49 | 55 | 60 | 67 | 72 | 79 | 84 | 3 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 3 | 3 | 2 | 1 | 2 | 1 | 3 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 2 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 2
8 | 9 | 7 | 13 | 22 | 28 | 37 | 41 | 48 | 54 | 62 | 72 | 82 | 89 | 95 | 3 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 3 | 1 | 2 | 2 | 1 | 1 | 3 | 2 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 3 | 1 | 3 | 3 | 3 | 1 | 3 | 3 | 1 | 3 | 3 | 1 | 1 | 3 | 2 | 2 | 1 | 1 | 2
9 | 16 | 12 | 20 | 24 | 31 | 40 | 49 | 57 | 66 | 76 | 85 | 97 | 103 | 109 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 3 | 1 | 2 | 3 | 3 | 3 | 1 | 2 | 2 | 1 | 3 | 2 | 2 | 3 | 1 | 3 | 2 | 3 | 2 | 3 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 1
10 | 13 | 8 | 17 | 24 | 34 | 41 | 51 | 61 | 69 | 74 | 82 | 88 | 94 | 99 | 2 | 1 | 2 | 3 | 2 | 3 | 3 | 1 | 2 | 1 | 3 | 1 | 2 | 2 | 3 | 3 | 1 | 3 | 1 | 2 | 3 | 1 | 3 | 3 | 3 | 2 | 2 | 3 | 1 | 3 | 1 | 3 | 2 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2
11 | 8 | 6 | 12 | 18 | 25 | 34 | 39 | 47 | 55 | 62 | 69 | 74 | 83 | 88 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 3 | 2 | 3 | 1 | 1 | 2 | 1 | 2 | 1 | 3 | 2 | 3 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 3 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 3 | 3 | 2 | 1 | 1 | 2 | 1
12 | 11 | 7 | 16 | 20 | 28 | 34 | 38 | 43 | 50 | 59 | 66 | 72 | 77 | 83 | 2 | 1 | 3 | 1 | 1 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 2 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 2 | 1 | 3 | 2 | 1 | 3 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 1
13 | 11 | 7 | 13 | 20 | 24 | 31 | 37 | 47 | 53 | 63 | 70 | 76 | 86 | 92 | 1 | 2 | 1 | 3 | 1 | 3 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 3 | 3 | 3 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 1 | 1 | 1 | 3 | 3 | 3 | 1 | 3 | 1 | 1
14 | 12 | 8 | 16 | 24 | 32 | 37 | 47 | 52 | 60 | 67 | 76 | 82 | 93 | 99 | 3 | 2 | 1 | 2 | 3 | 1 | 2 | 2 | 1 | 1 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 2 | 3 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 3 | 2 | 1 | 3 | 1 | 2 | 3 | 3 | 1 | 1 | 1 | 1 | 3 | 2 | 3 | 3 | 3 | 1 | 1 | 2 | 2
15 | 11 | 6 | 17 | 23 | 30 | 38 | 48 | 58 | 67 | 77 | 83 | 89 | 97 | 101 | 1 | 3 | 1 | 1 | 3 | 2 | 3 | 3 | 1 | 3 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 2 | 3 | 2 | 3 | 3 | 3 | 1 | 2 | 2 | 3 | 3 | 2 | 3 | 3 | 1 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 3 | 2 | 2 | 1 | 1 | 3 | 1 | 2 | 2 | 1 | 1 | 1 | 1
16 | 8 | 6 | 12 | 17 | 22 | 30 | 37 | 45 | 55 | 63 | 69 | 76 | 82 | 90 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 3 | 1 | 2 | 1 | 3 | 3 | 1 | 1 | 3 | 3 | 3 | 3 | 1 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 3
17 | 11 | 9 | 15 | 25 | 34 | 40 | 45 | 51 | 57 | 63 | 68 | 73 | 77 | 86 | 1 | 2 | 3 | 3 | 1 | 1 | 3 | 1 | 3 | 1 | 3 | 3 | 2 | 3 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 3
18 | 7 | 5 | 11 | 17 | 25 | 33 | 39 | 44 | 52 | 58 | 62 | 68 | 78 | 86 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 3 | 3 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 3 | 2 | 1
19 | 13 | 10 | 17 | 26 | 36 | 45 | 55 | 64 | 70 | 80 | 87 | 94 | 101 | 106 | 2 | 2 | 3 | 3 | 1 | 2 | 2 | 2 | 3 | 2 | 1 | 3 | 1 | 3 | 3 | 3 | 3 | 2 | 1 | 3 | 3 | 3 | 1 | 3 | 2 | 1 | 3 | 3 | 2 | 1 | 1 | 2 | 1 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 3 | 2 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 2
20 | 10 | 5 | 14 | 19 | 27 | 35 | 43 | 50 | 55 | 63 | 73 | 78 | 84 | 94 | 1 | 2 | 1 | 1 | 2 | 3 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 1 | 2 | 3 | 2 | 2 | 2 | 3 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 2 | 1 | 2 | 3 | 3 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 2 | 3
21 | 10 | 4 | 15 | 22 | 31 | 39 | 47 | 52 | 60 | 65 | 73 | 80 | 84 | 94 | 1 | 1 | 1 | 1 | 3 | 3 | 2 | 3 | 2 | 3 | 1 | 1 | 3 | 1 | 3 | 2 | 2 | 3 | 2 | 1 | 3 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 3
22 | 8 | 6 | 11 | 15 | 24 | 32 | 38 | 43 | 49 | 57 | 64 | 71 | 78 | 82 | 1 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 2 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 3 | 3 | 2 | 1 | 3 | 1 | 2 | 2 | 2 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 1
23 | 11 | 7 | 17 | 25 | 32 | 41 | 52 | 60 | 68 | 78 | 85 | 90 | 95 | 102 | 2 | 3 | 1 | 1 | 3 | 1 | 3 | 3 | 2 | 2 | 1 | 3 | 3 | 1 | 2 | 1 | 3 | 2 | 1 | 3 | 2 | 3 | 3 | 3 | 2 | 2 | 1 | 3 | 3 | 1 | 1 | 3 | 3 | 2 | 3 | 2 | 1 | 1 | 2 | 3 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 2
24 | 13 | 7 | 15 | 20 | 25 | 34 | 41 | 46 | 54 | 62 | 68 | 73 | 82 | 86 | 2 | 1 | 3 | 1 | 3 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 3 | 3 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 1 | 1 | 3 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1
25 | 8 | 5 | 13 | 19 | 24 | 32 | 40 | 47 | 57 | 65 | 69 | 77 | 86 | 97 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 2 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 2 | 3 | 2 | 2 | 1 | 3 | 1 | 1 | 3 | 2 | 3 | 2 | 3 | 2 | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 2 | 1 | 2 | 3 | 3 | 3
26 | 10 | 7 | 16 | 22 | 31 | 40 | 46 | 52 | 59 | 63 | 68 | 79 | 90 | 98 | 2 | 1 | 3 | 1 | 1 | 2 | 3 | 3 | 3 | 1 | 1 | 1 | 3 | 3 | 1 | 2 | 3 | 3 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 2 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 1 | 3 | 1
27 | 9 | 6 | 11 | 16 | 21 | 30 | 37 | 45 | 52 | 60 | 70 | 78 | 86 | 97 | 2 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 1 | 2 | 1 | 3 | 1 | 3 | 3 | 1 | 2 | 3 | 1 | 1 | 3 | 1 | 1 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 3 | 3 | 3 | 1 | 1 | 3 | 3 | 3 | 3 | 2
28 | 12 | 10 | 14 | 21 | 26 | 34 | 41 | 49 | 58 | 65 | 72 | 77 | 81 | 89 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 2 | 1 | 1 | 2 | 3 | 1 | 2 | 1 | 3 | 1 | 2 | 3 | 1 | 1 | 3 | 2 | 1 | 3 | 3 | 3 | 1 | 2 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3
29 | 15 | 10 | 18 | 23 | 31 | 39 | 47 | 54 | 60 | 67 | 73 | 78 | 85 | 91 | 2 | 2 | 3 | 3 | 2 | 3 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 3 | 2 | 1 | 3 | 3 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 2 | 3 | 1 | 3 | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 3
30 | 9 | 7 | 13 | 21 | 29 | 36 | 46 | 52 | 57 | 64 | 70 | 77 | 83 | 89 | 2 | 3 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 2 | 1 | 3 | 3 | 3 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 2 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | 2
31 | 10 | 7 | 15 | 22 | 30 | 36 | 44 | 54 | 61 | 72 | 77 | 85 | 92 | 99 | 2 | 1 | 2 | 2 | 1 | 2 | 2 | 3 | 1 | 3 | 1 | 2 | 3 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 3 | 3 | 1 | 3 | 2 | 2 | 3 | 1 | 3 | 2 | 1 | 3 | 3 | 3 | 2 | 1 | 1 | 2 | 1 | 3 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | 3 | 1 | 1 | 2
32 | 11 | 7 | 13 | 23 | 28 | 35 | 42 | 46 | 54 | 59 | 68 | 77 | 86 | 92 | 1 | 1 | 2 | 3 | 3 | 1 | 1 | 1 | 3 | 1 | 3 | 3 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 1 | 1 | 2 | 1 | 1 | 3 | 2 | 1 | 3 | 1 | 3 | 3 | 2 | 3 | 3 | 1 | 2 | 1 | 2 | 1 | 2
33 | 8 | 6 | 11 | 19 | 26 | 34 | 41 | 49 | 58 | 64 | 73 | 78 | 83 | 91 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 2 | 2 | 2 | 1 | 3 | 1 | 2 | 2 | 3 | 1 | 1 | 2 | 3 | 1 | 1 | 3 | 2 | 2 | 2 | 1 | 3 | 3 | 1 | 3 | 1 | 1 | 3 | 3 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 3
34 | 8 | 5 | 13 | 20 | 25 | 29 | 36 | 45 | 52 | 59 | 64 | 72 | 79 | 86 | 2 | 1 | 1 | 1 | 2 | 1 | 2 | 3 | 1 | 3 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 2 | 3 | 1 | 3 | 3 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 3 | 3 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 2 | 1 | 3
35 | 13 | 8 | 17 | 23 | 30 | 35 | 40 | 46 | 55 | 62 | 68 | 76 | 84 | 88 | 1 | 1 | 3 | 3 | 3 | 2 | 3 | 1 | 2 | 1 | 2 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 3 | 2 | 3 | 1 | 1 | 1 | 2 | 3 | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 3 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 1
36 | 13 | 9 | 17 | 22 | 32 | 39 | 48 | 55 | 61 | 72 | 81 | 85 | 93 | 100 | 2 | 3 | 3 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 3 | 3 | 3 | 1 | 1 | 2 | 1 | 2 | 3 | 3 | 2 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 3 | 2 | 3 | 2 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 2
37 | 9 | 7 | 12 | 18 | 27 | 34 | 41 | 48 | 53 | 62 | 66 | 76 | 84 | 90 | 2 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 2 | 3 | 3 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 2 | 1 | 1 | 2 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 1
38 | 11 | 8 | 14 | 21 | 27 | 34 | 41 | 52 | 60 | 69 | 78 | 87 | 91 | 97 | 1 | 2 | 3 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 3 | 1 | 3 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 1 | 1 | 3 | 2 | 1 | 3 | 1 | 2 | 3 | 3 | 3 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2
39 | 11 | 9 | 15 | 24 | 31 | 38 | 46 | 52 | 58 | 68 | 75 | 83 | 89 | 97 | 2 | 2 | 3 | 2 | 1 | 1 | 2 | 2 | 3 | 2 | 3 | 1 | 2 | 1 | 1 | 3 | 2 | 3 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 3 | 2 | 2 | 3 | 2 | 3 | 1 | 1 | 2 | 1 | 3 | 2 | 1 | 3 | 1 | 1 | 3 | 3 | 1 | 1
40 | 10 | 6 | 12 | 22 | 29 | 35 | 42 | 49 | 55 | 59 | 66 | 71 | 78 | 84 | 1 | 2 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 3 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 3 | 1 | 1
41 | 10 | 6 | 15 | 21 | 31 | 38 | 45 | 51 | 57 | 64 | 71 | 77 | 83 | 88 | 2 | 2 | 1 | 1 | 3 | 1 | 3 | 2 | 2 | 1 | 2 | 1 | 2 | 3 | 2 | 3 | 1 | 1 | 3 | 2 | 1 | 1 | 2 | 3 | 2 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 3 | 1 | 2 | 3 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 2
42 | 7 | 4 | 12 | 21 | 27 | 31 | 38 | 45 | 52 | 58 | 65 | 71 | 77 | 82 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 1 | 2 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 1 | 3 | 1 | 2 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 1 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 1 | 1
43 | 10 | 4 | 14 | 19 | 23 | 29 | 36 | 44 | 51 | 60 | 67 | 74 | 81 | 88 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 1 | 3 | 2 | 2 | 3 | 1 | 1 | 2 | 2 | 3 | 3 | 1 | 1 | 3 | 2 | 1 | 1 | 3 | 2 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 3 | 2
44 | 12 | 7 | 15 | 19 | 25 | 34 | 41 | 46 | 53 | 63 | 72 | 76 | 82 | 89 | 1 | 2 | 3 | 1 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 1 | 3 | 3 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 2 | 3 | 1 | 3 | 3 | 2 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 3
45 | 12 | 9 | 16 | 20 | 27 | 33 | 37 | 43 | 47 | 51 | 58 | 66 | 74 | 82 | 3 | 2 | 1 | 3 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 3 | 2 | 2 | 1 | 2 | 3 | 1 | 1 | 3 | 3
46 | 10 | 6 | 14 | 22 | 31 | 35 | 41 | 49 | 57 | 63 | 70 | 79 | 87 | 91 | 1 | 2 | 1 | 2 | 1 | 3 | 2 | 2 | 3 | 1 | 1 | 3 | 3 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 3 | 1 | 2 | 2 | 1 | 2 | 2 | 3 | 1 | 1 | 3 | 1 | 2 | 2 | 2 | 1 | 2 | 3 | 3 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1
47 | 10 | 7 | 12 | 18 | 25 | 31 | 39 | 45 | 53 | 60 | 66 | 76 | 81 | 91 | 3 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 3 | 2 | 3 | 2 | 3 | 1 | 1 | 1 | 2 | 1 | 3 | 3 | 3
48 | 12 | 6 | 14 | 21 | 29 | 34 | 42 | 50 | 58 | 64 | 73 | 79 | 85 | 91 | 2 | 2 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 2 | 2 | 3 | 1 | 2 | 1 | 1 | 1 | 3 | 2 | 2 | 3 | 2 | 1 | 2 | 3 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 3 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 1
49 | 11 | 8 | 17 | 27 | 34 | 40 | 47 | 52 | 58 | 66 | 75 | 81 | 86 | 95 | 1 | 3 | 1 | 3 | 1 | 2 | 3 | 3 | 3 | 3 | 1 | 3 | 2 | 1 | 1 | 3 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 3 | 1 | 2 | 3 | 3 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 3 | 3
50 | 15 | 10 | 18 | 25 | 31 | 38 | 48 | 54 | 58 | 65 | 71 | 78 | 84 | 92 | 1 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 2 | 3 | 1 | 3 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 2 | 2 | 1 | 1 | 1 | 3 | 2 | 1 | 2 | 2 | 1 | 3 | 1 | 2 | 2
51 | 8 | 6 | 11 | 18 | 22 | 28 | 35 | 42 | 48 | 55 | 63 | 72 | 77 | 84 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 2 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 3 | 3 | 1 | 3 | 1 | 3 | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 3
52 | 10 | 7 | 16 | 23 | 31 | 37 | 44 | 48 | 55 | 65 | 72 | 78 | 86 | 93 | 1 | 3 | 2 | 1 | 1 | 2 | 3 | 3 | 1 | 2 | 3 | 1 | 1 | 3 | 2 | 2 | 1 | 3 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 2 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 3 | 2 | 1 | 3 | 1
53 | 8 | 6 | 11 | 20 | 29 | 36 | 43 | 48 | 58 | 69 | 75 | 82 | 89 | 95 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 3 | 2 | 1 | 3 | 3 | 2 | 2 | 2 | 1 | 2 | 3 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 1 | 1 | 3 | 3 | 3 | 1 | 2 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 2 | 2 | 1
54 | 13 | 7 | 17 | 22 | 27 | 33 | 39 | 49 | 55 | 62 | 69 | 75 | 82 | 90 | 2 | 2 | 1 | 2 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 3 | 2 | 3 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 1 | 3 | 1 | 1 | 3
55 | 11 | 7 | 15 | 22 | 30 | 38 | 42 | 50 | 57 | 67 | 76 | 80 | 88 | 97 | 1 | 1 | 2 | 3 | 3 | 1 | 3 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 2 | 2 | 1 | 3 | 2 | 3 | 2 | 3 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 2 | 2 | 1 | 2 | 2 | 2 | 3
56 | 13 | 10 | 17 | 23 | 31 | 36 | 42 | 51 | 57 | 64 | 72 | 77 | 85 | 89 | 3 | 3 | 3 | 1 | 2 | 1 | 2 | 2 | 3 | 1 | 1 | 1 | 1 | 3 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 3 | 1 | 2 | 3 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 3 | 3 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 1
57 | 10 | 7 | 13 | 19 | 24 | 30 | 37 | 43 | 50 | 57 | 65 | 70 | 78 | 88 | 2 | 1 | 2 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 3 | 2 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 3 | 3 | 2 | 2
58 | 10 | 6 | 13 | 18 | 25 | 33 | 42 | 48 | 52 | 59 | 63 | 69 | 76 | 82 | 1 | 3 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 3 | 3 | 2 | 3 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 2 | 1 | 2
59 | 12 | 8 | 16 | 21 | 28 | 36 | 42 | 52 | 61 | 68 | 76 | 81 | 88 | 92 | 1 | 3 | 2 | 2 | 3 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 3 | 2 | 2 | 1 | 1 | 2 | 1 | 2 | 3 | 3 | 3 | 1 | 3 | 2 | 3 | 1 | 2 | 2 | 2 | 1 | 2 | 3 | 1 | 2 | 1 | 1 | 1 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1
60 | 14 | 9 | 16 | 21 | 29 | 38 | 46 | 53 | 61 | 67 | 73 | 79 | 89 | 98 | 2 | 2 | 2 | 3 | 2 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 3 | 3 | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 3 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 3 | 1 | 3 | 3 | 2 | 3 | 3 | 1
61 | 8 | 4 | 12 | 19 | 27 | 31 | 37 | 43 | 51 | 58 | 65 | 71 | 81 | 85 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 2 | 2 | 2 | 1 | 3 | 1 | 2 | 1 | 2 | 2 | 2 | 1 | 1 | 2 | 3 | 2 | 2 | 3 | 1 | 1 | 1 | 1
62 | 13 | 10 | 17 | 27 | 32 | 38 | 43 | 53 | 60 | 67 | 76 | 82 | 90 | 94 | 3 | 3 | 1 | 3 | 1 | 2 | 1 | 3 | 1 | 3 | 3 | 3 | 1 | 2 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 3 | 3 | 3 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 1 | 1 | 1 | 3 | 2 | 3 | 1 | 1 | 3 | 1 | 3 | 2 | 1 | 2 | 1 | 1 | 1 | 1
63 | 13 | 7 | 15 | 24 | 29 | 38 | 44 | 52 | 60 | 66 | 70 | 75 | 85 | 93 | 2 | 1 | 3 | 1 | 3 | 3 | 1 | 1 | 2 | 2 | 2 | 3 | 1 | 1 | 2 | 1 | 3 | 1 | 3 | 2 | 1 | 1 | 1 | 3 | 2 | 2 | 3 | 1 | 1 | 3 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 3 | 3 | 3 | 1 | 3 | 1
64 | 8 | 6 | 12 | 19 | 23 | 29 | 33 | 37 | 45 | 51 | 56 | 62 | 66 | 72 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1
65 | 10 | 7 | 12 | 22 | 29 | 41 | 50 | 60 | 70 | 79 | 89 | 97 | 105 | 111 | 3 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 3 | 2 | 3 | 2 | 2 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 1 | 3 | 3 | 3 | 3 | 1 | 2 | 3 | 2 | 3 | 3 | 1 | 3 | 2 | 3 | 1 | 3 | 3 | 3 | 1 | 1 | 3 | 1 | 1 | 3 | 3 | 1 | 1 | 3 | 1
66 | 10 | 7 | 13 | 19 | 25 | 34 | 44 | 51 | 57 | 63 | 71 | 77 | 84 | 92 | 1 | 3 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 3 | 2 | 3 | 2 | 3 | 2 | 3 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 3 | 3
67 | 9 | 5 | 13 | 19 | 27 | 32 | 41 | 48 | 53 | 60 | 65 | 72 | 81 | 88 | 1 | 1 | 2 | 1 | 3 | 1 | 2 | 2 | 1 | 3 | 1 | 1 | 2 | 2 | 3 | 1 | 1 | 1 | 2 | 1 | 3 | 3 | 1 | 2 | 1 | 1 | 3 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 2 | 3 | 2 | 2 | 1 | 3 | 2 | 1
68 | 11 | 7 | 15 | 20 | 30 | 36 | 42 | 47 | 53 | 59 | 66 | 72 | 80 | 86 | 2 | 3 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 2 | 1 | 2 | 3 | 3 | 2 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 2 | 1 | 2 | 2 | 1
69 | 10 | 7 | 15 | 19 | 26 | 36 | 42 | 49 | 61 | 69 | 75 | 83 | 88 | 95 | 1 | 2 | 3 | 1 | 2 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 3 | 3 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 1 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 3 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 1
70 | 10 | 7 | 12 | 19 | 28 | 38 | 46 | 51 | 61 | 67 | 73 | 80 | 85 | 92 | 1 | 1 | 2 | 3 | 2 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 1 | 3 | 2 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 3 | 1
71 | 11 | 7 | 14 | 24 | 31 | 38 | 44 | 50 | 57 | 67 | 78 | 84 | 92 | 97 | 1 | 2 | 2 | 2 | 3 | 1 | 2 | 1 | 3 | 2 | 3 | 2 | 2 | 1 | 1 | 3 | 2 | 1 | 1 | 3 | 1 | 2 | 2 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 1 | 3 | 2 | 3 | 2 | 2 | 3 | 3 | 3 | 1 | 2 | 1 | 2 | 3 | 1 | 3 | 1 | 1 | 2 | 1 | 1
72 | 10 | 6 | 13 | 18 | 24 | 31 | 41 | 50 | 56 | 63 | 71 | 75 | 85 | 92 | 1 | 1 | 1 | 3 | 1 | 3 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 2 | 1 | 3 | 1 | 3 | 3 | 3 | 2 | 1 | 3 | 1 | 2 | 1 | 2 | 1 | 1 | 2 | 3 | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 1 | 1 | 2 | 3 | 1
73 | 9 | 7 | 13 | 21 | 27 | 33 | 44 | 49 | 55 | 61 | 67 | 73 | 81 | 86 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 3 | 2 | 2 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 2 | 3 | 3 | 3 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 2 | 1 | 2 | 2 | 1 | 1 | 2 | 1 | 3 | 2 | 1 | 2 | 1 | 1
74 | 12 | 9 | 16 | 20 | 25 | 31 | 36 | 42 | 48 | 57 | 62 | 70 | 75 | 81 | 3 | 3 | 2 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 2 | 3 | 1 | 1 | 1 | 2 | 1 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 1
75 | 9 | 4 | 11 | 19 | 26 | 33 | 41 | 47 | 53 | 61 | 67 | 74 | 83 | 89 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 3 | 3 | 1 | 3 | 2 | 1 | 1 | 1 | 3 | 2 | 1 | 2 | 3 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 3 | 1 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | 2 | 3 | 3 | 1 | 2 | 1 | 1 | 2
76 | 15 | 10 | 17 | 24 | 32 | 38 | 44 | 50 | 58 | 65 | 70 | 76 | 81 | 89 | 2 | 2 | 3 | 3 | 2 | 3 | 1 | 1 | 1 | 2 | 3 | 1 | 3 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 3
77 | 12 | 10 | 16 | 24 | 31 | 37 | 42 | 48 | 53 | 58 | 66 | 74 | 83 | 90 | 3 | 2 | 3 | 2 | 1 | 1 | 3 | 1 | 2 | 2 | 3 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 1 | 1 | 1 | 3 | 3 | 1 | 3 | 1 | 3 | 2 | 1 | 2 | 1 | 3
78 | 10 | 7 | 13 | 24 | 32 | 43 | 50 | 56 | 65 | 75 | 81 | 90 | 95 | 100 | 2 | 1 | 3 | 1 | 2 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 2 | 2 | 1 | 3 | 3 | 2 | 3 | 3 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 2 | 3 | 2 | 3 | 3 | 2 | 1 | 2 | 1 | 2 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1
79 | 12 | 8 | 15 | 24 | 28 | 34 | 40 | 49 | 57 | 65 | 73 | 81 | 89 | 97 | 1 | 3 | 3 | 1 | 1 | 3 | 2 | 1 | 3 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 3 | 1 | 1 | 3 | 3 | 1 | 3 | 3 | 1 | 1 | 3 | 1 | 3 | 1 | 3 | 3 | 1 | 3 | 3 | 1 | 1 | 3 | 2 | 2 | 1
80 | 7 | 5 | 10 | 16 | 25 | 31 | 36 | 43 | 51 | 60 | 68 | 75 | 82 | 86 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 2 | 3 | 1 | 3 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 2 | 3 | 1 | 3 | 1 | 3 | 3 | 1 | 2 | 1 | 3 | 3 | 1 | 1 | 2 | 3 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 1
81 | 12 | 8 | 16 | 25 | 34 | 38 | 47 | 53 | 59 | 66 | 70 | 79 | 89 | 99 | 2 | 2 | 2 | 2 | 3 | 1 | 3 | 1 | 2 | 3 | 1 | 3 | 3 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 2 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 3 | 3 | 3 | 3 | 1 | 3 | 3 | 3 | 1
82 | 12 | 7 | 16 | 25 | 30 | 34 | 40 | 45 | 52 | 57 | 64 | 71 | 78 | 87 | 2 | 3 | 1 | 1 | 3 | 2 | 2 | 2 | 2 | 1 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 3
83 | 9 | 7 | 11 | 20 | 27 | 35 | 43 | 51 | 61 | 69 | 78 | 86 | 94 | 102 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 2 | 3 | 1 | 2 | 1 | 2 | 3 | 1 | 2 | 2 | 3 | 2 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 3 | 3 | 1 | 2 | 2 | 2 | 3 | 2 | 2 | 1 | 1 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 1
84 | 10 | 5 | 14 | 18 | 23 | 31 | 37 | 46 | 51 | 56 | 62 | 67 | 71 | 79 | 2 | 1 | 1 | 1 | 3 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 3 | 1 | 1 | 2 | 1 | 3 | 3 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 3
85 | 7 | 4 | 11 | 18 | 27 | 35 | 41 | 51 | 58 | 64 | 70 | 78 | 86 | 92 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 3 | 1 | 2 | 1 | 1 | 3 | 2 | 3 | 3 | 1 | 3 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 3 | 3 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 3 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 3
86 | 13 | 8 | 16 | 22 | 27 | 34 | 40 | 45 | 52 | 60 | 66 | 70 | 74 | 82 | 3 | 2 | 2 | 1 | 2 | 3 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 3 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 3 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 1
87 | 10 | 8 | 12 | 18 | 26 | 31 | 38 | 42 | 48 | 55 | 62 | 68 | 73 | 78 | 1 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 3 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 3 | 1 | 1 | 2 | 3 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1
88 | 11 | 8 | 13 | 20 | 25 | 32 | 37 | 44 | 53 | 61 | 69 | 76 | 84 | 88 | 1 | 3 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 1 | 3 | 2 | 1 | 2 | 3 | 2 | 3 | 1 | 2 | 3 | 2 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 1
89 | 14 | 10 | 16 | 22 | 32 | 37 | 45 | 51 | 56 | 62 | 67 | 72 | 82 | 90 | 2 | 3 | 2 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 3 | 3 | 1 | 1 | 2 | 1 | 1 | 3 | 2 | 2 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 1 | 3 | 3 | 1
90 | 15 | 11 | 19 | 26 | 33 | 40 | 45 | 51 | 61 | 69 | 74 | 85 | 92 | 100 | 3 | 3 | 3 | 2 | 2 | 2 | 3 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 2 | 2 | 3 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 3 | 3 | 1 | 2 | 2 | 2 | 1 | 3 | 2 | 2
91 | 9 | 6 | 11 | 21 | 31 | 40 | 50 | 55 | 63 | 72 | 79 | 88 | 96 | 102 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 3 | 3 | 3 | 1 | 3 | 1 | 3 | 3 | 3 | 2 | 1 | 3 | 3 | 2 | 2 | 3 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 3 | 3 | 2 | 3 | 1 | 2 | 2 | 1 | 2 | 1 | 3 | 3 | 2 | 1 | 3 | 3 | 1 | 1 | 1 | 3 | 1
92 | 6 | 4 | 8 | 16 | 22 | 30 | 37 | 45 | 52 | 58 | 64 | 69 | 75 | 84 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 2 | 2 | 1 | 1 | 3 | 1 | 3 | 1 | 3 | 2 | 1 | 1 | 1 | 3 | 1 | 3 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 2 | 3
93 | 11 | 7 | 14 | 18 | 26 | 30 | 36 | 44 | 48 | 53 | 59 | 64 | 71 | 78 | 3 | 1 | 1 | 2 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 3 | 1 | 2 | 1 | 1 | 3 | 2 | 1
94 | 12 | 7 | 15 | 19 | 26 | 33 | 43 | 48 | 56 | 64 | 68 | 74 | 81 | 88 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 2 | 1 | 3 | 3 | 3 | 1 | 3 | 1 | 2 | 1 | 1 | 2 | 3 | 2 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 3 | 2
95 | 9 | 5 | 11 | 18 | 26 | 30 | 36 | 44 | 54 | 60 | 67 | 77 | 83 | 90 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 1 | 1 | 3 | 3 | 1 | 3 | 1 | 1 | 3 | 1 | 2 | 1 | 3 | 1 | 3 | 3 | 2 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | 1
96 | 10 | 6 | 15 | 19 | 23 | 27 | 33 | 40 | 47 | 55 | 64 | 72 | 78 | 86 | 1 | 1 | 2 | 2 | 3 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 3 | 1 | 1 | 3 | 1 | 2 | 2 | 3 | 1 | 2 | 2 | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 3
97 | 10 | 7 | 12 | 19 | 26 | 32 | 43 | 52 | 58 | 63 | 73 | 81 | 86 | 95 | 2 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 3 | 3 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 2 | 3 | 1 | 3
98 | 14 | 12 | 17 | 25 | 32 | 38 | 46 | 55 | 64 | 69 | 74 | 80 | 89 | 94 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 3 | 1 | 2 | 2 | 2 | 1 | 3 | 1 | 1 | 3 | 2 | 2 | 1 | 3 | 3 | 1 | 2 | 3 | 1 | 3 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 3 | 3 | 1 | 1 | 2 | 1
99 | 15 | 9 | 18 | 26 | 32 | 38 | 43 | 49 | 57 | 61 | 67 | 73 | 80 | 88 | 1 | 3 | 3 | 2 | 3 | 3 | 2 | 1 | 3 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 1 | 1
100 | 14 | 9 | 18 | 25 | 32 | 38 | 47 | 55 | 64 | 71 | 76 | 85 | 93 | 101 | 3 | 1 | 2 | 3 | 2 | 3 | 1 | 3 | 2 | 1 | 1 | 3 | 2 | 1 | 3 | 1 | 1 | 2 | 1 | 2 | 2 | 3 | 1 | 3 | 3 | 2 | 2 | 1 | 3 | 2 | 1 | 3 | 1 | 2 | 1 | 3 | 1 | 2 | 1 | 1 | 3 | 3 | 2 | 1 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 3
101 | 9 | 6 | 14 | 18 | 27 | 37 | 44 | 53 | 58 | 63 | 70 | 76 | 82 | 92 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 3 | 1 | 1 | 1 | 1 | 3 | 3 | 2 | 1 | 2 | 3 | 3 | 2 | 3 | 1 | 2 | 1 | 1 | 2 | 3 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 2 | 3 | 2
102 | 9 | 6 | 13 | 19 | 27 | 33 | 38 | 42 | 48 | 55 | 61 | 68 | 73 | 79 | 1 | 3 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 1 | 1 | 1 | 2 | 1 | 2 | 3 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 3 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 2
103 | 10 | 8 | 12 | 21 | 27 | 33 | 38 | 46 | 51 | 56 | 62 | 69 | 78 | 86 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 2 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 2 | 2 | 3 | 2 | 3 | 1 | 1 | 3
104 | 8 | 4 | 10 | 18 | 26 | 30 | 39 | 49 | 56 | 61 | 66 | 72 | 77 | 84 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 2 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 3 | 2 | 3 | 3 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 1
105 | 8 | 5 | 12 | 20 | 26 | 32 | 38 | 44 | 52 | 59 | 65 | 72 | 76 | 82 | 1 | 1 | 2 | 1 | 1 | 2 | 3 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 2 | 3 | 1 | 1 | 1 | 2 | 3 | 2 | 1 | 2 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1
106 | 10 | 6 | 14 | 24 | 31 | 37 | 44 | 52 | 60 | 66 | 74 | 82 | 89 | 94 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 3 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 3 | 1 | 2 | 3 | 2 | 1 | 2 | 3 | 1 | 2 | 1 | 1 | 1 | 3 | 2 | 1 | 3 | 2 | 3 | 3 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 2 | 1 | 1
107 | 10 | 7 | 13 | 20 | 26 | 30 | 35 | 40 | 44 | 49 | 55 | 62 | 72 | 80 | 3 | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 2 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 1 | 2 | 2 | 3 | 3 | 2 | 1 | 3 | 3 | 1
108 | 13 | 8 | 18 | 22 | 29 | 35 | 43 | 49 | 59 | 65 | 71 | 80 | 89 | 95 | 2 | 2 | 1 | 3 | 2 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 3 | 3 | 3 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 3 | 3 | 1 | 2 | 3 | 3 | 1 | 2 | 1 | 1 | 3 | 1
109 | 11 | 6 | 14 | 21 | 32 | 39 | 46 | 52 | 60 | 69 | 76 | 83 | 93 | 101 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 2 | 1 | 3 | 1 | 2 | 3 | 2 | 3 | 3 | 3 | 1 | 1 | 2 | 1 | 3 | 1 | 2 | 1 | 2 | 1 | 2 | 3 | 3 | 1 | 1 | 2 | 2 | 2 | 3 | 1 | 2 | 2 | 2 | 3 | 1 | 2 | 1 | 3 | 3 | 1 | 3 | 3 | 1 | 1 | 3
110 | 12 | 8 | 15 | 21 | 30 | 34 | 43 | 51 | 59 | 66 | 73 | 80 | 86 | 94 | 3 | 1 | 1 | 3 | 3 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 3 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 2 | 1 | 3 | 1 | 3 | 3 | 1 | 3 | 1 | 1 | 3 | 1 | 2 | 2 | 1 | 1 | 3 | 3 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 2 | 3 | 1 | 2
111 | 7 | 5 | 10 | 19 | 24 | 28 | 34 | 42 | 51 | 56 | 66 | 75 | 80 | 87 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 2 | 2 | 3 | 1 | 3 | 2 | 1 | 2 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 2 | 1 | 3 | 1 | 1 | 2 | 1 | 2 | 2 | 2 | 1
112 | 8 | 4 | 10 | 17 | 24 | 34 | 41 | 48 | 54 | 60 | 65 | 73 | 84 | 91 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 2 | 1 | 3 | 3 | 3 | 1 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 3 | 2 | 2 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 2 | 1 | 2 | 2 | 3 | 3 | 3 | 2 | 2 | 2 | 1
113 | 11 | 7 | 14 | 23 | 28 | 34 | 40 | 46 | 52 | 61 | 67 | 75 | 81 | 87 | 2 | 3 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 3 | 2 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 3 | 3 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3
114 | 7 | 4 | 10 | 16 | 22 | 31 | 39 | 43 | 50 | 57 | 65 | 71 | 78 | 88 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 2 | 3 | 3 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 2 | 1 | 3 | 1 | 2 | 1 | 2 | 3 | 1 | 3 | 1 | 1 | 2 | 3 | 1 | 1 | 3 | 2 | 3 | 2
115 | 13 | 8 | 15 | 20 | 24 | 31 | 38 | 49 | 56 | 63 | 69 | 77 | 87 | 95 | 2 | 2 | 1 | 3 | 3 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 2 | 3 | 2 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 3 | 3 | 1 | 1 | 3 | 2 | 2 | 3 | 1 | 2 | 2 | 3
116 | 10 | 8 | 13 | 23 | 30 | 39 | 48 | 55 | 62 | 66 | 74 | 81 | 90 | 101 | 1 | 3 | 3 | 1 | 1 | 1 | 2 | 1 | 3 | 2 | 3 | 2 | 3 | 1 | 1 | 2 | 3 | 2 | 3 | 1 | 3 | 3 | 1 | 2 | 2 | 1 | 3 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 3 | 2 | 3 | 3 | 2 | 3 | 3
117 | 7 | 5 | 13 | 23 | 28 | 33 | 40 | 48 | 52 | 60 | 66 | 71 | 78 | 83 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 1 | 3 | 3 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 1 | 2 | 1 | 1
118 | 8 | 6 | 12 | 21 | 29 | 33 | 38 | 45 | 54 | 63 | 68 | 74 | 80 | 84 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 1 | 2 | 3 | 3 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 3 | 3 | 1 | 2 | 3 | 2 | 1 | 3 | 3 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1
119 | 10 | 8 | 13 | 18 | 28 | 33 | 41 | 49 | 61 | 68 | 73 | 81 | 85 | 91 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 1 | 3 | 2 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1
120 | 7 | 5 | 9 | 18 | 26 | 34 | 42 | 49 | 57 | 65 | 73 | 79 | 86 | 94 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 3 | 1 | 3 | 3 | 1 | 3 | 2 | 2 | 1 | 3 | 3 | 1 | 1 | 3 | 1 | 1 | 2 | 3 | 3 | 1 | 1 | 3 | 2 | 2 | 1 | 1 | 3 | 3 | 1 | 2 | 2 | 1 | 1 | 2 | 1 | 3 | 1 | 3 | 1 | 2 | 2
121 | 9 | 6 | 13 | 17 | 26 | 34 | 39 | 44 | 51 | 57 | 64 | 70 | 76 | 86 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 3 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 2 | 2 | 3
122 | 8 | 5 | 12 | 21 | 27 | 35 | 42 | 49 | 58 | 62 | 70 | 81 | 86 | 96 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 1 | 3 | 3 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 2 | 1 | 2 | 1 | 3 | 3 | 2 | 1 | 1 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 2 | 3 | 3 | 3 | 1 | 2 | 1 | 1 | 3 | 3 | 1 | 3
123 | 7 | 5 | 9 | 13 | 20 | 27 | 34 | 42 | 49 | 53 | 62 | 70 | 76 | 82 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 3 | 1 | 2 | 1 | 1 | 3 | 3 | 1 | 2 | 2 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 3 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 1
124 | 13 | 9 | 19 | 26 | 33 | 42 | 50 | 57 | 64 | 72 | 80 | 87 | 91 | 101 | 3 | 3 | 2 | 1 | 1 | 3 | 3 | 3 | 3 | 1 | 1 | 2 | 3 | 1 | 2 | 1 | 2 | 3 | 2 | 2 | 1 | 3 | 3 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 3 | 2 | 2 | 3 | 1 | 1 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 3
125 | 10 | 6 | 13 | 19 | 27 | 34 | 41 | 49 | 53 | 62 | 68 | 75 | 82 | 87 | 3 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 3 | 2 | 3 | 1 | 1 | 3 | 1 | 2 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 2 | 1 | 3 | 2 | 1 | 2 | 1 | 1 | 1
126 | 7 | 4 | 10 | 16 | 24 | 30 | 37 | 45 | 53 | 59 | 64 | 74 | 80 | 85 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 2 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 3 | 3 | 2 | 1 | 2 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 3 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 1
127 | 10 | 5 | 15 | 22 | 28 | 33 | 40 | 45 | 49 | 58 | 63 | 69 | 77 | 81 | 1 | 1 | 2 | 1 | 3 | 2 | 3 | 2 | 3 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 1
128 | 12 | 8 | 14 | 23 | 27 | 33 | 40 | 50 | 57 | 65 | 73 | 79 | 89 | 97 | 1 | 1 | 3 | 3 | 1 | 3 | 1 | 1 | 2 | 2 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 3 | 1 | 3 | 2 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 2 | 1 | 3 | 2 | 1 | 3 | 2 | 1 | 1 | 2 | 2 | 3 | 1 | 3 | 3 | 2 | 3 | 2 | 1
129 | 10 | 6 | 13 | 17 | 25 | 33 | 42 | 47 | 54 | 58 | 63 | 70 | 78 | 84 | 1 | 1 | 1 | 3 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 3 | 2 | 1 | 2 | 2 | 1 | 3 | 3 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 3
130 | 12 | 8 | 14 | 20 | 26 | 31 | 42 | 48 | 56 | 64 | 72 | 78 | 82 | 87 | 1 | 3 | 1 | 3 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 3 | 2 | 3 | 1 | 2 | 3 | 1 | 1 | 3 | 1 | 1 | 3 | 3 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
131 | 12 | 6 | 14 | 22 | 31 | 41 | 48 | 55 | 61 | 65 | 73 | 78 | 86 | 94 | 1 | 1 | 3 | 1 | 3 | 3 | 1 | 1 | 3 | 3 | 1 | 1 | 2 | 3 | 2 | 2 | 3 | 3 | 2 | 2 | 1 | 1 | 2 | 3 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 3 | 2 | 2 | 3 | 1 | 1 | 3
132 | 9 | 6 | 12 | 19 | 25 | 32 | 42 | 48 | 54 | 63 | 69 | 76 | 82 | 89 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | 3 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 2 | 2 | 3 | 3 | 1 | 2 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 3 | 3 | 2 | 2 | 2 | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 2 | 1 | 2 | 3 | 2 | 1 | 1
133 | 8 | 4 | 12 | 19 | 25 | 31 | 39 | 47 | 54 | 61 | 65 | 72 | 79 | 88 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 3 | 1 | 1 | 2 | 1 | 2 | 1 | 3 | 2 | 1 | 2 | 3 | 1 | 1 | 3 | 1 | 3 | 1 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 3 | 1 | 2 | 1 | 2 | 3 | 2 | 2
134 | 13 | 10 | 15 | 22 | 29 | 34 | 43 | 52 | 56 | 64 | 70 | 76 | 82 | 89 | 3 | 2 | 3 | 2 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 2 | 3 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 2 | 2 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 2 | 2 | 1 | 1 | 2 | 1 | 3 | 1
135 | 13 | 11 | 17 | 25 | 31 | 38 | 44 | 49 | 54 | 64 | 70 | 75 | 83 | 92 | 3 | 3 | 3 | 2 | 1 | 1 | 3 | 1 | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 3 | 3 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 3 | 1 | 3 | 2 | 3
136 | 11 | 7 | 15 | 25 | 32 | 40 | 47 | 53 | 64 | 70 | 78 | 84 | 94 | 99 | 1 | 3 | 1 | 2 | 2 | 2 | 1 | 3 | 3 | 2 | 3 | 2 | 2 | 1 | 1 | 3 | 3 | 2 | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 2 | 3 | 1 | 1 | 3 | 1 | 1 | 2 | 3 | 2 | 1 | 1 | 1 | 3 | 2 | 3 | 2 | 3 | 1 | 1 | 2 | 1
137 | 8 | 6 | 13 | 20 | 25 | 34 | 44 | 54 | 60 | 67 | 77 | 85 | 94 | 100 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 1 | 3 | 2 | 3 | 2 | 3 | 3 | 1 | 3 | 3 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 1 | 3 | 1 | 3 | 3 | 3 | 1 | 1 | 3 | 3 | 1 | 3 | 2 | 1 | 1 | 1 | 3
138 | 13 | 8 | 17 | 22 | 30 | 36 | 41 | 48 | 53 | 59 | 65 | 74 | 80 | 84 | 1 | 3 | 2 | 2 | 2 | 3 | 3 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 3 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1
139 | 10 | 6 | 14 | 21 | 27 | 33 | 40 | 48 | 58 | 64 | 70 | 79 | 86 | 92 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 2 | 3 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 2 | 1 | 3 | 1 | 3 | 3 | 2 | 3 | 2 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 3 | 3 | 1 | 2 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 3
140 | 10 | 6 | 13 | 23 | 29 | 37 | 43 | 54 | 61 | 67 | 76 | 83 | 92 | 96 | 1 | 1 | 2 | 2 | 3 | 1 | 1 | 2 | 3 | 3 | 1 | 3 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 2 | 3 | 3 | 3 | 2 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 1 | 2 | 1 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1
141 | 8 | 5 | 12 | 17 | 22 | 30 | 41 | 47 | 55 | 61 | 67 | 76 | 83 | 93 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 2 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 3 | 2 | 3 | 2 | 3 | 3 | 2 | 1 | 2 | 1 | 1 | 3 | 3 | 1 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 3 | 2 | 2 | 2 | 1 | 2 | 3 | 2 | 3 | 2
142 | 8 | 4 | 10 | 18 | 25 | 32 | 39 | 46 | 54 | 60 | 67 | 74 | 81 | 88 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 3 | 1 | 2 | 1 | 3 | 2 | 1 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 3 | 1 | 2 | 2 | 3 | 1 | 2 | 1 | 1 | 3 | 1 | 3 | 1 | 2 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 1
143 | 13 | 10 | 17 | 24 | 32 | 39 | 47 | 53 | 60 | 67 | 75 | 81 | 87 | 94 | 2 | 3 | 3 | 2 | 1 | 2 | 3 | 1 | 2 | 1 | 1 | 3 | 3 | 1 | 1 | 3 | 2 | 1 | 2 | 2 | 2 | 3 | 1 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 2 | 1 | 3 | 1 | 2 | 2 | 1 | 2 | 3 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | 2 | 1 | 3
144 | 10 | 6 | 12 | 20 | 27 | 33 | 39 | 44 | 50 | 55 | 65 | 75 | 81 | 87 | 2 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 2 | 3 | 1 | 2 | 2 | 1 | 2 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 1 | 3 | 3 | 3 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1
145 | 12 | 8 | 14 | 21 | 32 | 40 | 47 | 55 | 61 | 66 | 72 | 77 | 84 | 92 | 3 | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 3 | 1 | 2 | 1 | 3 | 2 | 3 | 3 | 1 | 2 | 3 | 2 | 1 | 1 | 3 | 2 | 2 | 3 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 3 | 3
146 | 10 | 6 | 14 | 23 | 28 | 33 | 41 | 50 | 57 | 64 | 73 | 80 | 87 | 95 | 1 | 2 | 1 | 2 | 1 | 3 | 2 | 2 | 3 | 2 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 3 | 3 | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 1 | 1 | 2 | 3 | 1 | 3 | 3 | 2 | 1 | 3 | 2 | 1 | 1 | 2 | 1 | 3 | 3 | 2 | 1 | 2
147 | 11 | 7 | 15 | 19 | 28 | 37 | 45 | 54 | 65 | 73 | 81 | 87 | 93 | 103 | 1 | 1 | 3 | 2 | 3 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 1 | 3 | 3 | 2 | 3 | 2 | 2 | 1 | 2 | 2 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 1 | 2 | 2 | 2 | 2 | 3 | 1 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 3 | 1 | 3
148 | 10 | 6 | 14 | 22 | 31 | 36 | 42 | 46 | 54 | 60 | 68 | 76 | 83 | 87 | 1 | 1 | 2 | 2 | 3 | 1 | 1 | 3 | 2 | 2 | 3 | 1 | 3 | 1 | 3 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 2 | 1 | 1 | 2 | 3 | 2 | 2 | 1 | 3 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 1
149 | 14 | 9 | 18 | 25 | 31 | 41 | 47 | 53 | 60 | 67 | 72 | 77 | 85 | 95 | 3 | 2 | 3 | 1 | 2 | 3 | 3 | 1 | 1 | 3 | 1 | 2 | 3 | 1 | 1 | 1 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 3 | 2 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 3 | 2 | 1 | 3 | 3 | 1 | 3
150 | 13 | 9 | 16 | 23 | 31 | 38 | 43 | 50 | 57 | 65 | 72 | 78 | 84 | 91 | 2 | 1 | 3 | 3 | 3 | 1 | 2 | 1 | 2 | 1 | 1 | 3 | 2 | 2 | 1 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 3 | 2 | 1 | 1 | 2 | 3 | 2 | 1 | 3 | 1 | 2 | 1 | 2 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 2 | 3 | 1
151 | 10 | 8 | 14 | 22 | 29 | 41 | 48 | 55 | 64 | 75 | 84 | 90 | 99 | 106 | 3 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 3 | 1 | 1 | 2 | 1 | 3 | 3 | 3 | 3 | 3 | 1 | 3 | 2 | 1 | 1 | 1 | 2 | 3 | 1 | 3 | 3 | 2 | 3 | 2 | 3 | 3 | 3 | 2 | 3 | 1 | 1 | 1 | 3 | 1 | 3 | 2 | 1 | 3 | 1 | 3 | 2 | 1
152 | 7 | 4 | 12 | 18 | 25 | 31 | 39 | 44 | 51 | 57 | 64 | 72 | 80 | 87 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 3 | 3 | 1 | 1 | 1 | 1 | 3 | 2 | 2 | 1 | 2 | 1 | 1 | 3 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 3 | 2 | 3 | 1 | 2 | 3 | 2 | 1 | 2 | 1 | 3 | 2 | 1
153 | 12 | 8 | 16 | 22 | 28 | 34 | 39 | 45 | 53 | 61 | 68 | 76 | 85 | 90 | 1 | 2 | 3 | 2 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 3 | 1 | 2 | 2 | 2 | 1 | 1 | 3 | 2 | 3 | 1 | 2 | 2 | 2 | 2 | 3 | 1 | 1 | 2 | 1
154 | 12 | 10 | 15 | 24 | 28 | 39 | 43 | 54 | 61 | 68 | 75 | 84 | 90 | 96 | 3 | 1 | 3 | 3 | 1 | 1 | 2 | 1 | 2 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 2 | 3 | 3 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 3 | 3 | 1 | 1 | 2 | 2 | 1 | 3 | 1 | 3 | 3 | 1 | 2 | 2 | 1 | 1 | 2 | 2 | 1 | 2 | 1
155 | 10 | 8 | 14 | 24 | 29 | 35 | 40 | 45 | 52 | 60 | 66 | 75 | 84 | 95 | 1 | 2 | 2 | 3 | 1 | 1 | 2 | 2 | 1 | 3 | 3 | 3 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 1 | 2 | 2 | 1 | 3 | 1 | 3 | 2 | 2 | 2 | 3 | 2 | 3 | 3 | 2 | 3
156 | 9 | 6 | 14 | 22 | 28 | 34 | 41 | 49 | 57 | 64 | 70 | 79 | 84 | 91 | 1 | 2 | 1 | 2 | 2 | 1 | 3 | 2 | 2 | 3 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 3 | 2 | 2 | 1 | 3 | 3 | 1 | 2 | 2 | 1 | 1 | 3 | 2 | 1 | 1 | 2 | 2 | 1 | 2 | 3 | 3 | 1 | 1 | 2 | 1 | 2 | 3 | 1 | 1
157 | 9 | 5 | 11 | 18 | 26 | 30 | 36 | 41 | 48 | 54 | 60 | 72 | 77 | 82 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 2 | 2 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 1
158 | 10 | 7 | 14 | 21 | 27 | 34 | 43 | 50 | 57 | 61 | 68 | 77 | 83 | 88 | 2 | 1 | 3 | 1 | 2 | 1 | 1 | 3 | 2 | 3 | 1 | 1 | 2 | 1 | 1 | 2 | 3 | 1 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 1 | 2 | 3 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 3 | 2 | 2 | 2 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 1
159 | 10 | 8 | 14 | 21 | 31 | 39 | 45 | 50 | 57 | 65 | 73 | 81 | 91 | 98 | 1 | 3 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 3 | 1 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 2 | 3 | 3 | 1 | 1 | 3 | 1 | 2 | 2 | 3 | 1 | 2 | 2 | 1 | 3 | 3 | 3 | 1 | 2 | 3 | 1
160 | 12 | 6 | 16 | 24 | 29 | 34 | 41 | 49 | 55 | 65 | 73 | 79 | 85 | 91 | 1 | 1 | 3 | 1 | 3 | 3 | 3 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 2 | 2 | 1 | 3 | 3 | 1 | 3 | 3 | 1 | 2 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 2 | 1
161 | 14 | 8 | 16 | 21 | 29 | 35 | 43 | 49 | 55 | 61 | 69 | 76 | 86 | 95 | 1 | 3 | 3 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 3 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 3 | 2 | 2 | 3 | 2 | 3 | 3 | 2 | 3 | 1
162 | 12 | 8 | 14 | 22 | 32 | 36 | 42 | 49 | 53 | 61 | 69 | 79 | 89 | 99 | 2 | 3 | 1 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 1 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 3 | 3 | 3 | 1 | 3 | 3 | 1 | 3 | 3 | 3 | 3 | 2 | 2 | 3
163 | 9 | 6 | 12 | 22 | 28 | 34 | 42 | 48 | 57 | 64 | 75 | 83 | 92 | 98 | 1 | 1 | 1 | 3 | 2 | 1 | 2 | 1 | 1 | 3 | 3 | 3 | 2 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 3 | 1 | 3 | 1 | 1 | 3 | 2 | 3 | 1 | 1 | 1 | 3 | 2 | 3 | 2 | 3 | 3 | 1 | 3 | 2 | 2 | 3 | 2 | 3 | 1 | 1 | 3 | 1 | 1
164 | 8 | 5 | 10 | 16 | 23 | 29 | 36 | 41 | 46 | 52 | 59 | 70 | 76 | 81 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 2 | 3 | 3 | 2 | 3 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 1
165 | 11 | 8 | 14 | 21 | 29 | 35 | 42 | 47 | 58 | 62 | 66 | 72 | 80 | 87 | 2 | 3 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 3 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 1 | 1 | 2 | 1 | 3 | 1
166 | 11 | 8 | 13 | 17 | 23 | 29 | 35 | 44 | 52 | 59 | 65 | 75 | 80 | 86 | 3 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 1 | 3 | 1 | 3 | 2 | 3 | 2 | 1 | 2 | 3 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 3 | 3 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 1
167 | 10 | 8 | 12 | 22 | 30 | 34 | 43 | 50 | 59 | 65 | 71 | 81 | 87 | 95 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 1 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 2 | 1 | 1 | 3 | 2 | 2 | 3 | 3 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 1 | 3 | 1 | 1 | 3 | 3 | 1 | 1
168 | 11 | 8 | 15 | 23 | 29 | 33 | 41 | 47 | 55 | 61 | 67 | 74 | 82 | 92 | 3 | 3 | 1 | 1 | 1 | 2 | 3 | 1 | 3 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 1 | 1 | 1 | 3 | 2 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 2 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 1
169 | 13 | 7 | 17 | 26 | 34 | 42 | 50 | 56 | 62 | 68 | 74 | 82 | 89 | 98 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 1 | 1 | 3 | 2 | 3 | 1 | 1 | 3 | 3 | 2 | 1 | 3 | 2 | 3 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 3 | 1 | 1 | 2 | 3 | 2 | 1 | 3 | 3
170 | 7 | 4 | 12 | 19 | 25 | 30 | 36 | 42 | 52 | 57 | 65 | 70 | 77 | 83 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 1 | 2 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 3 | 3 | 1 | 3 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 2 | 2
171 | 8 | 6 | 10 | 18 | 28 | 36 | 40 | 46 | 52 | 60 | 68 | 75 | 82 | 90 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 3 | 3 | 3 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 2 | 3 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 2 | 3 | 2
172 | 9 | 5 | 11 | 19 | 26 | 33 | 37 | 43 | 50 | 54 | 60 | 68 | 74 | 82 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 3 | 2 | 3 | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 2 | 3 | 1 | 2 | 1 | 2 | 1 | 3 | 3 | 1
173 | 8 | 6 | 12 | 18 | 25 | 32 | 43 | 50 | 57 | 65 | 71 | 81 | 87 | 99 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 3 | 1 | 2 | 1 | 3 | 1 | 3 | 3 | 3 | 2 | 2 | 3 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 3 | 1 | 2 | 1 | 2 | 1 | 3 | 3 | 1 | 3 | 1 | 1 | 3 | 1 | 3 | 3 | 3 | 3
174 | 11 | 8 | 14 | 20 | 30 | 36 | 41 | 47 | 54 | 60 | 69 | 75 | 84 | 91 | 2 | 1 | 2 | 3 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 1 | 3 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 3 | 2 | 2 | 2 | 1 | 1 | 3 | 1 | 1 | 3 | 3 | 2 | 1 | 1 | 2 | 3
175 | 10 | 5 | 15 | 22 | 29 | 35 | 43 | 51 | 59 | 66 | 75 | 83 | 90 | 100 | 2 | 1 | 1 | 1 | 2 | 3 | 2 | 3 | 2 | 3 | 1 | 1 | 2 | 3 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 2 | 2 | 1 | 3 | 3 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 3 | 2 | 2 | 1 | 3 | 3 | 2 | 3 | 1 | 2 | 3 | 2 | 1 | 1 | 2 | 3 | 2 | 3
176 | 14 | 10 | 17 | 26 | 33 | 40 | 45 | 51 | 55 | 61 | 65 | 70 | 76 | 81 | 3 | 3 | 3 | 1 | 1 | 3 | 2 | 1 | 2 | 3 | 3 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 2
177 | 10 | 5 | 14 | 20 | 30 | 37 | 43 | 47 | 53 | 61 | 66 | 71 | 77 | 86 | 1 | 2 | 1 | 1 | 3 | 2 | 2 | 2 | 3 | 1 | 1 | 1 | 3 | 3 | 3 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 3 | 3 | 2 | 1
178 | 8 | 6 | 11 | 18 | 25 | 30 | 37 | 45 | 55 | 60 | 66 | 74 | 83 | 89 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 3 | 1 | 2 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 3 | 3 | 3 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 1 | 3 | 3 | 3 | 2 | 1 | 3 | 2 | 1 | 1 | 2
179 | 10 | 7 | 14 | 21 | 28 | 37 | 44 | 49 | 55 | 62 | 68 | 77 | 83 | 90 | 1 | 2 | 3 | 1 | 1 | 2 | 1 | 3 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 2 | 1 | 2 | 1 | 3 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 1 | 3 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 3
180 | 9 | 7 | 15 | 21 | 25 | 31 | 40 | 44 | 52 | 59 | 63 | 71 | 81 | 86 | 1 | 2 | 3 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 2 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 1 | 2 | 3 | 3 | 2 | 2 | 1 | 1 | 1
181 | 8 | 5 | 12 | 19 | 30 | 38 | 43 | 52 | 59 | 64 | 70 | 80 | 87 | 93 | 2 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 2 | 3 | 3 | 3 | 2 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 3 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 1 | 3 | 2 | 1 | 2 | 2 | 3 | 1 | 1 | 1
182 | 10 | 7 | 15 | 20 | 26 | 33 | 40 | 46 | 53 | 59 | 67 | 73 | 79 | 83 | 1 | 2 | 1 | 3 | 2 | 1 | 2 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 3 | 2 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1
183 | 12 | 6 | 14 | 25 | 35 | 42 | 50 | 58 | 66 | 70 | 77 | 83 | 90 | 97 | 1 | 1 | 1 | 3 | 3 | 3 | 1 | 1 | 3 | 3 | 2 | 3 | 1 | 3 | 3 | 3 | 1 | 1 | 2 | 3 | 2 | 3 | 2 | 1 | 1 | 3 | 3 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 3 | 2 | 1 | 3 | 1
184 | 7 | 5 | 12 | 21 | 29 | 36 | 44 | 53 | 58 | 65 | 71 | 78 | 83 | 90 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 3 | 2 | 3 | 3 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | 2 | 2 | 3 | 1 | 1 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 2
185 | 7 | 5 | 11 | 17 | 27 | 33 | 41 | 48 | 55 | 62 | 69 | 76 | 81 | 90 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 3 | 3 | 1 | 2 | 1 | 2 | 2 | 2 | 3 | 1 | 1 | 2 | 1 | 3 | 3 | 2 | 1 | 1 | 2 | 1 | 1 | 3 | 2 | 1 | 2 | 2 | 2 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 2 | 3
186 | 10 | 7 | 15 | 25 | 31 | 38 | 44 | 50 | 58 | 66 | 74 | 80 | 86 | 93 | 3 | 1 | 1 | 2 | 1 | 2 | 2 | 3 | 3 | 3 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 3 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 3 | 1 | 3 | 1 | 1 | 2 | 3 | 2 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 3 | 2 | 1 | 1
187 | 10 | 7 | 13 | 17 | 22 | 26 | 31 | 38 | 46 | 52 | 59 | 67 | 72 | 78 | 2 | 1 | 3 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 2 | 3 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 2 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2
188 | 10 | 5 | 13 | 20 | 24 | 32 | 39 | 46 | 54 | 60 | 64 | 69 | 75 | 82 | 1 | 2 | 1 | 1 | 2 | 3 | 1 | 2 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 1 | 3 | 1 | 1 | 2 | 2 | 2 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 3 | 2
189 | 10 | 8 | 13 | 19 | 25 | 31 | 39 | 44 | 49 | 57 | 63 | 70 | 76 | 84 | 3 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 2 | 1 | 2 | 3 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 2 | 2
190 | 8 | 5 | 12 | 17 | 23 | 32 | 39 | 46 | 54 | 63 | 71 | 80 | 84 | 90 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 2 | 1 | 3 | 1 | 3 | 1 | 2 | 1 | 1 | 2 | 3 | 3 | 3 | 1 | 1 | 3 | 2 | 2 | 2 | 2 | 1 | 2 | 3 | 3 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1
191 | 11 | 7 | 15 | 27 | 36 | 44 | 52 | 60 | 70 | 77 | 83 | 89 | 95 | 101 | 1 | 2 | 3 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 1 | 3 | 3 | 2 | 1 | 3 | 2 | 2 | 1 | 2 | 3 | 1 | 3 | 2 | 2 | 2 | 3 | 3 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 2 | 1
192 | 10 | 8 | 13 | 22 | 29 | 34 | 44 | 53 | 60 | 67 | 73 | 79 | 86 | 91 | 1 | 3 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 3 | 3 | 3 | 2 | 3 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 2 | 1 | 2 | 1 | 1 | 1
193 | 9 | 6 | 13 | 21 | 28 | 32 | 39 | 47 | 56 | 62 | 71 | 77 | 84 | 91 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 3 | 2 | 2 | 1 | 3 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 2 | 1 | 2 | 3 | 2 | 3 | 3 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 2 | 3 | 2 | 1 | 1 | 2 | 1 | 2 | 3 | 1 | 1 | 3 | 1 | 2
194 | 14 | 9 | 18 | 28 | 40 | 45 | 50 | 54 | 61 | 65 | 73 | 80 | 84 | 89 | 1 | 2 | 3 | 3 | 2 | 3 | 1 | 3 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1
195 | 8 | 6 | 14 | 19 | 27 | 35 | 42 | 52 | 59 | 67 | 78 | 83 | 90 | 96 | 2 | 2 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 2 | 2 | 3 | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 1 | 1 | 3 | 3 | 1 | 3 | 3 | 1 | 2 | 1 | 3 | 1 | 1 | 3 | 3 | 2 | 3 | 3 | 1 | 2 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 3 | 1 | 1
196 | 10 | 6 | 15 | 23 | 27 | 34 | 40 | 46 | 52 | 58 | 66 | 70 | 79 | 87 | 2 | 1 | 2 | 1 | 1 | 3 | 2 | 3 | 2 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 1 | 1 | 3 | 3 | 1
197 | 10 | 8 | 15 | 21 | 28 | 34 | 41 | 46 | 52 | 61 | 70 | 77 | 83 | 94 | 2 | 2 | 1 | 3 | 1 | 1 | 3 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 3 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 3 | 2 | 2 | 1 | 1 | 3 | 2 | 2 | 1 | 2 | 1 | 3 | 2 | 3 | 3
198 | 8 | 5 | 10 | 17 | 23 | 30 | 36 | 44 | 49 | 53 | 61 | 65 | 77 | 83 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 3 | 1 | 1 | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 1 | 2 | 1 | 2
199 | 9 | 6 | 12 | 19 | 24 | 29 | 35 | 43 | 49 | 53 | 59 | 66 | 75 | 81 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 3 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 1 | 3 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 3 | 3 | 1 | 2 | 2 | 2 | 1 | 1
200 | 14 | 8 | 18 | 25 | 31 | 35 | 45 | 51 | 58 | 66 | 71 | 80 | 90 | 94 | 3 | 2 | 2 | 1 | 3 | 3 | 1 | 3 | 1 | 1 | 2 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 2 | 2 | 2 | 1 | 2 | 1 | 2 | 3 | 1 | 1 | 2 | 3 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 3 | 3 | 2 | 3 | 2 | 1 | 1 | 1 | 1
201 | 13 | 8 | 17 | 25 | 31 | 37 | 43 | 51 | 57 | 66 | 72 | 81 | 88 | 96 | 2 | 1 | 2 | 3 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 3 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 3 | 2 | 1 | 2 | 1 | 2 | 3 | 2 | 1 | 3 | 1 | 2 | 2 | 2 | 3 | 1 | 1 | 3
202 | 9 | 5 | 12 | 16 | 20 | 26 | 36 | 44 | 53 | 57 | 66 | 74 | 82 | 88 | 2 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 3 | 1 | 3 | 3 | 3 | 1 | 2 | 2 | 1 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 2 | 1 | 2 | 2 | 3 | 3 | 2 | 1 | 2 | 2 | 2 | 1 | 1
203 | 7 | 5 | 11 | 18 | 25 | 32 | 42 | 49 | 57 | 61 | 65 | 72 | 78 | 83 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 3 | 2 | 2 | 1 | 2 | 1 | 1 | 3 | 2 | 3 | 2 | 2 | 3 | 1 | 1 | 3 | 2 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 1
204 | 11 | 7 | 15 | 22 | 29 | 34 | 39 | 49 | 57 | 63 | 70 | 76 | 86 | 93 | 1 | 3 | 1 | 2 | 1 | 3 | 2 | 2 | 3 | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 3 | 2 | 2 | 3 | 2 | 2 | 1 | 3 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 2 | 3 | 2 | 3 | 1 | 3 | 1 | 2
205 | 12 | 9 | 14 | 18 | 24 | 32 | 38 | 46 | 52 | 58 | 68 | 76 | 83 | 90 | 2 | 1 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 3 | 2 | 2 | 1 | 1 | 2 | 1 | 3 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 3 | 3 | 2 | 3 | 2 | 3 | 1 | 1 | 3 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 3
206 | 14 | 10 | 19 | 24 | 33 | 43 | 50 | 58 | 64 | 74 | 80 | 86 | 93 | 99 | 3 | 1 | 3 | 3 | 1 | 3 | 2 | 3 | 1 | 1 | 1 | 2 | 1 | 2 | 3 | 3 | 1 | 3 | 3 | 3 | 1 | 2 | 2 | 2 | 3 | 1 | 3 | 1 | 1 | 2 | 1 | 2 | 3 | 2 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 2 | 1 | 3 | 1 | 1 | 1
207 | 11 | 7 | 17 | 24 | 35 | 43 | 54 | 58 | 64 | 71 | 80 | 89 | 97 | 104 | 1 | 2 | 1 | 3 | 1 | 3 | 3 | 3 | 2 | 2 | 1 | 2 | 2 | 3 | 3 | 3 | 1 | 1 | 3 | 3 | 2 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 2 | 3 | 3 | 1 | 3 | 3 | 2 | 2 | 1 | 2 | 3 | 2 | 1 | 1 | 3
208 | 10 | 5 | 14 | 22 | 29 | 38 | 44 | 52 | 59 | 67 | 74 | 83 | 91 | 98 | 1 | 2 | 1 | 1 | 2 | 3 | 3 | 1 | 1 | 3 | 1 | 3 | 2 | 2 | 1 | 2 | 3 | 2 | 1 | 3 | 2 | 1 | 2 | 1 | 1 | 3 | 3 | 1 | 2 | 3 | 1 | 1 | 2 | 1 | 3 | 2 | 1 | 2 | 1 | 3 | 2 | 2 | 3 | 2 | 3 | 1 | 1 | 3 | 3 | 1 | 2 | 1
209 | 11 | 7 | 14 | 18 | 29 | 33 | 39 | 45 | 51 | 58 | 64 | 70 | 76 | 81 | 1 | 2 | 3 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 1 | 3 | 1 | 2 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 2
210 | 11 | 7 | 13 | 19 | 26 | 32 | 41 | 49 | 54 | 62 | 72 | 79 | 85 | 95 | 1 | 2 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 3 | 3 | 1 | 2 | 3 | 2 | 1 | 1 | 1 | 2 | 3 | 1 | 2 | 2 | 3 | 2 | 2 | 3 | 1 | 2 | 3 | 1 | 1 | 3 | 1 | 1 | 3 | 3 | 1 | 3
211 | 11 | 7 | 17 | 27 | 37 | 46 | 53 | 60 | 67 | 73 | 82 | 87 | 96 | 104 | 1 | 2 | 3 | 1 | 1 | 3 | 3 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 2 | 1 | 3 | 3 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 3 | 2 | 3 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 1 | 2 | 2 | 3
212 | 10 | 7 | 12 | 18 | 23 | 30 | 37 | 43 | 49 | 56 | 63 | 70 | 74 | 83 | 2 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 2 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 3 | 1 | 1 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 2 | 1
213 | 13 | 8 | 15 | 21 | 30 | 38 | 44 | 49 | 58 | 66 | 71 | 77 | 87 | 92 | 2 | 2 | 1 | 3 | 2 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 3 | 2 | 1 | 3 | 3 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 3 | 3 | 1 | 3 | 1 | 2 | 1 | 1
214 | 13 | 8 | 17 | 24 | 30 | 35 | 39 | 47 | 53 | 61 | 69 | 75 | 83 | 89 | 3 | 2 | 1 | 2 | 3 | 2 | 1 | 3 | 1 | 3 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 2 | 1 | 2 | 3 | 1 | 1 | 3 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 3 | 2 | 2 | 2 | 2 | 1 | 1
215 | 9 | 7 | 13 | 20 | 28 | 34 | 43 | 49 | 56 | 62 | 68 | 75 | 79 | 84 | 1 | 3 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 2 | 1 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1
216 | 11 | 7 | 15 | 19 | 28 | 32 | 40 | 47 | 52 | 59 | 67 | 74 | 79 | 86 | 1 | 1 | 2 | 3 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 3 | 1 | 3 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 3 | 2 | 2 | 2 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 2 | 1
217 | 11 | 8 | 15 | 22 | 31 | 37 | 46 | 57 | 63 | 69 | 75 | 81 | 89 | 95 | 1 | 2 | 3 | 2 | 2 | 1 | 2 | 2 | 3 | 2 | 1 | 1 | 2 | 2 | 3 | 2 | 2 | 1 | 1 | 2 | 3 | 1 | 2 | 3 | 3 | 2 | 3 | 3 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 3 | 3 | 1 | 1 | 3 | 1 | 1 | 1
218 | 9 | 7 | 12 | 21 | 29 | 37 | 45 | 51 | 58 | 66 | 73 | 82 | 90 | 96 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 1 | 2 | 3 | 1 | 2 | 2 | 2 | 1 | 2 | 3 | 1 | 1 | 3 | 3 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 1 | 2 | 2 | 3 | 1 | 3 | 1 | 2 | 1 | 3 | 1 | 2 | 3 | 1 | 3 | 3 | 1 | 1 | 1 | 3 | 1
219 | 8 | 6 | 13 | 20 | 27 | 34 | 41 | 48 | 56 | 61 | 68 | 78 | 85 | 93 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 3 | 2 | 1 | 3 | 1 | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 3 | 1 | 2 | 3 | 1 | 1 | 2 | 2 | 1 | 3 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 1 | 3 | 3 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 3 | 3 | 1
220 | 12 | 8 | 14 | 25 | 32 | 37 | 45 | 52 | 58 | 62 | 68 | 75 | 83 | 93 | 2 | 1 | 3 | 2 | 3 | 1 | 1 | 1 | 3 | 3 | 2 | 3 | 1 | 1 | 2 | 3 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 3 | 3 | 1 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 3 | 3 | 1 | 3 | 3 | 3 | 1
221 | 7 | 5 | 12 | 19 | 29 | 37 | 43 | 50 | 57 | 64 | 72 | 77 | 84 | 91 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 2 | 1 | 2 | 3 | 1 | 3 | 2 | 3 | 2 | 2 | 3 | 1 | 2 | 1 | 2 | 2 | 1 | 2 | 3 | 1 | 1 | 3 | 2 | 1 | 1 | 2 | 1 | 3 | 1 | 3 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 2 | 1 | 3
222 | 11 | 7 | 13 | 17 | 25 | 30 | 40 | 48 | 54 | 60 | 67 | 72 | 76 | 83 | 3 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 3 | 1 | 3 | 3 | 1 | 2 | 2 | 3 | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3
223 | 13 | 9 | 16 | 22 | 30 | 37 | 44 | 49 | 56 | 62 | 69 | 74 | 78 | 88 | 2 | 1 | 3 | 3 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 3 | 3 | 2 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 3
224 | 14 | 11 | 18 | 26 | 31 | 37 | 45 | 52 | 59 | 65 | 69 | 76 | 84 | 91 | 3 | 3 | 3 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 3 | 1 | 1 | 3 | 2 | 2 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 3 | 1 | 3 | 2 | 3 | 1 | 1
225 | 16 | 10 | 22 | 30 | 37 | 44 | 52 | 58 | 65 | 74 | 83 | 89 | 97 | 104 | 3 | 3 | 1 | 3 | 3 | 3 | 3 | 3 | 1 | 2 | 2 | 3 | 1 | 1 | 2 | 3 | 2 | 2 | 1 | 2 | 1 | 2 | 3 | 2 | 1 | 1 | 3 | 1 | 1 | 2 | 2 | 2 | 3 | 1 | 2 | 3 | 1 | 3 | 3 | 2 | 2 | 2 | 1 | 1 | 2 | 1 | 2 | 3 | 1 | 2 | 2 | 2
226 | 11 | 6 | 14 | 19 | 26 | 34 | 42 | 50 | 55 | 61 | 68 | 74 | 80 | 88 | 1 | 1 | 2 | 2 | 3 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 2 | 3 | 2 | 1 | 3 | 3 | 1 | 1 | 1 | 3 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 3 | 2 | 1 | 2 | 1 | 3 | 2 | 2 | 1
227 | 11 | 9 | 17 | 27 | 34 | 41 | 49 | 55 | 62 | 66 | 71 | 77 | 85 | 91 | 3 | 3 | 1 | 2 | 1 | 1 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 3 | 2 | 1 | 3 | 2 | 1 | 2 | 2 | 1 | 3 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 3 | 1 | 1 | 3 | 1 | 1 | 3 | 1
228 | 9 | 7 | 14 | 21 | 30 | 40 | 48 | 53 | 61 | 70 | 78 | 86 | 94 | 102 | 2 | 1 | 3 | 1 | 1 | 1 | 3 | 2 | 2 | 3 | 1 | 1 | 3 | 2 | 1 | 3 | 2 | 3 | 2 | 3 | 2 | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 3 | 1 | 3 | 2 | 2 | 2 | 3 | 1 | 3 | 2 | 2 | 1 | 1 | 3 | 3 | 1 | 1 | 3 | 1 | 3
229 | 13 | 8 | 17 | 25 | 33 | 39 | 46 | 52 | 59 | 65 | 72 | 77 | 84 | 90 | 1 | 2 | 2 | 3 | 2 | 3 | 3 | 1 | 3 | 2 | 1 | 2 | 2 | 1 | 2 | 3 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 2 | 2 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 3 | 1 | 1 | 1
230 | 9 | 5 | 13 | 19 | 29 | 37 | 44 | 50 | 56 | 63 | 71 | 78 | 83 | 89 | 2 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 3 | 3 | 1 | 3 | 2 | 3 | 2 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 1 | 1 | 1 | 3 | 2 | 1 | 3 | 1 | 3 | 1 | 2 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 1
231 | 11 | 7 | 13 | 21 | 28 | 36 | 45 | 54 | 59 | 67 | 75 | 81 | 86 | 92 | 2 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 3 | 2 | 2 | 2 | 1 | 1 | 2 | 3 | 2 | 1 | 2 | 3 | 3 | 3 | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 1 | 2 | 3 | 2 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 1
232 | 6 | 4 | 12 | 18 | 27 | 36 | 42 | 52 | 61 | 68 | 74 | 81 | 87 | 93 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 3 | 3 | 1 | 3 | 2 | 2 | 3 | 2 | 2 | 1 | 2 | 2 | 1 | 1 | 3 | 3 | 3 | 1 | 2 | 3 | 3 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 3 | 1
233 | 13 | 10 | 15 | 23 | 29 | 35 | 42 | 49 | 59 | 69 | 75 | 83 | 88 | 94 | 2 | 2 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 2 | 1 | 3 | 3 | 3 | 1 | 3 | 2 | 2 | 3 | 3 | 1 | 3 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 1
234 | 10 | 7 | 16 | 27 | 32 | 41 | 48 | 56 | 65 | 69 | 77 | 84 | 90 | 96 | 3 | 2 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 3 | 3 | 3 | 1 | 1 | 2 | 1 | 3 | 3 | 2 | 1 | 1 | 3 | 1 | 2 | 3 | 1 | 2 | 2 | 1 | 3 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 2 | 3 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 1
235 | 12 | 10 | 14 | 20 | 29 | 33 | 44 | 55 | 61 | 69 | 77 | 84 | 89 | 95 | 2 | 3 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 3 | 3 | 2 | 3 | 3 | 3 | 2 | 3 | 1 | 1 | 1 | 3 | 2 | 1 | 2 | 3 | 2 | 1 | 2 | 3 | 3 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 1
236 | 9 | 5 | 15 | 19 | 26 | 35 | 40 | 48 | 53 | 57 | 64 | 70 | 79 | 88 | 1 | 1 | 2 | 1 | 1 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 3 | 2 | 3 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 3 | 3 | 3 | 1 | 2 | 3 | 2 | 2 | 2
237 | 11 | 9 | 15 | 23 | 29 | 37 | 43 | 49 | 54 | 60 | 67 | 73 | 84 | 93 | 2 | 2 | 2 | 3 | 1 | 1 | 2 | 2 | 3 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 2 | 3 | 2 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 3 | 1 | 3 | 1 | 1 | 3 | 3 | 2 | 3 | 1 | 3 | 2 | 3
238 | 10 | 7 | 14 | 25 | 31 | 37 | 45 | 51 | 55 | 60 | 66 | 73 | 83 | 90 | 1 | 3 | 1 | 2 | 1 | 2 | 3 | 1 | 3 | 3 | 2 | 3 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 3 | 2 | 3 | 3 | 1 | 3 | 3 | 2 | 1 | 1
239 | 11 | 8 | 13 | 21 | 29 | 35 | 43 | 50 | 56 | 63 | 69 | 75 | 82 | 87 | 3 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 2 | 1 | 2 | 3 | 3 | 2 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 1 | 3 | 1 | 2 | 1 | 1 | 2 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 1 | 2 | 1 | 3 | 1 | 2 | 1 | 1 | 1
240 | 10 | 8 | 13 | 19 | 24 | 33 | 39 | 43 | 47 | 54 | 59 | 68 | 76 | 82 | 1 | 3 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 3 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 2 | 1 | 1 | 1 | 3 | 3 | 2 | 3 | 1 | 1 | 3 | 1 | 1 | 2 | 2
241 | 12 | 7 | 14 | 20 | 27 | 33 | 43 | 53 | 61 | 70 | 76 | 84 | 91 | 99 | 1 | 1 | 2 | 3 | 2 | 3 | 1 | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 3 | 1 | 1 | 2 | 1 | 3 | 3 | 3 | 1 | 1 | 1 | 3 | 2 | 1 | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 1
242 | 15 | 9 | 19 | 27 | 37 | 43 | 49 | 57 | 62 | 70 | 74 | 81 | 88 | 97 | 1 | 3 | 2 | 3 | 3 | 3 | 1 | 3 | 1 | 3 | 2 | 2 | 2 | 2 | 3 | 3 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 2 | 3 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 3 | 1 | 1 | 2 | 3 | 1 | 3
243 | 15 | 9 | 17 | 26 | 34 | 42 | 48 | 56 | 64 | 69 | 79 | 85 | 94 | 100 | 3 | 1 | 3 | 2 | 3 | 3 | 1 | 1 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 1 | 1 | 3 | 1 | 3 | 2 | 1 | 1 | 2 | 2 | 3 | 2 | 1 | 1 | 3 | 2 | 2 | 1 | 1 | 2 | 1 | 3 | 2 | 2 | 3 | 1 | 1 | 3 | 1 | 3 | 3 | 1 | 2 | 2 | 1 | 2 | 1
244 | 7 | 5 | 10 | 16 | 24 | 30 | 39 | 48 | 54 | 62 | 69 | 75 | 80 | 86 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 2 | 3 | 2 | 1 | 3 | 1 | 1 | 1 | 3 | 2 | 1 | 3 | 3 | 2 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 2
245 | 7 | 5 | 11 | 18 | 25 | 32 | 39 | 43 | 49 | 57 | 66 | 71 | 81 | 87 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 3 | 1 | 2 | 3 | 1 | 1 | 3 | 2 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 1 | 3 | 2 | 3 | 1 | 1 | 2 | 1 | 3 | 1 | 3 | 3 | 2 | 2 | 1 | 1
246 | 12 | 8 | 14 | 20 | 27 | 31 | 39 | 45 | 51 | 59 | 66 | 75 | 80 | 90 | 3 | 2 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 3 | 2 | 2 | 1 | 3 | 1 | 2 | 1 | 2 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 3 | 2 | 2 | 3
247 | 10 | 8 | 12 | 20 | 26 | 32 | 38 | 43 | 47 | 53 | 61 | 69 | 77 | 86 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 3 | 1 | 2 | 2 | 1 | 2 | 3 | 2 | 1 | 2 | 3 | 3 | 1 | 2 | 3
248 | 12 | 8 | 14 | 19 | 28 | 35 | 41 | 49 | 55 | 63 | 69 | 76 | 84 | 89 | 3 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 3 | 3 | 1 | 3 | 2 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 3 | 2 | 1 | 3 | 2 | 1 | 2 | 2 | 1 | 1 | 1
249 | 13 | 9 | 16 | 22 | 27 | 33 | 39 | 48 | 53 | 59 | 65 | 69 | 77 | 83 | 2 | 3 | 1 | 3 | 2 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 2 | 3 | 3 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 2 | 2 | 1
250 | 12 | 8 | 15 | 23 | 32 | 40 | 48 | 59 | 65 | 72 | 79 | 88 | 96 | 101 | 3 | 1 | 1 | 3 | 2 | 2 | 1 | 2 | 2 | 2 | 1 | 3 | 2 | 1 | 3 | 3 | 2 | 2 | 3 | 1 | 3 | 1 | 1 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 3 | 3 | 2 | 1 | 1 | 3 | 3 | 2 | 1 | 2 | 2 | 1 | 3 | 2 | 1 | 1 | 1
251 | 14 | 9 | 18 | 25 | 29 | 36 | 45 | 53 | 62 | 70 | 77 | 86 | 93 | 103 | 2 | 3 | 1 | 3 | 3 | 2 | 1 | 3 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 3 | 3 | 1 | 2 | 2 | 1 | 2 | 3 | 1 | 3 | 2 | 3 | 3 | 1 | 1 | 3 | 3 | 1 | 1 | 2 | 1 | 2 | 3 | 3 | 3 | 1 | 1 | 2 | 3 | 1 | 3 | 3
252 | 10 | 7 | 12 | 16 | 20 | 27 | 35 | 40 | 48 | 55 | 61 | 68 | 78 | 88 | 1 | 3 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 1 | 2 | 3 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 3 | 1 | 1 | 3 | 3 | 3 | 1 | 3 | 3 | 3
253 | 15 | 11 | 19 | 25 | 31 | 40 | 46 | 53 | 59 | 67 | 71 | 79 | 87 | 92 | 3 | 3 | 2 | 3 | 2 | 2 | 1 | 3 | 1 | 1 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 1 | 2 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 2 | 2 | 3 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 3 | 3 | 1 | 2 | 1 | 1 | 1
254 | 11 | 8 | 16 | 22 | 27 | 35 | 44 | 51 | 57 | 64 | 73 | 82 | 89 | 96 | 3 | 3 | 1 | 1 | 1 | 2 | 3 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 3 | 1 | 2 | 3 | 3 | 1 | 3 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 3 | 1 | 3 | 2 | 1 | 3 | 3 | 1 | 2 | 3 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 3
255 | 12 | 8 | 16 | 26 | 32 | 36 | 42 | 53 | 59 | 63 | 69 | 76 | 82 | 87 | 3 | 1 | 1 | 3 | 3 | 1 | 3 | 1 | 2 | 3 | 3 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 2 | 2 | 1 | 1 | 2 | 1 | 2 | 1 | 1
256 | 6 | 4 | 11 | 15 | 25 | 31 | 38 | 45 | 52 | 58 | 66 | 72 | 78 | 85 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 1 | 1 | 3 | 3 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 3 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 3 | 1 | 2 | 1
257 | 13 | 9 | 15 | 24 | 30 | 37 | 41 | 49 | 57 | 63 | 69 | 74 | 82 | 90 | 1 | 3 | 2 | 3 | 3 | 1 | 1 | 1 | 3 | 1 | 2 | 3 | 1 | 3 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 3 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 3 | 1 | 3 | 1 | 1 | 3
258 | 12 | 9 | 17 | 24 | 29 | 37 | 43 | 48 | 55 | 61 | 66 | 73 | 81 | 88 | 3 | 1 | 2 | 3 | 2 | 1 | 3 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 2 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 1 | 3 | 1 | 2
259 | 11 | 9 | 13 | 18 | 28 | 34 | 42 | 47 | 55 | 64 | 72 | 77 | 86 | 92 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 3 | 3 | 1 | 1 | 1 | 3 | 2 | 2 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 3 | 2 | 2 | 2 | 3 | 2 | 1 | 2 | 3 | 1 | 1 | 1 | 2 | 2 | 1 | 3 | 3 | 1 | 3 | 1 | 1
260 | 12 | 8 | 16 | 23 | 31 | 41 | 48 | 56 | 65 | 70 | 75 | 83 | 92 | 99 | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 1 | 2 | 1 | 3 | 2 | 3 | 2 | 1 | 3 | 3 | 1 | 3 | 1 | 2 | 2 | 2 | 3 | 1 | 3 | 1 | 2 | 3 | 3 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 3 | 3 | 1 | 2 | 1 | 3 | 2 | 1
261 | 12 | 8 | 14 | 21 | 33 | 41 | 47 | 52 | 58 | 64 | 68 | 77 | 86 | 94 | 1 | 3 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 1 | 2 | 3 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 2 | 3 | 3 | 1 | 2 | 2 | 3 | 1 | 2
262 | 10 | 6 | 15 | 25 | 31 | 37 | 43 | 49 | 57 | 65 | 72 | 79 | 89 | 96 | 2 | 1 | 1 | 2 | 2 | 2 | 3 | 2 | 3 | 1 | 3 | 3 | 1 | 2 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 3 | 3 | 2 | 1 | 1 | 3 | 2 | 3 | 1 | 1 | 1 | 3 | 3 | 3 | 1 | 1 | 3 | 2
263 | 10 | 7 | 16 | 24 | 30 | 35 | 42 | 49 | 55 | 62 | 66 | 72 | 80 | 86 | 1 | 3 | 1 | 2 | 2 | 1 | 3 | 3 | 3 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 2 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 3 | 2 | 1 | 1 | 1 | 3
264 | 10 | 5 | 14 | 22 | 30 | 36 | 44 | 55 | 60 | 70 | 76 | 83 | 89 | 101 | 1 | 1 | 1 | 2 | 3 | 2 | 1 | 3 | 1 | 1 | 3 | 3 | 2 | 2 | 3 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 3 | 1 | 3 | 3 | 2 | 3 | 2 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 3 | 3 | 3 | 3
265 | 13 | 9 | 15 | 22 | 31 | 39 | 47 | 56 | 62 | 70 | 78 | 89 | 98 | 103 | 3 | 1 | 2 | 3 | 2 | 2 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 3 | 2 | 3 | 1 | 1 | 3 | 3 | 3 | 1 | 1 | 3 | 3 | 3 | 1 | 2 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 1 | 2 | 1 | 2 | 1 | 1
266 | 10 | 8 | 15 | 25 | 30 | 36 | 43 | 51 | 60 | 69 | 77 | 86 | 90 | 96 | 2 | 1 | 3 | 2 | 1 | 1 | 3 | 2 | 3 | 2 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 3 | 1 | 3 | 2 | 1 | 2 | 1 | 3 | 2 | 3 | 3 | 1 | 2 | 3 | 1 | 3 | 2 | 2 | 3 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2
267 | 12 | 10 | 15 | 24 | 32 | 39 | 51 | 56 | 66 | 74 | 81 | 90 | 99 | 106 | 3 | 3 | 1 | 3 | 1 | 1 | 1 | 2 | 3 | 2 | 3 | 1 | 3 | 1 | 3 | 1 | 1 | 2 | 3 | 1 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 3 | 3 | 2 | 2 | 3 | 2 | 1 | 2 | 2 | 3 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 1 | 3 | 2 | 1 | 3 | 2 | 1
268 | 11 | 6 | 17 | 27 | 33 | 43 | 49 | 55 | 62 | 68 | 74 | 79 | 86 | 93 | 2 | 1 | 1 | 2 | 3 | 2 | 3 | 3 | 3 | 1 | 3 | 3 | 2 | 2 | 1 | 1 | 3 | 3 | 2 | 2 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 3 | 2 | 1 | 1
269 | 13 | 9 | 17 | 21 | 28 | 37 | 45 | 53 | 59 | 65 | 74 | 80 | 85 | 92 | 3 | 2 | 3 | 1 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 3 | 2 | 3 | 1 | 1 | 2 | 3 | 2 | 1 | 3 | 2 | 2 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 2 | 3 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 2
270 | 10 | 6 | 12 | 22 | 29 | 37 | 42 | 48 | 54 | 63 | 71 | 76 | 84 | 92 | 1 | 3 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 3 | 3 | 1 | 3 | 1 | 2 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 2 | 1 | 2 | 2 | 1 | 3 | 2 | 1 | 3 | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 2 | 2 | 3 | 2 | 1 | 2 | 1 | 3 | 2
271 | 11 | 7 | 15 | 22 | 32 | 38 | 47 | 54 | 63 | 71 | 79 | 85 | 93 | 97 | 3 | 1 | 1 | 2 | 2 | 2 | 1 | 3 | 1 | 1 | 3 | 2 | 2 | 3 | 2 | 3 | 1 | 1 | 1 | 3 | 1 | 3 | 3 | 2 | 2 | 1 | 1 | 3 | 3 | 2 | 1 | 3 | 2 | 2 | 3 | 1 | 3 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 1
272 | 9 | 6 | 15 | 21 | 29 | 35 | 41 | 47 | 52 | 58 | 63 | 67 | 72 | 78 | 2 | 2 | 1 | 1 | 2 | 1 | 3 | 3 | 1 | 1 | 1 | 3 | 3 | 1 | 3 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 2
273 | 10 | 6 | 14 | 23 | 32 | 38 | 45 | 52 | 58 | 64 | 74 | 80 | 86 | 91 | 1 | 1 | 2 | 2 | 3 | 1 | 1 | 3 | 1 | 3 | 3 | 2 | 3 | 2 | 1 | 3 | 1 | 2 | 1 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 3 | 3 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 2
274 | 11 | 8 | 13 | 20 | 25 | 32 | 39 | 49 | 56 | 63 | 71 | 76 | 82 | 94 | 2 | 3 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 1 | 2 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 1 | 3 | 1 | 2 | 2 | 1 | 1 | 3 | 2 | 3 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 3
275 | 9 | 7 | 14 | 21 | 28 | 36 | 41 | 51 | 59 | 66 | 73 | 81 | 87 | 91 | 1 | 1 | 3 | 2 | 1 | 1 | 2 | 3 | 2 | 1 | 3 | 1 | 2 | 1 | 2 | 2 | 1 | 2 | 2 | 3 | 1 | 1 | 2 | 1 | 3 | 1 | 3 | 3 | 3 | 1 | 1 | 3 | 1 | 2 | 2 | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1
276 | 11 | 8 | 15 | 23 | 29 | 35 | 40 | 47 | 54 | 63 | 74 | 82 | 90 | 96 | 2 | 3 | 1 | 2 | 2 | 1 | 1 | 3 | 2 | 1 | 2 | 3 | 1 | 2 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 2 | 1 | 3 | 1 | 2 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 1 | 3 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 3 | 1
277 | 8 | 4 | 11 | 18 | 25 | 31 | 41 | 49 | 57 | 64 | 73 | 77 | 83 | 91 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 3 | 2 | 1 | 3 | 1 | 2 | 2 | 2 | 1 | 1 | 3 | 3 | 2 | 2 | 2 | 1 | 3 | 2 | 3 | 1 | 1 | 3 | 1 | 1 | 2 | 3 | 2 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 3 | 3 | 1
278 | 8 | 6 | 13 | 21 | 29 | 35 | 40 | 46 | 53 | 61 | 65 | 71 | 77 | 84 | 2 | 1 | 1 | 2 | 1 | 1 | 3 | 2 | 1 | 2 | 2 | 3 | 3 | 3 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 3
279 | 9 | 7 | 13 | 21 | 29 | 37 | 44 | 53 | 60 | 66 | 71 | 79 | 88 | 92 | 3 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 3 | 1 | 3 | 1 | 1 | 2 | 3 | 2 | 3 | 1 | 1 | 3 | 2 | 1 | 3 | 1 | 2 | 1 | 3 | 3 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 1 | 3 | 2 | 2 | 1 | 3 | 1 | 2 | 3 | 1 | 1 | 1 | 1
280 | 14 | 10 | 19 | 24 | 33 | 39 | 46 | 55 | 61 | 70 | 80 | 88 | 93 | 101 | 3 | 2 | 2 | 3 | 3 | 1 | 3 | 2 | 1 | 1 | 2 | 1 | 2 | 2 | 2 | 3 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 1 | 3 | 3 | 2 | 1 | 3 | 1 | 1 | 1 | 3 | 2 | 1 | 3 | 3 | 2 | 2 | 3 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 3 | 2
281 | 7 | 5 | 9 | 13 | 21 | 27 | 36 | 44 | 50 | 57 | 62 | 74 | 80 | 86 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 3 | 2 | 3 | 3 | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 2 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 3 | 1 | 1 | 1
282 | 6 | 4 | 8 | 14 | 24 | 32 | 40 | 48 | 57 | 65 | 73 | 81 | 86 | 91 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 3 | 3 | 2 | 2 | 1 | 1 | 3 | 3 | 3 | 1 | 1 | 3 | 1 | 3 | 2 | 2 | 3 | 3 | 1 | 2 | 1 | 3 | 3 | 1 | 2 | 1 | 3 | 2 | 1 | 3 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1
283 | 10 | 8 | 14 | 22 | 29 | 36 | 40 | 49 | 55 | 63 | 68 | 76 | 80 | 88 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 2 | 3 | 2 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 1 | 3 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 2
284 | 9 | 5 | 11 | 17 | 25 | 31 | 37 | 45 | 50 | 56 | 62 | 71 | 77 | 85 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 2 | 2 | 3 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 1 | 3 | 2 | 3 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 2 | 2
285 | 8 | 5 | 12 | 19 | 28 | 35 | 43 | 55 | 61 | 71 | 76 | 82 | 87 | 93 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 2 | 1 | 3 | 3 | 1 | 3 | 2 | 1 | 1 | 3 | 2 | 3 | 3 | 1 | 1 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 3 | 2 | 2 | 3 | 3 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 1
286 | 8 | 6 | 11 | 18 | 27 | 31 | 38 | 49 | 56 | 64 | 68 | 74 | 84 | 89 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 3 | 1 | 2 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 2 | 3 | 1 | 1 | 2 | 2 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 3 | 3 | 1 | 1 | 1 | 2 | 1
287 | 9 | 5 | 13 | 19 | 31 | 36 | 44 | 51 | 58 | 64 | 69 | 76 | 86 | 92 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 3 | 1 | 3 | 3 | 3 | 3 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 3 | 1 | 2 | 3 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 3 | 2 | 1 | 1 | 3 | 1 | 3 | 3 | 2 | 2 | 1 | 1
288 | 7 | 5 | 9 | 14 | 21 | 28 | 33 | 42 | 49 | 55 | 62 | 69 | 76 | 82 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 2 | 1 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 3 | 1 | 1 | 2 | 2 | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 3 | 1 | 1 | 1
289 | 6 | 4 | 10 | 20 | 25 | 30 | 37 | 43 | 50 | 57 | 63 | 71 | 76 | 82 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 2 | 2 | 1 | 1 | 2 | 3 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 1 | 2 | 2 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 3
290 | 9 | 5 | 13 | 20 | 25 | 33 | 42 | 50 | 54 | 62 | 70 | 76 | 84 | 93 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 3 | 3 | 1 | 2 | 3 | 2 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 3 | 2 | 1 | 1 | 3 | 1 | 2 | 2 | 1 | 3 | 2 | 3 | 2 | 2
291 | 8 | 6 | 12 | 21 | 29 | 36 | 40 | 48 | 53 | 57 | 65 | 73 | 82 | 90 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 3 | 2 | 3 | 1 | 2 | 3 | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 2 | 3 | 2 | 1 | 3 | 2 | 1 | 3 | 3 | 1 | 1 | 3
292 | 12 | 10 | 14 | 22 | 32 | 37 | 41 | 46 | 52 | 56 | 62 | 68 | 73 | 81 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 2 | 3 | 3 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 2 | 1 | 2 | 3
293 | 14 | 10 | 17 | 23 | 29 | 34 | 41 | 49 | 55 | 62 | 68 | 75 | 81 | 89 | 3 | 3 | 1 | 3 | 1 | 3 | 1 | 2 | 2 | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 2 | 3 | 1 | 1 | 3 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 3 | 2 | 1 | 2 | 1 | 3 | 1 | 3 | 1
294 | 11 | 8 | 14 | 24 | 32 | 37 | 45 | 50 | 56 | 66 | 75 | 84 | 94 | 100 | 2 | 3 | 1 | 2 | 1 | 2 | 2 | 1 | 3 | 1 | 3 | 3 | 1 | 2 | 2 | 3 | 1 | 1 | 1 | 2 | 1 | 3 | 3 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 3 | 3 | 1 | 2 | 3 | 3 | 2 | 3 | 3 | 1 | 2 | 3 | 3 | 2 | 1 | 2 | 2 | 1
295 | 14 | 8 | 16 | 24 | 31 | 39 | 47 | 55 | 62 | 69 | 75 | 81 | 88 | 95 | 3 | 2 | 2 | 1 | 3 | 3 | 1 | 1 | 1 | 3 | 1 | 3 | 3 | 1 | 1 | 2 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 2 | 1 | 2 | 3 | 1 | 3 | 1 | 2 | 1 | 2 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 2 | 1 | 3 | 1 | 1 | 2
296 | 13 | 7 | 17 | 25 | 33 | 42 | 49 | 56 | 64 | 73 | 82 | 89 | 96 | 105 | 3 | 1 | 2 | 1 | 3 | 3 | 1 | 3 | 1 | 2 | 3 | 2 | 1 | 3 | 1 | 3 | 2 | 2 | 2 | 3 | 1 | 3 | 2 | 1 | 2 | 1 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 3 | 2 | 3 | 2 | 2 | 2 | 1 | 2 | 3 | 1 | 1 | 2 | 1 | 3 | 2 | 1 | 3 | 3
297 | 14 | 10 | 18 | 25 | 30 | 37 | 43 | 53 | 60 | 66 | 75 | 82 | 90 | 97 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 3 | 1 | 2 | 2 | 1 | 1 | 3 | 3 | 3 | 1 | 3 | 1 | 2 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 1 | 1 | 1 | 3 | 2 | 3 | 1 | 1 | 3 | 2 | 1 | 3 | 1
298 | 12 | 7 | 15 | 25 | 34 | 42 | 48 | 54 | 62 | 72 | 76 | 85 | 91 | 97 | 1 | 2 | 1 | 3 | 3 | 2 | 1 | 2 | 3 | 1 | 3 | 3 | 3 | 1 | 2 | 3 | 1 | 3 | 1 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 3 | 3 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 1 | 1 | 1 | 2 | 1 | 2 | 1
299 | 11 | 6 | 15 | 22 | 29 | 39 | 48 | 58 | 65 | 73 | 81 | 87 | 97 | 104 | 2 | 2 | 1 | 1 | 2 | 3 | 1 | 3 | 3 | 1 | 2 | 1 | 1 | 3 | 2 | 1 | 3 | 3 | 1 | 3 | 2 | 3 | 3 | 1 | 2 | 3 | 3 | 2 | 1 | 3 | 2 | 1 | 1 | 3 | 1 | 3 | 1 | 2 | 3 | 2 | 3 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 1 | 1 | 2
300 | 13 | 7 | 18 | 24 | 30 | 39 | 44 | 48 | 55 | 63 | 68 | 76 | 81 | 89 | 1 | 2 | 1 | 3 | 3 | 3 | 2 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 2 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 2 | 3 | 2
301 | 12 | 8 | 14 | 20 | 25 | 32 | 39 | 46 | 51 | 61 | 68 | 77 | 83 | 90 | 1 | 3 | 1 | 3 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 2 | 2 | 1 | 2 | 3 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 3 | 3 | 3 | 2 | 1 | 2 | 2 | 2 | 3 | 3 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 3 | 1
302 | 9 | 6 | 12 | 17 | 28 | 34 | 40 | 48 | 53 | 59 | 67 | 73 | 80 | 86 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 3 | 3 | 3 | 2 | 1 | 2 | 2 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 2 | 2 | 1 | 3 | 1 | 1
303 | 9 | 5 | 13 | 17 | 28 | 33 | 41 | 50 | 55 | 62 | 67 | 75 | 81 | 89 | 1 | 1 | 1 | 2 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 3 | 3 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 2 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 1 | 2 | 1 | 2 | 1 | 1 | 3 | 3
304 | 9 | 7 | 13 | 19 | 26 | 33 | 38 | 46 | 57 | 64 | 70 | 76 | 84 | 93 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 3 | 2 | 2 | 1 | 1 | 2 | 2 | 1 | 2 | 2 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 3 | 3 | 3 | 2 | 2 | 2 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 3 | 3 | 1 | 1 | 3 | 3 | 2
305 | 9 | 6 | 11 | 17 | 24 | 30 | 37 | 47 | 54 | 59 | 63 | 67 | 72 | 78 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 1 | 3 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 1
306 | 14 | 9 | 18 | 24 | 29 | 35 | 41 | 50 | 57 | 64 | 68 | 74 | 83 | 90 | 3 | 1 | 3 | 2 | 2 | 3 | 2 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 3 | 3 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 2 | 2 | 3 | 1 | 1 | 3 | 2
307 | 11 | 9 | 14 | 21 | 31 | 36 | 43 | 51 | 59 | 65 | 72 | 82 | 86 | 91 | 3 | 1 | 2 | 3 | 1 | 1 | 1 | 2 | 2 | 3 | 1 | 1 | 3 | 3 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 2 | 3 | 3 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1
308 | 11 | 9 | 13 | 22 | 28 | 33 | 42 | 49 | 56 | 62 | 68 | 74 | 80 | 89 | 3 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 3 | 2 | 2 | 1 | 3 | 1 | 2 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 3 | 1 | 2 | 3
309 | 8 | 5 | 13 | 19 | 26 | 32 | 39 | 43 | 50 | 57 | 64 | 71 | 80 | 86 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 3 | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 2 | 3 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 3 | 2 | 3 | 1 | 1 | 1 | 3
310 | 9 | 7 | 15 | 21 | 31 | 37 | 45 | 54 | 61 | 66 | 76 | 83 | 89 | 96 | 1 | 2 | 1 | 3 | 1 | 1 | 3 | 3 | 2 | 1 | 1 | 2 | 1 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 2 | 3 | 3 | 3 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 1 | 3 | 3 | 1 | 2 | 1 | 3 | 1 | 2 | 2 | 1 | 1 | 3 | 1 | 2
311 | 10 | 6 | 12 | 20 | 26 | 31 | 40 | 44 | 51 | 59 | 66 | 73 | 77 | 83 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 2 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 2 | 1 | 3 | 2 | 1 | 1 | 3 | 2 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1
312 | 13 | 10 | 16 | 23 | 30 | 41 | 50 | 56 | 61 | 70 | 76 | 82 | 87 | 91 | 1 | 3 | 3 | 3 | 2 | 1 | 1 | 2 | 1 | 2 | 3 | 1 | 1 | 1 | 3 | 2 | 3 | 3 | 2 | 3 | 3 | 2 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 2 | 2 | 2 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1
313 | 7 | 5 | 11 | 18 | 27 | 33 | 41 | 48 | 55 | 64 | 71 | 77 | 88 | 92 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 3 | 3 | 2 | 3 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 3 | 2 | 3 | 3 | 1 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 2 | 3 | 1 | 1 | 1 | 1
314 | 12 | 8 | 15 | 23 | 33 | 38 | 44 | 50 | 57 | 62 | 71 | 79 | 87 | 93 | 1 | 3 | 1 | 3 | 3 | 1 | 2 | 1 | 1 | 3 | 1 | 3 | 3 | 1 | 3 | 3 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 3 | 1 | 3 | 2 | 3 | 1 | 3 | 1 | 2 | 3 | 1 | 2 | 2 | 1 | 1 | 2
315 | 8 | 6 | 10 | 17 | 26 | 34 | 38 | 47 | 52 | 57 | 65 | 71 | 80 | 85 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 3 | 2 | 3 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 3 | 2 | 1 | 1 | 1 | 2 | 2 | 3 | 1 | 3 | 2 | 1 | 1 | 1 | 2
316 | 11 | 5 | 15 | 22 | 29 | 35 | 45 | 52 | 59 | 63 | 71 | 77 | 84 | 90 | 1 | 1 | 2 | 1 | 3 | 3 | 3 | 1 | 1 | 2 | 1 | 3 | 1 | 3 | 1 | 2 | 2 | 1 | 2 | 1 | 3 | 2 | 2 | 3 | 2 | 3 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 2 | 1 | 2 | 2 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 2
317 | 8 | 6 | 12 | 21 | 30 | 39 | 43 | 47 | 52 | 57 | 66 | 70 | 77 | 82 | 2 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 3 | 3 | 2 | 3 | 3 | 1 | 2 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 1
318 | 8 | 6 | 10 | 17 | 26 | 35 | 41 | 45 | 52 | 60 | 66 | 72 | 76 | 83 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 3 | 3 | 1 | 2 | 2 | 3 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 2 | 2 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 1
319 | 9 | 7 | 14 | 20 | 26 | 32 | 38 | 43 | 50 | 59 | 65 | 70 | 76 | 84 | 1 | 1 | 2 | 3 | 1 | 1 | 2 | 3 | 1 | 2 | 1 | 2 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 3 | 2 | 1 | 3 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 3
320 | 12 | 10 | 18 | 23 | 28 | 35 | 43 | 53 | 57 | 64 | 74 | 78 | 88 | 95 | 2 | 3 | 3 | 2 | 1 | 1 | 3 | 3 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 1 | 2 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 1 | 2 | 3 | 1
321 | 12 | 10 | 14 | 22 | 31 | 37 | 43 | 49 | 59 | 63 | 70 | 75 | 81 | 88 | 3 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 3 | 2 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 2 | 1 | 2 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 2 | 1 | 2
322 | 11 | 9 | 16 | 23 | 31 | 38 | 46 | 54 | 60 | 67 | 74 | 81 | 90 | 101 | 3 | 3 | 2 | 1 | 1 | 1 | 3 | 2 | 3 | 2 | 1 | 1 | 2 | 2 | 1 | 3 | 2 | 2 | 2 | 1 | 2 | 3 | 2 | 1 | 2 | 2 | 3 | 1 | 1 | 2 | 1 | 2 | 1 | 2 | 3 | 1 | 1 | 1 | 2 | 3 | 3 | 1 | 2 | 1 | 3 | 2 | 3 | 1 | 3 | 3 | 2 | 3
323 | 15 | 10 | 20 | 25 | 32 | 39 | 47 | 54 | 63 | 67 | 71 | 81 | 89 | 95 | 3 | 3 | 3 | 1 | 2 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 3 | 2 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 3 | 2 | 2 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 3 | 1 | 3 | 2 | 2 | 1 | 1 | 2 | 2
324 | 10 | 6 | 16 | 24 | 32 | 38 | 45 | 51 | 56 | 65 | 71 | 78 | 86 | 93 | 1 | 2 | 2 | 1 | 3 | 1 | 3 | 3 | 2 | 2 | 3 | 1 | 2 | 1 | 2 | 3 | 1 | 1 | 3 | 1 | 3 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 3 | 1 | 3 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 3 | 2 | 2 | 2 | 2 | 1 | 1 | 3 | 2
325 | 11 | 6 | 14 | 19 | 27 | 33 | 38 | 42 | 50 | 57 | 65 | 73 | 79 | 85 | 1 | 2 | 2 | 1 | 2 | 3 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 3 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 1 | 2 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 3 | 3 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 2
326 | 12 | 9 | 15 | 19 | 27 | 32 | 39 | 45 | 50 | 56 | 62 | 72 | 78 | 85 | 2 | 2 | 3 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 1 | 3 | 3 | 2 | 2 | 1 | 1 | 3 | 1 | 1 | 2
327 | 10 | 8 | 15 | 20 | 27 | 32 | 40 | 46 | 55 | 61 | 67 | 76 | 84 | 90 | 1 | 3 | 3 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 2 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 3 | 2 | 1 | 1 | 3 | 3 | 1 | 3 | 1 | 1 | 1
328 | 12 | 8 | 16 | 23 | 29 | 35 | 43 | 51 | 58 | 64 | 69 | 77 | 84 | 93 | 1 | 3 | 2 | 2 | 3 | 1 | 3 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 3 | 2 | 1 | 2 | 1 | 1 | 3 | 3 | 1 | 3 | 3 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 3 | 3 | 1 | 2 | 1 | 2 | 3 | 3 | 1
329 | 10 | 7 | 12 | 21 | 27 | 35 | 40 | 46 | 52 | 56 | 64 | 69 | 76 | 81 | 1 | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 3 | 2 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 2 | 3 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 2 | 2 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 2 | 1 | 1
330 | 10 | 7 | 13 | 22 | 32 | 42 | 48 | 53 | 58 | 67 | 73 | 82 | 86 | 94 | 1 | 2 | 1 | 3 | 2 | 1 | 2 | 1 | 3 | 3 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 3 | 2 | 3 | 1 | 2 | 1 | 2 | 3 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 1
331 | 11 | 7 | 13 | 20 | 26 | 31 | 36 | 40 | 49 | 55 | 61 | 69 | 76 | 84 | 3 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 3 | 1 | 1 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 3 | 1 | 1 | 3
332 | 11 | 7 | 15 | 23 | 30 | 35 | 44 | 52 | 58 | 65 | 75 | 80 | 87 | 91 | 2 | 1 | 3 | 1 | 1 | 3 | 1 | 3 | 3 | 3 | 1 | 1 | 1 | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 2 | 1 | 3 | 3 | 2 | 3 | 2 | 1 | 2 | 2 | 1 | 1 | 2 | 3 | 1 | 1 | 2 | 3 | 2 | 3 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 1
333 | 14 | 8 | 17 | 25 | 34 | 42 | 50 | 54 | 62 | 68 | 75 | 82 | 92 | 101 | 1 | 3 | 1 | 3 | 3 | 3 | 2 | 1 | 3 | 2 | 1 | 2 | 1 | 3 | 3 | 2 | 1 | 1 | 3 | 3 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 3 | 2 | 1 | 1 | 3 | 3 | 3 | 1 | 3 | 2 | 3
334 | 9 | 7 | 12 | 18 | 23 | 32 | 40 | 47 | 51 | 56 | 63 | 69 | 77 | 83 | 1 | 1 | 2 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 3 | 3 | 2 | 1 | 1 | 2 | 3 | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 2 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 2 | 1 | 3 | 1 | 1
335 | 14 | 8 | 18 | 23 | 32 | 39 | 45 | 50 | 58 | 66 | 73 | 80 | 86 | 93 | 3 | 1 | 1 | 3 | 3 | 3 | 1 | 3 | 1 | 1 | 1 | 2 | 2 | 3 | 2 | 2 | 1 | 2 | 3 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 1 | 3 | 1 | 3 | 3 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 3 | 1 | 2 | 1 | 3 | 1 | 1 | 2 | 1 | 2 | 2
336 | 9 | 5 | 13 | 19 | 27 | 34 | 39 | 48 | 53 | 63 | 68 | 75 | 82 | 89 | 1 | 2 | 1 | 1 | 1 | 3 | 2 | 2 | 1 | 3 | 1 | 1 | 2 | 2 | 1 | 3 | 1 | 1 | 2 | 3 | 1 | 1 | 2 | 1 | 2 | 3 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 3 | 2
337 | 9 | 6 | 13 | 21 | 27 | 34 | 41 | 47 | 54 | 59 | 67 | 73 | 78 | 86 | 1 | 1 | 3 | 1 | 1 | 2 | 3 | 1 | 3 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 2 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 3
338 | 13 | 7 | 16 | 23 | 33 | 37 | 42 | 54 | 59 | 67 | 75 | 81 | 85 | 93 | 3 | 1 | 1 | 2 | 3 | 3 | 2 | 1 | 2 | 1 | 3 | 1 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 3 | 3 | 3 | 1 | 1 | 2 | 1 | 2 | 1 | 2 | 3 | 1 | 1 | 3 | 3 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 3
339 | 10 | 7 | 12 | 20 | 27 | 35 | 39 | 47 | 54 | 59 | 66 | 74 | 79 | 87 | 2 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 2 | 2 | 1 | 3 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 2 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 3 | 1 | 2 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 3
340 | 7 | 5 | 13 | 21 | 28 | 37 | 45 | 50 | 56 | 62 | 68 | 75 | 82 | 86 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 2 | 3 | 2 | 1 | 3 | 2 | 1 | 3 | 3 | 1 | 2 | 2 | 2 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 1
341 | 9 | 7 | 12 | 21 | 29 | 35 | 41 | 47 | 53 | 59 | 65 | 72 | 78 | 86 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 3 | 1 | 1 | 3 | 3 | 1 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 2 | 2
342 | 11 | 7 | 13 | 18 | 23 | 29 | 38 | 45 | 53 | 59 | 65 | 73 | 81 | 86 | 1 | 2 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 3 | 3 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 2 | 1
343 | 9 | 6 | 13 | 20 | 31 | 37 | 45 | 51 | 59 | 65 | 72 | 78 | 88 | 92 | 2 | 1 | 2 | 1 | 1 | 2 | 3 | 1 | 1 | 3 | 1 | 2 | 3 | 2 | 3 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 3 | 1 | 1 | 1 | 3 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 2 | 3 | 1 | 2 | 1 | 2 | 1 | 3 | 3 | 1 | 3 | 1 | 1 | 1 | 1
344 | 9 | 7 | 11 | 16 | 23 | 30 | 37 | 43 | 47 | 54 | 63 | 67 | 71 | 77 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 3 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 3 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2
345 | 13 | 7 | 17 | 22 | 31 | 37 | 44 | 51 | 57 | 65 | 71 | 81 | 87 | 96 | 2 | 2 | 2 | 1 | 3 | 3 | 1 | 3 | 1 | 2 | 1 | 1 | 3 | 2 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 3 | 3 | 1 | 3 | 2 | 2 | 1 | 1 | 3 | 1 | 3 | 2
346 | 13 | 8 | 15 | 23 | 30 | 35 | 44 | 51 | 59 | 65 | 75 | 82 | 89 | 95 | 1 | 1 | 3 | 3 | 2 | 3 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 3 | 3 | 1 | 2 | 3 | 1 | 1 | 3 | 3 | 1 | 1 | 2 | 1 | 2 | 3 | 2 | 2 | 3 | 1 | 1 | 2 | 3 | 2 | 1 | 1 | 3 | 2 | 1 | 2 | 1
347 | 8 | 5 | 10 | 16 | 21 | 29 | 34 | 39 | 45 | 52 | 58 | 69 | 76 | 83 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 2 | 1 | 3 | 1 | 1 | 3 | 2 | 3 | 3 | 3 | 1 | 2 | 1 | 2 | 1 | 1 | 3
348 | 12 | 8 | 17 | 22 | 28 | 35 | 43 | 47 | 52 | 58 | 64 | 69 | 77 | 87 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 1 | 3 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 3 | 2 | 3 | 2 | 3
349 | 13 | 8 | 17 | 24 | 32 | 37 | 44 | 51 | 59 | 64 | 71 | 82 | 89 | 99 | 3 | 2 | 2 | 1 | 3 | 2 | 2 | 2 | 1 | 2 | 3 | 1 | 3 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 2 | 1 | 3 | 1 | 2 | 3 | 2 | 1 | 1 | 2 | 1 | 3 | 1 | 2 | 1 | 3 | 2 | 3 | 3 | 2 | 1 | 3 | 1 | 2 | 2 | 3 | 3
350 | 7 | 4 | 10 | 16 | 21 | 28 | 36 | 43 | 51 | 59 | 68 | 75 | 81 | 87 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 3 | 2 | 2 | 1 | 3 | 1 | 2 | 2 | 1 | 3 | 2 | 3 | 2 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 3 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1
351 | 10 | 6 | 13 | 18 | 27 | 31 | 38 | 44 | 51 | 57 | 63 | 70 | 80 | 88 | 2 | 2 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 3 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | 2 | 1 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 1 | 3 | 1 | 3
352 | 12 | 6 | 16 | 21 | 28 | 33 | 42 | 49 | 59 | 66 | 74 | 79 | 85 | 92 | 3 | 1 | 1 | 1 | 3 | 3 | 1 | 3 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 3 | 3 | 3 | 1 | 2 | 3 | 1 | 2 | 2 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 2
353 | 11 | 9 | 15 | 24 | 33 | 40 | 47 | 55 | 63 | 72 | 81 | 89 | 98 | 104 | 3 | 3 | 2 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 3 | 1 | 2 | 1 | 3 | 3 | 1 | 1 | 3 | 1 | 3 | 2 | 1 | 3 | 3 | 2 | 3 | 1 | 3 | 3 | 2 | 2 | 1 | 3 | 1 | 2 | 3 | 2 | 1 | 2 | 1
354 | 8 | 6 | 10 | 21 | 29 | 37 | 42 | 50 | 57 | 61 | 66 | 74 | 83 | 90 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 3 | 3 | 3 | 2 | 2 | 1 | 3 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 1 | 2 | 3 | 2 | 3 | 1 | 2 | 1 | 1 | 3
355 | 10 | 6 | 15 | 20 | 27 | 33 | 40 | 47 | 57 | 63 | 72 | 79 | 83 | 91 | 1 | 1 | 1 | 3 | 1 | 3 | 2 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 2 | 2 | 3 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 3 | 3 | 2 | 2 | 1 | 1 | 3 | 2 | 2 | 2 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 1
356 | 11 | 7 | 13 | 21 | 27 | 31 | 35 | 42 | 50 | 58 | 62 | 69 | 77 | 86 | 3 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 3 | 2 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 3 | 1 | 1 | 3 | 1 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 3 | 1 | 1 | 3 | 3 | 1 | 3 | 2
357 | 9 | 6 | 13 | 21 | 27 | 33 | 40 | 48 | 57 | 65 | 75 | 81 | 87 | 95 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 3 | 3 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 2 | 2 | 3 | 1 | 3 | 1 | 2 | 3 | 3 | 1 | 3 | 1 | 3 | 1 | 2 | 3 | 2 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 3
358 | 10 | 7 | 15 | 23 | 32 | 39 | 45 | 51 | 58 | 64 | 70 | 78 | 88 | 95 | 1 | 3 | 1 | 2 | 2 | 1 | 2 | 3 | 3 | 1 | 3 | 1 | 1 | 2 | 3 | 3 | 1 | 2 | 2 | 2 | 1 | 2 | 2 | 1 | 1 | 2 | 1 | 2 | 1 | 3 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 3 | 3 | 2 | 2 | 3 | 2 | 3 | 1 | 1
359 | 8 | 5 | 11 | 15 | 20 | 27 | 33 | 40 | 48 | 54 | 63 | 68 | 73 | 81 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 3 | 3 | 2 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 3 | 1 | 2 | 2
360 | 10 | 8 | 14 | 18 | 22 | 29 | 37 | 45 | 53 | 61 | 68 | 75 | 83 | 90 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 2 | 2 | 1 | 3 | 3 | 1 | 2 | 2 | 1 | 2 | 2 | 3 | 3 | 1 | 3 | 1 | 3 | 1 | 1 | 2 | 3 | 1 | 2 | 1 | 3 | 1 | 3 | 1 | 1 | 2 | 1 | 3
361 | 13 | 11 | 17 | 24 | 33 | 38 | 45 | 52 | 58 | 66 | 74 | 82 | 88 | 97 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 3 | 1 | 3 | 2 | 1 | 2 | 1 | 3 | 3 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 2 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 2 | 2 | 1 | 3 | 2 | 2 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 3 | 3 | 1 | 2 | 3
362 | 13 | 7 | 15 | 23 | 29 | 36 | 44 | 49 | 56 | 65 | 72 | 77 | 83 | 90 | 3 | 1 | 2 | 1 | 3 | 3 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 3 | 3 | 1 | 2 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | 3
363 | 10 | 8 | 15 | 23 | 30 | 36 | 47 | 55 | 64 | 74 | 79 | 85 | 93 | 102 | 2 | 2 | 1 | 3 | 1 | 1 | 2 | 3 | 3 | 1 | 3 | 1 | 2 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 3 | 3 | 3 | 2 | 1 | 3 | 2 | 2 | 1 | 2 | 3 | 3 | 3 | 3 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 2 | 2 | 2 | 2 | 1 | 3 | 3 | 2
364 | 14 | 9 | 17 | 29 | 37 | 45 | 52 | 57 | 63 | 73 | 82 | 91 | 96 | 103 | 3 | 2 | 2 | 2 | 3 | 2 | 2 | 1 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 2 | 1 | 1 | 3 | 3 | 1 | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 3 | 1 | 3 | 2 | 3 | 1 | 3 | 1 | 3 | 3 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 3 | 1
365 | 8 | 5 | 10 | 20 | 27 | 34 | 40 | 46 | 54 | 62 | 71 | 83 | 91 | 99 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 3 | 3 | 1 | 3 | 1 | 3 | 2 | 1 | 1 | 1 | 2 | 3 | 1 | 2 | 1 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 3 | 3 | 2 | 2 | 1 | 1 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 1 | 3 | 2 | 2 | 3 | 1 | 1 | 3
366 | 11 | 7 | 15 | 20 | 27 | 33 | 41 | 48 | 56 | 60 | 68 | 74 | 85 | 91 | 3 | 1 | 1 | 2 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 3 | 2 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 2 | 1 | 2 | 2 | 1
367 | 9 | 7 | 12 | 21 | 29 | 35 | 44 | 51 | 59 | 63 | 70 | 78 | 85 | 92 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 2 | 2 | 3 | 1 | 3 | 2 | 1 | 2 | 3 | 1 | 3 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 1 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 2 | 3 | 1 | 1 | 3 | 2
368 | 10 | 7 | 14 | 21 | 28 | 33 | 40 | 49 | 53 | 59 | 67 | 72 | 81 | 89 | 3 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 3 | 2 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 2 | 1 | 1 | 3 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 2 | 1 | 1 | 3 | 2 | 1 | 3 | 2 | 2 | 1 | 3
369 | 9 | 6 | 11 | 19 | 26 | 30 | 36 | 43 | 53 | 61 | 65 | 70 | 74 | 82 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 3 | 3 | 3 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 3
370 | 12 | 8 | 14 | 20 | 27 | 36 | 42 | 52 | 60 | 68 | 75 | 81 | 86 | 92 | 3 | 1 | 2 | 2 | 3 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 1 | 3 | 3 | 1 | 3 | 1 | 1 | 3 | 3 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 3
371 | 10 | 7 | 12 | 16 | 23 | 28 | 36 | 45 | 51 | 59 | 68 | 74 | 81 | 87 | 3 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 3 | 2 | 1 | 3 | 3 | 1 | 2 | 2 | 1 | 3 | 2 | 1 | 2 | 3 | 2 | 3 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 3 | 1 | 2 | 2 | 1
372 | 16 | 12 | 20 | 25 | 33 | 37 | 46 | 55 | 65 | 74 | 83 | 90 | 97 | 102 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 2 | 3 | 1 | 1 | 3 | 2 | 3 | 2 | 3 | 2 | 3 | 3 | 1 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 2
373 | 8 | 6 | 12 | 22 | 30 | 40 | 46 | 52 | 61 | 68 | 75 | 83 | 90 | 95 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 1 | 3 | 1 | 3 | 1 | 1 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 3 | 1 | 3 | 1 | 1 | 2 | 3 | 1 | 1 | 2 | 3 | 3 | 2 | 1 | 2 | 3 | 2 | 1 | 1 | 1 | 2 | 1 | 1
374 | 11 | 7 | 15 | 24 | 32 | 40 | 47 | 53 | 61 | 69 | 78 | 85 | 94 | 102 | 1 | 1 | 3 | 2 | 1 | 3 | 3 | 1 | 2 | 1 | 3 | 3 | 3 | 2 | 1 | 2 | 1 | 3 | 3 | 1 | 2 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 2 | 3 | 1 | 2 | 3 | 3 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 1 | 1 | 3 | 1 | 3 | 3 | 2 | 2 | 3 | 1 | 2
375 | 9 | 5 | 11 | 19 | 28 | 36 | 43 | 50 | 57 | 65 | 76 | 84 | 89 | 93 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 3 | 1 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 2 | 1 | 3 | 2 | 3 | 2 | 3 | 3 | 3 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
376 | 8 | 4 | 11 | 18 | 24 | 35 | 43 | 52 | 59 | 65 | 69 | 76 | 82 | 93 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 2 | 1 | 3 | 1 | 1 | 2 | 2 | 1 | 3 | 3 | 2 | 3 | 3 | 1 | 1 | 3 | 3 | 2 | 3 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 2 | 3 | 3 | 3
377 | 12 | 7 | 16 | 22 | 31 | 38 | 45 | 51 | 61 | 68 | 75 | 85 | 93 | 101 | 1 | 3 | 1 | 2 | 3 | 2 | 1 | 3 | 3 | 1 | 1 | 1 | 2 | 3 | 3 | 1 | 1 | 2 | 3 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 1 | 3 | 1 | 2 | 1 | 3 | 3 | 1 | 1 | 2 | 3 | 1 | 3 | 3 | 2 | 1 | 3 | 2 | 2 | 3 | 2 | 1
378 | 8 | 5 | 10 | 15 | 24 | 31 | 39 | 46 | 55 | 62 | 70 | 76 | 84 | 94 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 1 | 3 | 3 | 1 | 2 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 3 | 2 | 3 | 3 | 2 | 1 | 2 | 1 | 2 | 2 | 1 | 2 | 3 | 2 | 1 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 2 | 3 | 2
379 | 11 | 7 | 14 | 20 | 29 | 35 | 44 | 49 | 54 | 61 | 66 | 71 | 76 | 80 | 3 | 2 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 3 | 3 | 1 | 2 | 1 | 2 | 1 | 2 | 2 | 3 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1
380 | 8 | 5 | 11 | 19 | 28 | 34 | 42 | 49 | 54 | 62 | 71 | 81 | 90 | 96 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 3 | 3 | 1 | 1 | 3 | 2 | 3 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 1 | 2 | 3 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 2 | 1 | 3 | 3 | 1 | 3 | 3 | 3 | 3 | 2 | 1 | 3 | 1 | 1 | 1 | 3
381 | 10 | 6 | 12 | 17 | 25 | 29 | 37 | 42 | 48 | 55 | 63 | 68 | 73 | 77 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 3 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
382 | 12 | 8 | 16 | 21 | 27 | 33 | 39 | 49 | 58 | 65 | 69 | 75 | 82 | 89 | 1 | 1 | 3 | 3 | 3 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 3 | 2 | 3 | 2 | 2 | 3 | 3 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 3 | 1 | 2
383 | 11 | 7 | 16 | 24 | 29 | 33 | 39 | 46 | 53 | 58 | 66 | 70 | 77 | 84 | 3 | 1 | 1 | 2 | 2 | 2 | 3 | 2 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 3 | 1 | 1 | 2 | 1 | 3 | 2 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 3 | 2
384 | 12 | 8 | 17 | 25 | 34 | 41 | 47 | 54 | 59 | 64 | 71 | 77 | 81 | 85 | 1 | 1 | 3 | 3 | 3 | 1 | 3 | 2 | 1 | 1 | 3 | 3 | 1 | 3 | 3 | 2 | 1 | 3 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
385 | 14 | 8 | 16 | 24 | 28 | 32 | 38 | 48 | 55 | 61 | 67 | 74 | 82 | 92 | 1 | 3 | 3 | 1 | 3 | 3 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 3 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 1 | 1 | 1 | 3 | 1 | 3 | 3 | 1 | 3 | 3
386 | 13 | 7 | 17 | 25 | 33 | 40 | 47 | 55 | 60 | 66 | 73 | 80 | 85 | 94 | 2 | 1 | 1 | 3 | 3 | 3 | 1 | 3 | 3 | 1 | 3 | 1 | 3 | 2 | 1 | 2 | 3 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 2 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 3 | 1 | 2
387 | 9 | 6 | 12 | 20 | 30 | 38 | 47 | 52 | 61 | 70 | 79 | 84 | 90 | 97 | 3 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 3 | 2 | 2 | 1 | 2 | 3 | 3 | 2 | 1 | 1 | 3 | 3 | 2 | 1 | 3 | 3 | 1 | 2 | 1 | 1 | 2 | 3 | 1 | 3 | 1 | 3 | 2 | 3 | 3 | 1 | 3 | 2 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 2 | 1
388 | 11 | 9 | 13 | 24 | 31 | 39 | 46 | 55 | 60 | 70 | 75 | 82 | 91 | 98 | 2 | 2 | 2 | 3 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 2 | 1 | 1 | 2 | 3 | 3 | 1 | 2 | 2 | 1 | 2 | 2 | 2 | 3 | 2 | 1 | 3 | 1 | 2 | 1 | 1 | 2 | 3 | 3 | 2 | 1 | 2 | 1 | 1 | 1 | 3 | 2 | 1 | 3 | 1 | 2 | 3 | 1 | 3 | 1 | 2
389 | 14 | 9 | 18 | 24 | 31 | 38 | 44 | 48 | 55 | 65 | 71 | 76 | 84 | 90 | 3 | 2 | 1 | 3 | 3 | 2 | 3 | 1 | 1 | 1 | 2 | 2 | 1 | 3 | 2 | 1 | 2 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 3 | 2 | 2 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 3 | 1 | 1 | 2 | 2 | 1
390 | 12 | 8 | 14 | 22 | 31 | 38 | 46 | 53 | 62 | 66 | 75 | 82 | 88 | 97 | 3 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 3 | 3 | 2 | 2 | 3 | 1 | 1 | 3 | 2 | 1 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 3 | 3 | 2 | 1 | 2 | 1 | 3 | 1 | 2 | 1 | 1 | 2 | 2 | 3 | 1 | 3
391 | 10 | 7 | 15 | 20 | 27 | 35 | 45 | 52 | 60 | 66 | 72 | 83 | 89 | 96 | 1 | 2 | 3 | 1 | 1 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 3 | 1 | 1 | 3 | 3 | 3 | 3 | 1 | 2 | 1 | 1 | 3 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 2 | 3 | 2 | 3 | 3 | 2 | 1 | 2 | 1 | 2 | 1 | 1 | 3
392 | 8 | 6 | 12 | 21 | 26 | 34 | 38 | 45 | 51 | 56 | 63 | 69 | 73 | 82 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 3
393 | 8 | 6 | 10 | 17 | 26 | 36 | 42 | 46 | 55 | 64 | 71 | 78 | 84 | 90 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 2 | 3 | 1 | 2 | 3 | 1 | 1 | 2 | 3 | 2 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 2
394 | 10 | 6 | 12 | 18 | 26 | 31 | 39 | 45 | 52 | 61 | 71 | 79 | 85 | 91 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 3 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 2 | 1 | 2 | 1 | 1 | 3 | 1 | 2 | 3 | 2 | 3 | 1 | 3 | 3 | 1 | 3 | 2 | 3 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 2
395 | 9 | 7 | 13 | 18 | 27 | 32 | 42 | 50 | 55 | 64 | 71 | 77 | 83 | 93 | 1 | 1 | 3 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 3 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 1 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 3 | 2 | 3 | 2
396 | 11 | 8 | 16 | 23 | 32 | 37 | 45 | 50 | 56 | 64 | 71 | 78 | 87 | 96 | 2 | 2 | 1 | 3 | 1 | 2 | 3 | 2 | 3 | 1 | 1 | 2 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 3 | 3 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 2 | 1 | 2 | 1 | 3 | 2 | 3 | 1 | 3 | 2 | 3
397 | 12 | 9 | 15 | 21 | 25 | 30 | 37 | 45 | 52 | 56 | 61 | 68 | 75 | 84 | 3 | 1 | 2 | 3 | 2 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 2 | 2 | 2 | 1 | 3 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 3 | 1 | 2 | 1 | 2 | 3 | 3
398 | 10 | 7 | 14 | 20 | 25 | 32 | 40 | 48 | 53 | 61 | 67 | 72 | 80 | 85 | 2 | 1 | 1 | 3 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 3 | 1 | 3 | 2 | 1 | 2 | 3 | 1 | 1 | 1 | 2 | 3 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 1 | 1 | 1 | 1 | 2
399 | 12 | 9 | 17 | 23 | 32 | 36 | 40 | 50 | 56 | 63 | 68 | 72 | 81 | 88 | 3 | 2 | 2 | 2 | 1 | 2 | 2 | 3 | 1 | 2 | 2 | 1 | 3 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 3 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 3 | 1 | 3 | 2 | 1
400 | 12 | 9 | 15 | 24 | 31 | 37 | 42 | 51 | 59 | 68 | 72 | 80 | 86 | 93 | 1 | 3 | 3 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 3 | 3 | 1 | 3 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 3 | 2 | 3 | 1 | 1 | 3 | 1 | 3 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 1
401 | 9 | 7 | 13 | 24 | 34 | 40 | 44 | 51 | 58 | 64 | 71 | 81 | 87 | 94 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 1 | 1 | 3 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 3 | 2 | 3 | 2 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 3
402 | 10 | 6 | 15 | 21 | 26 | 33 | 40 | 47 | 53 | 61 | 68 | 74 | 83 | 88 | 1 | 1 | 1 | 3 | 1 | 3 | 3 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 3 | 1 | 2 | 1 | 2 | 1 | 1 | 3 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 3 | 2 | 3 | 1 | 2 | 1 | 2 | 3 | 1 | 1 | 1 | 2 | 2 | 3 | 2 | 3 | 1 | 1 | 1 | 1 | 2
403 | 10 | 6 | 16 | 24 | 31 | 38 | 47 | 56 | 61 | 67 | 73 | 82 | 90 | 97 | 3 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 1 | 3 | 1 | 1 | 3 | 1 | 2 | 1 | 3 | 2 | 1 | 3 | 2 | 1 | 3 | 1 | 3 | 2 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 2 | 1 | 3 | 1 | 2 | 3 | 1 | 3 | 1 | 3 | 3 | 1 | 2 | 1
404 | 7 | 4 | 10 | 18 | 24 | 29 | 35 | 43 | 49 | 54 | 60 | 67 | 74 | 79 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 2
405 | 11 | 8 | 15 | 23 | 34 | 40 | 46 | 53 | 58 | 64 | 72 | 79 | 86 | 95 | 1 | 3 | 1 | 3 | 2 | 1 | 2 | 2 | 1 | 2 | 3 | 2 | 2 | 3 | 3 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 2 | 2 | 3 | 2 | 3 | 1 | 1 | 2 | 1 | 3 | 1 | 3 | 1 | 3 | 2
406 | 13 | 9 | 16 | 23 | 33 | 41 | 45 | 55 | 65 | 71 | 77 | 83 | 89 | 98 | 3 | 2 | 1 | 3 | 2 | 2 | 1 | 2 | 3 | 1 | 1 | 2 | 1 | 3 | 3 | 3 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 3 | 3 | 1 | 3 | 3 | 1 | 1 | 1 | 3 | 2 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 2 | 3 | 3 | 1
407 | 15 | 9 | 19 | 27 | 33 | 40 | 45 | 55 | 63 | 70 | 78 | 86 | 94 | 106 | 3 | 1 | 3 | 2 | 3 | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 3 | 1 | 3 | 3 | 1 | 2 | 1 | 1 | 3 | 1 | 3 | 1 | 3 | 3 | 1 | 1 | 3 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3
408 | 11 | 9 | 16 | 23 | 31 | 39 | 48 | 57 | 62 | 69 | 75 | 80 | 87 | 98 | 3 | 2 | 2 | 2 | 1 | 1 | 2 | 3 | 1 | 3 | 2 | 1 | 3 | 1 | 2 | 2 | 2 | 2 | 3 | 1 | 3 | 2 | 1 | 3 | 1 | 3 | 2 | 3 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 2 | 3 | 3 | 3
409 | 12 | 9 | 14 | 21 | 28 | 32 | 40 | 47 | 52 | 59 | 69 | 76 | 82 | 86 | 3 | 3 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 2 | 3 | 1 | 3 | 3 | 2 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1
410 | 9 | 6 | 13 | 22 | 30 | 37 | 41 | 50 | 57 | 65 | 72 | 81 | 86 | 94 | 1 | 2 | 1 | 2 | 1 | 2 | 2 | 2 | 3 | 2 | 3 | 1 | 2 | 1 | 2 | 3 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 1 | 2 | 1 | 3 | 1 | 3 | 3 | 1 | 2 | 1 | 3 | 2 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 3 | 3 | 1
411 | 10 | 7 | 13 | 20 | 27 | 33 | 42 | 48 | 54 | 65 | 72 | 78 | 82 | 87 | 1 | 1 | 3 | 2 | 2 | 1 | 1 | 2 | 1 | 3 | 1 | 2 | 2 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 3 | 2 | 1 | 2 | 1 | 2 | 2 | 2 | 1 | 1 | 3 | 3 | 2 | 3 | 1 | 3 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1
412 | 9 | 7 | 11 | 17 | 24 | 31 | 39 | 47 | 51 | 59 | 65 | 72 | 82 | 86 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 2 | 3 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 3 | 3 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 2 | 3 | 3 | 2 | 1 | 1 | 1 | 1
413 | 10 | 7 | 12 | 22 | 32 | 40 | 48 | 56 | 62 | 67 | 73 | 77 | 83 | 90 | 1 | 3 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 3 | 2 | 2 | 3 | 1 | 1 | 3 | 3 | 1 | 3 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 1 | 3
414 | 13 | 10 | 16 | 24 | 33 | 40 | 48 | 53 | 59 | 68 | 73 | 80 | 87 | 96 | 2 | 3 | 3 | 2 | 1 | 2 | 1 | 2 | 2 | 3 | 2 | 1 | 1 | 3 | 2 | 3 | 2 | 1 | 3 | 1 | 2 | 3 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 3 | 2 | 2 | 2 | 1 | 1 | 2 | 1 | 3 | 1 | 2 | 1 | 3 | 2 | 1 | 1 | 2 | 3 | 3 | 1
415 | 9 | 7 | 13 | 18 | 27 | 33 | 41 | 51 | 56 | 61 | 70 | 81 | 90 | 98 | 3 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 3 | 2 | 3 | 1 | 1 | 1 | 2 | 3 | 2 | 1 | 3 | 3 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 1 | 2 | 3 | 2 | 3 | 3 | 3 | 1 | 3 | 2 | 3 | 3 | 1 | 1
416 | 10 | 6 | 16 | 21 | 28 | 36 | 44 | 52 | 61 | 69 | 77 | 86 | 93 | 99 | 3 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 2 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 2 | 3 | 2 | 3 | 1 | 1 | 3 | 3 | 1 | 1 | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 3 | 2 | 2 | 2 | 1 | 3 | 1 | 2 | 3 | 3 | 2 | 1 | 2 | 2 | 3 | 1 | 1 | 1
417 | 10 | 7 | 12 | 18 | 25 | 31 | 37 | 43 | 53 | 59 | 67 | 76 | 83 | 90 | 2 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 1 | 1 | 3 | 1 | 3 | 1 | 2 | 2 | 2 | 2 | 3 | 2 | 3 | 1 | 2 | 1 | 1 | 3 | 1 | 2
418 | 7 | 5 | 10 | 18 | 25 | 33 | 39 | 45 | 54 | 60 | 66 | 71 | 79 | 86 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 3 | 3 | 1 | 2 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 2 | 1 | 3 | 3 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 2 | 3 | 2 | 3 | 1 | 1
419 | 9 | 6 | 12 | 18 | 23 | 27 | 34 | 40 | 45 | 50 | 56 | 61 | 67 | 73 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 3 | 1 | 1
420 | 10 | 8 | 14 | 23 | 30 | 38 | 45 | 51 | 58 | 69 | 75 | 83 | 89 | 99 | 2 | 3 | 2 | 1 | 1 | 1 | 2 | 2 | 3 | 2 | 1 | 3 | 3 | 1 | 1 | 2 | 1 | 1 | 3 | 3 | 1 | 3 | 1 | 2 | 1 | 3 | 1 | 1 | 2 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 1 | 1 | 2 | 2 | 2 | 3 | 1 | 2 | 1 | 1 | 1 | 3 | 3 | 1 | 3 | 3
421 | 8 | 6 | 12 | 18 | 26 | 33 | 40 | 46 | 53 | 58 | 64 | 68 | 74 | 81 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 3 | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 2 | 1
422 | 13 | 9 | 17 | 23 | 31 | 38 | 43 | 49 | 56 | 63 | 70 | 77 | 86 | 93 | 3 | 1 | 2 | 3 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 3 | 3 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 3 | 1 | 3 | 1 | 2 | 1 | 1 | 3 | 2 | 3 | 1 | 3 | 2 | 1
423 | 8 | 6 | 12 | 18 | 29 | 35 | 44 | 48 | 54 | 58 | 63 | 71 | 78 | 87 | 1 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 1 | 3 | 2 | 3 | 3 | 1 | 1 | 1 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 3 | 1 | 2 | 2 | 2 | 3 | 1 | 2 | 3
424 | 10 | 6 | 13 | 21 | 27 | 34 | 38 | 44 | 52 | 60 | 68 | 76 | 80 | 86 | 2 | 1 | 1 | 2 | 3 | 1 | 2 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 3 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 2 | 1 | 3 | 1 | 2 | 3 | 2 | 2 | 2 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1
425 | 12 | 8 | 14 | 20 | 27 | 33 | 39 | 46 | 56 | 64 | 72 | 77 | 85 | 90 | 3 | 2 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 2 | 1 | 1 | 1 | 2 | 1 | 2 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 3 | 3 | 3 | 1 | 2 | 3 | 2 | 3 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 2 | 1
426 | 11 | 7 | 14 | 21 | 26 | 30 | 37 | 48 | 58 | 62 | 70 | 76 | 85 | 90 | 3 | 1 | 2 | 1 | 2 | 2 | 1 | 2 | 2 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 3 | 3 | 3 | 2 | 3 | 2 | 2 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 3 | 1 | 1 | 1 | 2
427 | 10 | 5 | 14 | 22 | 28 | 33 | 40 | 47 | 54 | 61 | 68 | 76 | 81 | 89 | 2 | 1 | 1 | 1 | 2 | 3 | 3 | 1 | 3 | 1 | 2 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 2 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | 2 | 1 | 1 | 3 | 3 | 2 | 1 | 1 | 2 | 3 | 2 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 2 | 3
428 | 13 | 9 | 17 | 24 | 30 | 35 | 42 | 49 | 58 | 66 | 73 | 77 | 85 | 93 | 2 | 3 | 3 | 1 | 2 | 2 | 3 | 1 | 1 | 3 | 2 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 3 | 1 | 1 | 2 | 2 | 1 | 3 | 3 | 1 | 1 | 3 | 3 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 1 | 3 | 3 | 1
429 | 10 | 8 | 13 | 19 | 24 | 34 | 40 | 49 | 56 | 63 | 71 | 81 | 85 | 95 | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 2 | 3 | 3 | 1 | 2 | 1 | 1 | 3 | 1 | 2 | 2 | 2 | 3 | 1 | 3 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3
430 | 15 | 9 | 17 | 23 | 31 | 38 | 46 | 50 | 54 | 60 | 67 | 76 | 82 | 90 | 3 | 3 | 2 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 3 | 3 | 1 | 2 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 2 | 2 | 3 | 3 | 1 | 1 | 2 | 2 | 1 | 2 | 2 | 2 | 2
431 | 11 | 9 | 17 | 22 | 31 | 41 | 49 | 59 | 68 | 77 | 83 | 88 | 93 | 99 | 1 | 3 | 2 | 3 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 1 | 2 | 3 | 2 | 3 | 1 | 2 | 3 | 2 | 3 | 3 | 1 | 3 | 1 | 3 | 2 | 3 | 1 | 3 | 2 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 3
432 | 11 | 7 | 17 | 22 | 30 | 38 | 42 | 50 | 54 | 63 | 71 | 79 | 87 | 94 | 3 | 2 | 1 | 1 | 1 | 3 | 3 | 3 | 1 | 1 | 2 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 3 | 3 | 3 | 1 | 1 | 2 | 2 | 3 | 1 | 1 | 3 | 3 | 1 | 3 | 1 | 2 | 1
433 | 8 | 6 | 13 | 22 | 28 | 34 | 42 | 47 | 53 | 57 | 65 | 71 | 77 | 88 | 2 | 1 | 2 | 1 | 1 | 1 | 2 | 3 | 3 | 1 | 3 | 2 | 2 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 2 | 1 | 2 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 2
434 | 11 | 6 | 16 | 22 | 29 | 38 | 46 | 54 | 64 | 71 | 78 | 85 | 90 | 97 | 1 | 1 | 1 | 3 | 3 | 2 | 3 | 2 | 1 | 1 | 2 | 2 | 2 | 3 | 1 | 1 | 1 | 3 | 2 | 3 | 3 | 1 | 3 | 1 | 3 | 3 | 1 | 1 | 3 | 3 | 1 | 3 | 3 | 1 | 1 | 2 | 1 | 3 | 2 | 1 | 2 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 2 | 2 | 2 | 1
435 | 16 | 10 | 20 | 29 | 33 | 37 | 45 | 49 | 57 | 62 | 69 | 79 | 83 | 89 | 2 | 3 | 2 | 3 | 3 | 3 | 3 | 1 | 3 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 3 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1
436 | 11 | 9 | 14 | 20 | 27 | 35 | 42 | 49 | 60 | 68 | 75 | 83 | 92 | 98 | 1 | 3 | 3 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 3 | 2 | 1 | 1 | 3 | 2 | 1 | 2 | 2 | 1 | 3 | 1 | 3 | 1 | 1 | 2 | 3 | 3 | 2 | 3 | 1 | 3 | 3 | 1 | 3 | 2 | 1 | 1 | 2 | 1 | 3 | 2 | 2 | 3 | 3 | 1 | 1 | 1 | 2 | 2
437 | 10 | 6 | 12 | 17 | 27 | 32 | 38 | 44 | 54 | 62 | 68 | 79 | 87 | 98 | 2 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 3 | 3 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 2 | 3 | 1 | 2 | 2 | 3 | 2 | 2 | 1 | 1 | 3 | 3 | 2 | 3 | 3 | 1 | 2 | 2 | 3 | 3 | 3 | 2
438 | 11 | 8 | 14 | 20 | 27 | 35 | 43 | 51 | 55 | 63 | 69 | 75 | 85 | 91 | 3 | 2 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 3 | 3 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 2 | 3 | 3 | 3 | 1 | 3 | 1 | 1 | 1
439 | 10 | 7 | 16 | 24 | 30 | 40 | 48 | 55 | 62 | 67 | 75 | 84 | 89 | 96 | 3 | 1 | 2 | 1 | 2 | 1 | 3 | 3 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 3 | 2 | 3 | 2 | 3 | 3 | 1 | 3 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 2 | 3 | 1 | 1 | 2 | 1 | 3 | 3 | 1 | 1 | 3 | 3 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 2 | 2
440 | 10 | 8 | 15 | 22 | 29 | 35 | 43 | 49 | 56 | 64 | 71 | 80 | 91 | 98 | 1 | 2 | 3 | 2 | 1 | 1 | 2 | 3 | 3 | 1 | 1 | 2 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 3 | 1 | 3 | 1 | 1 | 2 | 3 | 1 | 1 | 2 | 3 | 2 | 1 | 2 | 2 | 2 | 1 | 2 | 2 | 3 | 2 | 3 | 3 | 3 | 2 | 2 | 3 | 1 | 1
441 | 8 | 6 | 12 | 17 | 22 | 28 | 32 | 38 | 46 | 52 | 61 | 67 | 75 | 86 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 1 | 3 | 2 | 3 | 3 | 3
442 | 10 | 8 | 13 | 23 | 29 | 34 | 42 | 50 | 55 | 64 | 70 | 77 | 81 | 87 | 1 | 2 | 2 | 3 | 1 | 1 | 2 | 1 | 3 | 2 | 2 | 3 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 2 | 2 | 3 | 1 | 1 | 3 | 2 | 2 | 1 | 1 | 2 | 1 | 2 | 3 | 2 | 2 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1
443 | 12 | 6 | 16 | 24 | 29 | 38 | 45 | 53 | 63 | 69 | 75 | 85 | 92 | 97 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 1 | 1 | 3 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 3 | 2 | 3 | 1 | 3 | 1 | 2 | 1 | 1 | 3 | 3 | 3 | 2 | 2 | 3 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 2 | 3 | 2 | 3 | 2 | 3 | 1 | 1 | 2 | 1 | 2 | 1 | 1
444 | 12 | 8 | 17 | 24 | 32 | 42 | 48 | 57 | 63 | 69 | 75 | 80 | 86 | 92 | 1 | 3 | 3 | 1 | 1 | 3 | 3 | 2 | 1 | 2 | 1 | 3 | 1 | 3 | 2 | 2 | 3 | 2 | 3 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 3 | 3 | 1 | 3 | 1 | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 1 | 1 | 1
445 | 10 | 6 | 12 | 18 | 22 | 31 | 37 | 45 | 54 | 61 | 70 | 77 | 83 | 89 | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 3 | 1 | 1 | 3 | 1 | 3 | 2 | 2 | 1 | 1 | 2 | 3 | 3 | 1 | 3 | 1 | 2 | 3 | 3 | 1 | 2 | 1 | 2 | 2 | 2 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1
446 | 9 | 6 | 11 | 18 | 25 | 29 | 38 | 42 | 49 | 55 | 62 | 70 | 82 | 88 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 3 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 2 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 3 | 1
447 | 8 | 6 | 12 | 18 | 22 | 29 | 37 | 45 | 52 | 59 | 68 | 76 | 82 | 88 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 3 | 1 | 1 | 3 | 3 | 1 | 2 | 2 | 3 | 1 | 1 | 2 | 1 | 3 | 1 | 2 | 2 | 3 | 2 | 2 | 1 | 2 | 3 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1
448 | 12 | 9 | 15 | 22 | 28 | 36 | 43 | 49 | 53 | 57 | 63 | 70 | 78 | 85 | 2 | 3 | 2 | 2 | 2 | 1 | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 1 | 1 | 3
449 | 10 | 8 | 14 | 20 | 26 | 33 | 38 | 45 | 51 | 57 | 64 | 69 | 75 | 82 | 3 | 2 | 1 | 2 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 3 | 1
450 | 12 | 8 | 16 | 23 | 32 | 39 | 45 | 50 | 55 | 63 | 69 | 74 | 79 | 84 | 2 | 3 | 2 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 2 | 3 | 3 | 2 | 3 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 1
451 | 12 | 8 | 15 | 25 | 30 | 36 | 40 | 47 | 53 | 59 | 64 | 70 | 77 | 81 | 3 | 1 | 1 | 3 | 3 | 1 | 1 | 2 | 3 | 2 | 3 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1
452 | 10 | 7 | 15 | 22 | 33 | 38 | 47 | 51 | 57 | 65 | 72 | 79 | 87 | 92 | 1 | 3 | 2 | 1 | 1 | 2 | 2 | 3 | 2 | 2 | 2 | 1 | 3 | 3 | 2 | 3 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 3 | 2 | 1 | 1 | 3 | 3 | 1 | 1 | 2 | 2 | 2 | 1 | 3 | 2 | 1 | 1 | 1
453 | 13 | 10 | 16 | 23 | 30 | 38 | 45 | 51 | 58 | 65 | 72 | 81 | 87 | 93 | 3 | 2 | 2 | 3 | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 2 | 3 | 1 | 2 | 1 | 1 | 2 | 2 | 3 | 3 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 3 | 1 | 2 | 1 | 2 | 2 | 2 | 3 | 1 | 1 | 2 | 3 | 3 | 1 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 1
454 | 9 | 6 | 12 | 19 | 27 | 36 | 43 | 51 | 59 | 66 | 71 | 79 | 87 | 91 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 2 | 3 | 1 | 1 | 2 | 1 | 2 | 3 | 3 | 2 | 3 | 1 | 1 | 1 | 3 | 2 | 2 | 2 | 2 | 2 | 3 | 2 | 2 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 3 | 3 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1
455 | 13 | 7 | 16 | 25 | 33 | 40 | 46 | 56 | 62 | 66 | 72 | 81 | 88 | 96 | 3 | 1 | 1 | 2 | 3 | 3 | 2 | 1 | 3 | 2 | 2 | 2 | 1 | 3 | 1 | 3 | 1 | 2 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 3 | 3 | 1 | 2 | 1 | 3 | 2 | 2 | 1 | 3
456 | 10 | 6 | 13 | 19 | 27 | 33 | 42 | 48 | 53 | 60 | 70 | 77 | 85 | 93 | 3 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 3 | 1 | 2 | 3 | 1 | 2 | 2 | 1 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 2 | 3 | 1 | 1 | 2 | 3 | 2 | 3 | 3 | 1 | 1 | 2 | 3 | 3 | 1 | 1 | 2 | 2 | 2 | 2
457 | 9 | 4 | 12 | 17 | 26 | 31 | 37 | 44 | 51 | 58 | 64 | 69 | 77 | 85 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 2 | 2 | 1 | 2 | 2 | 2 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 3 | 3 | 1
458 | 7 | 5 | 10 | 16 | 23 | 31 | 36 | 42 | 50 | 54 | 62 | 73 | 79 | 84 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 1 | 3 | 2 | 1 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 1 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 3 | 2 | 3 | 3 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2
459 | 10 | 6 | 14 | 22 | 29 | 35 | 41 | 47 | 55 | 59 | 68 | 78 | 83 | 87 | 2 | 2 | 1 | 1 | 1 | 3 | 3 | 1 | 2 | 1 | 3 | 2 | 1 | 3 | 1 | 2 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1
460 | 10 | 8 | 14 | 22 | 29 | 35 | 42 | 47 | 54 | 63 | 68 | 75 | 80 | 84 | 3 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 1 | 2 | 1 | 3 | 3 | 1 | 1 | 2 | 1 | 2 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1
461 | 12 | 8 | 16 | 23 | 30 | 35 | 42 | 48 | 55 | 60 | 69 | 77 | 85 | 92 | 3 | 1 | 1 | 3 | 3 | 1 | 1 | 3 | 1 | 1 | 2 | 3 | 3 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | 3 | 2 | 2 | 1 | 2 | 3 | 2 | 3 | 1 | 1 | 3 | 2 | 3 | 1 | 1
462 | 11 | 6 | 17 | 25 | 33 | 43 | 47 | 52 | 60 | 66 | 71 | 77 | 84 | 89 | 1 | 1 | 1 | 3 | 3 | 2 | 3 | 3 | 3 | 1 | 3 | 1 | 1 | 3 | 2 | 2 | 1 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 2 | 1 | 1
463 | 7 | 5 | 10 | 17 | 23 | 32 | 36 | 42 | 51 | 56 | 62 | 70 | 74 | 81 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 2 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 3
464 | 9 | 6 | 13 | 20 | 28 | 36 | 43 | 50 | 58 | 65 | 72 | 78 | 85 | 97 | 2 | 2 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 3 | 2 | 1 | 3 | 1 | 3 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 3 | 2 | 3 | 1 | 2 | 2 | 1 | 1 | 3 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3
465 | 9 | 5 | 12 | 17 | 25 | 33 | 40 | 45 | 49 | 55 | 61 | 66 | 75 | 81 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 1 | 1 | 2 | 3 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 3 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 3 | 1 | 3 | 1 | 1 | 3 | 1
466 | 13 | 8 | 15 | 21 | 28 | 37 | 46 | 50 | 57 | 62 | 68 | 73 | 78 | 88 | 3 | 2 | 2 | 1 | 2 | 3 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 1 | 2 | 3 | 2 | 1 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 3 | 3
467 | 9 | 7 | 11 | 19 | 26 | 33 | 38 | 47 | 51 | 58 | 63 | 69 | 76 | 82 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 2 | 1 | 3 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 2 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 3 | 1
468 | 9 | 7 | 11 | 20 | 26 | 37 | 46 | 55 | 64 | 73 | 79 | 88 | 95 | 104 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 3 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 1 | 3 | 3 | 2 | 3 | 3 | 1 | 2 | 1 | 3 | 2 | 3 | 2 | 3 | 3 | 1 | 3 | 1 | 1 | 1 | 2 | 3 | 1 | 3 | 3 | 1 | 2 | 1 | 1 | 3 | 2 | 3
469 | 10 | 8 | 12 | 17 | 23 | 32 | 37 | 43 | 51 | 56 | 64 | 71 | 79 | 86 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 3 | 2 | 1 | 3 | 1 | 2 | 2 | 3 | 1 | 1 | 1 | 2 | 3
470 | 10 | 6 | 14 | 20 | 30 | 38 | 45 | 53 | 59 | 63 | 70 | 74 | 82 | 87 | 1 | 2 | 2 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 3 | 1 | 3 | 1 | 3 | 3 | 1 | 3 | 3 | 1 | 2 | 1 | 3 | 1 | 1 | 3 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 2 | 1 | 2 | 1 | 1
471 | 13 | 9 | 15 | 21 | 29 | 34 | 38 | 43 | 54 | 62 | 72 | 76 | 81 | 89 | 3 | 1 | 2 | 3 | 1 | 3 | 1 | 1 | 2 | 1 | 2 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 3 | 2 | 2 | 1 | 3 | 3 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 3 | 1
472 | 12 | 7 | 17 | 22 | 30 | 36 | 43 | 50 | 57 | 65 | 69 | 76 | 82 | 88 | 1 | 2 | 1 | 3 | 2 | 3 | 3 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 3 | 3 | 2 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 2 | 3 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 2
473 | 12 | 8 | 15 | 24 | 31 | 38 | 45 | 50 | 56 | 61 | 67 | 73 | 83 | 90 | 1 | 3 | 2 | 2 | 1 | 3 | 1 | 2 | 3 | 2 | 3 | 1 | 1 | 3 | 1 | 2 | 2 | 1 | 3 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 2 | 3
474 | 9 | 7 | 14 | 20 | 28 | 36 | 44 | 53 | 60 | 67 | 77 | 83 | 88 | 97 | 3 | 1 | 1 | 2 | 1 | 1 | 2 | 3 | 1 | 3 | 1 | 1 | 2 | 2 | 3 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 3 | 3 | 3 | 1 | 2 | 3 | 3 | 1 | 1 | 2 | 1 | 1 | 2 | 3 | 3 | 1 | 3 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 2 | 3 | 1 | 3
475 | 13 | 7 | 17 | 23 | 29 | 35 | 39 | 46 | 53 | 59 | 67 | 75 | 82 | 87 | 1 | 2 | 3 | 1 | 3 | 3 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 3 | 1 | 3 | 3 | 1 | 1 | 3 | 2 | 2 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 2
476 | 10 | 4 | 12 | 23 | 30 | 37 | 45 | 51 | 60 | 66 | 74 | 80 | 87 | 94 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 3 | 3 | 3 | 2 | 1 | 1 | 3 | 2 | 2 | 1 | 1 | 3 | 2 | 2 | 2 | 2 | 3 | 1 | 1 | 1 | 3 | 1 | 3 | 2 | 1 | 2 | 2 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 3 | 2 | 1 | 1 | 1 | 3 | 1 | 2
477 | 12 | 8 | 15 | 22 | 31 | 38 | 45 | 55 | 63 | 70 | 77 | 82 | 90 | 98 | 1 | 3 | 2 | 2 | 3 | 1 | 1 | 2 | 3 | 1 | 1 | 2 | 3 | 1 | 2 | 3 | 2 | 3 | 1 | 1 | 2 | 1 | 3 | 1 | 2 | 2 | 3 | 3 | 2 | 1 | 2 | 3 | 2 | 2 | 2 | 1 | 3 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 2 | 1 | 2 | 1 | 2 | 3 | 2
478 | 9 | 5 | 15 | 20 | 29 | 37 | 45 | 49 | 58 | 66 | 77 | 82 | 91 | 97 | 1 | 1 | 2 | 1 | 3 | 1 | 3 | 3 | 1 | 1 | 1 | 2 | 1 | 3 | 3 | 2 | 3 | 1 | 1 | 3 | 2 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 2 | 1 | 2 | 2 | 3 | 3 | 2 | 3 | 3 | 1 | 1 | 1 | 2 | 3 | 3 | 1 | 2 | 2 | 1 | 1 | 2
479 | 11 | 8 | 14 | 23 | 30 | 37 | 44 | 52 | 56 | 62 | 70 | 74 | 83 | 87 | 1 | 3 | 2 | 2 | 2 | 1 | 2 | 1 | 3 | 2 | 1 | 3 | 2 | 1 | 1 | 3 | 1 | 2 | 2 | 2 | 1 | 2 | 3 | 1 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 3 | 2 | 3 | 1 | 1 | 1 | 1 | 1
480 | 15 | 9 | 19 | 25 | 30 | 39 | 46 | 54 | 58 | 67 | 74 | 83 | 90 | 96 | 2 | 3 | 3 | 1 | 3 | 3 | 3 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 3 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 3 | 1 | 3 | 1 | 2 | 2 | 3 | 3 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 2 | 1
481 | 13 | 9 | 17 | 21 | 26 | 34 | 41 | 47 | 53 | 61 | 67 | 71 | 78 | 85 | 3 | 3 | 1 | 2 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 2 | 1 | 1 | 3 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 3 | 1 | 2 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 2 | 3 | 1 | 1
482 | 11 | 7 | 16 | 22 | 26 | 32 | 40 | 44 | 52 | 62 | 71 | 77 | 84 | 94 | 2 | 1 | 3 | 1 | 3 | 1 | 2 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 1 | 3 | 3 | 1 | 3 | 1 | 1 | 2 | 3 | 1 | 1 | 3 | 1 | 3 | 3
483 | 9 | 5 | 11 | 19 | 24 | 32 | 37 | 44 | 51 | 58 | 64 | 70 | 78 | 84 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 3 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 3 | 2 | 2 | 1 | 1 | 2 | 3 | 1 | 2 | 1 | 2 | 1 | 2
484 | 7 | 5 | 13 | 21 | 31 | 40 | 45 | 56 | 66 | 75 | 82 | 91 | 98 | 105 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 3 | 3 | 1 | 2 | 2 | 3 | 1 | 3 | 3 | 1 | 3 | 3 | 2 | 1 | 1 | 2 | 1 | 3 | 3 | 3 | 2 | 3 | 1 | 3 | 3 | 1 | 3 | 3 | 2 | 2 | 1 | 3 | 1 | 2 | 2 | 3 | 2 | 2 | 1 | 2 | 2 | 1 | 1 | 3 | 2
485 | 9 | 5 | 12 | 19 | 24 | 30 | 38 | 46 | 53 | 59 | 65 | 72 | 77 | 82 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | 2 | 3 | 1 | 1 | 3 | 1 | 2 | 1 | 3 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1
486 | 14 | 9 | 18 | 24 | 29 | 35 | 41 | 51 | 59 | 66 | 73 | 82 | 91 | 97 | 2 | 3 | 3 | 1 | 2 | 3 | 1 | 3 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 3 | 3 | 3 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 2 | 2 | 1 | 2 | 3 | 1 | 2 | 3 | 2 | 2 | 2 | 3 | 2 | 1 | 2 | 1
487 | 9 | 6 | 11 | 17 | 23 | 29 | 37 | 44 | 55 | 61 | 65 | 73 | 80 | 89 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 2 | 2 | 3 | 1 | 1 | 2 | 3 | 3 | 2 | 3 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 2 | 2 | 1 | 2 | 2 | 1 | 3 | 3
488 | 10 | 8 | 15 | 20 | 26 | 32 | 40 | 49 | 56 | 61 | 65 | 73 | 81 | 88 | 2 | 2 | 3 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 3 | 1 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 3 | 3 | 3 | 1 | 1 | 3 | 1 | 1 | 2
489 | 9 | 6 | 13 | 18 | 28 | 37 | 44 | 49 | 55 | 61 | 70 | 75 | 84 | 92 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 1 | 3 | 2 | 1 | 2 | 3 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 3 | 3 | 1 | 2 | 1 | 1 | 1 | 2 | 3 | 3 | 1 | 1 | 3 | 1 | 3
490 | 11 | 7 | 13 | 23 | 31 | 39 | 50 | 56 | 62 | 69 | 76 | 84 | 90 | 94 | 1 | 1 | 2 | 3 | 2 | 2 | 1 | 1 | 3 | 2 | 3 | 2 | 1 | 3 | 1 | 3 | 1 | 3 | 2 | 2 | 3 | 2 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 3 | 2 | 2 | 3 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1
491 | 10 | 7 | 13 | 18 | 27 | 36 | 40 | 51 | 59 | 65 | 73 | 79 | 86 | 93 | 2 | 1 | 3 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 1 | 2 | 2 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 2 | 2 | 3 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 2 | 1 | 2 | 3 | 1
492 | 13 | 9 | 19 | 25 | 30 | 37 | 43 | 49 | 57 | 66 | 74 | 82 | 88 | 94 | 3 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 3 | 2 | 3 | 1 | 3 | 3 | 1 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 1
493 | 11 | 6 | 13 | 21 | 27 | 33 | 37 | 46 | 51 | 57 | 65 | 72 | 78 | 83 | 1 | 1 | 3 | 1 | 3 | 2 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 2 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 3 | 2 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 1
494 | 15 | 11 | 17 | 25 | 30 | 38 | 47 | 53 | 60 | 65 | 69 | 79 | 88 | 93 | 3 | 2 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 2 | 1 | 3 | 3 | 1 | 1 | 2 | 3 | 3 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 3 | 2 | 3 | 3 | 1 | 1 | 2 | 1 | 1
495 | 12 | 7 | 16 | 28 | 32 | 37 | 44 | 49 | 55 | 65 | 71 | 77 | 85 | 90 | 2 | 1 | 3 | 1 | 3 | 2 | 3 | 1 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 2 | 3 | 2 | 3 | 1 | 1 | 2 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 3 | 3 | 2 | 1 | 1 | 1
496 | 12 | 8 | 15 | 23 | 32 | 40 | 45 | 54 | 58 | 66 | 75 | 81 | 85 | 94 | 1 | 1 | 3 | 3 | 3 | 1 | 2 | 1 | 3 | 1 | 1 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 2 | 1 | 3 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 3 | 2 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 2
497 | 11 | 7 | 15 | 23 | 29 | 39 | 44 | 51 | 58 | 66 | 73 | 79 | 86 | 94 | 2 | 3 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 3 | 3 | 1 | 3 | 1 | 1 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 3 | 3 | 1 | 2 | 1 | 3 | 1 | 2 | 2 | 2 | 3 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 3 | 3 | 3 | 1 | 1
498 | 9 | 6 | 12 | 18 | 26 | 31 | 42 | 48 | 56 | 61 | 70 | 76 | 83 | 89 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 2 | 1 | 2 | 1 | 2 | 3 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 3 | 2 | 3 | 1 | 1 | 1 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 2 | 1 | 1
499 | 10 | 7 | 13 | 20 | 26 | 33 | 39 | 49 | 57 | 62 | 69 | 78 | 84 | 91 | 1 | 2 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 2 | 2 | 1 | 2 | 1 | 2 | 2 | 1 | 3 | 2 | 2 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 3 | 2 | 1 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 2
500 | 10 | 8 | 12 | 17 | 22 | 31 | 40 | 45 | 53 | 60 | 70 | 80 | 88 | 95 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 3 | 3 | 3 | 1 | 3 | 2 | 1 | 2 | 1 | 1 | 3 | 2 | 1 | 2 | 1 | 1 | 3 | 2 | 2 | 2 | 3 | 3 | 3 | 1 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 2 | 3
| 6 | 4 | 8 | 12 | 16 | 20 | 24 | 28 | 32 | 36 | 40 | 44 | 48 | 52
1% | 6.99 | 4 | 9 | 15 | 21 | 27 | 33 | 40 | 46 | 52 | 58.99 | 65.99 | 71.99 | 78
2% | 7 | 4 | 10 | 16 | 22 | 28 | 34.98 | 40.98 | 47 | 53 | 59.98 | 67 | 73 | 79
3% | 7 | 4 | 10 | 16 | 22 | 29 | 35 | 42 | 48 | 54 | 61 | 67.97 | 73.97 | 81
4% | 7 | 4 | 10 | 16 | 22.96 | 29 | 36 | 42 | 48 | 54.96 | 61 | 68 | 74 | 81
5% | 7 | 4.95 | 10 | 17 | 23 | 29 | 36 | 42 | 49 | 55 | 62 | 68 | 75 | 81
6% | 7 | 5 | 10 | 17 | 23 | 30 | 36 | 43 | 49 | 55 | 62 | 69 | 75 | 82
7% | 8 | 5 | 11 | 17 | 23 | 30 | 36.93 | 43 | 50 | 56 | 62 | 69 | 76 | 82
8% | 8 | 5 | 11 | 17 | 24 | 30 | 37 | 43 | 50 | 56 | 63 | 69 | 76 | 82
9% | 8 | 5 | 11 | 17 | 24 | 30 | 37 | 43 | 50 | 57 | 63 | 70 | 76 | 82
10% | 8 | 5 | 11 | 17 | 24 | 30 | 37 | 44 | 51 | 57 | 63 | 70 | 76.9 | 83
11% | 8 | 5 | 11 | 18 | 24 | 31 | 37 | 44 | 51 | 57 | 63.89 | 70 | 77 | 83
12% | 8 | 5 | 11 | 18 | 24 | 31 | 37 | 44 | 51 | 57 | 64 | 70 | 77 | 83.88
13% | 8 | 5 | 11 | 18 | 25 | 31 | 38 | 44 | 51 | 57 | 64 | 70 | 77 | 84
14% | 8 | 5 | 12 | 18 | 25 | 31 | 38 | 44 | 51 | 58 | 64 | 71 | 77 | 84
15% | 8 | 5 | 12 | 18 | 25 | 31 | 38 | 45 | 52 | 58 | 64.85 | 71 | 78 | 84
16% | 8 | 5 | 12 | 18 | 25 | 31 | 38 | 45 | 52 | 58 | 65 | 71 | 78 | 85
17% | 8 | 5 | 12 | 18 | 25 | 31 | 38 | 45 | 52 | 58 | 65 | 71 | 78 | 85
18% | 9 | 5.82 | 12 | 18 | 25 | 32 | 38 | 45 | 52 | 59 | 65 | 72 | 78 | 85
19% | 9 | 6 | 12 | 18 | 25 | 32 | 39 | 45 | 52 | 59 | 65 | 72 | 78 | 86
20% | 9 | 6 | 12 | 18 | 25 | 32 | 39 | 45 | 52 | 59 | 65 | 72 | 79 | 86
21% | 9 | 6 | 12 | 19 | 26 | 32 | 39 | 46 | 52 | 59 | 66 | 72 | 79 | 86
22% | 9 | 6 | 12 | 19 | 26 | 32 | 39 | 46 | 53 | 59 | 66 | 72 | 79 | 86
23% | 9 | 6 | 12 | 19 | 26 | 32 | 39 | 46 | 53 | 59 | 66 | 72 | 80 | 86
24% | 9 | 6 | 12 | 19 | 26 | 32 | 39 | 46 | 53 | 59 | 66 | 73 | 80 | 86
25% | 9 | 6 | 12 | 19 | 26 | 33 | 39 | 46 | 53 | 60 | 66 | 73 | 80 | 87
26% | 9 | 6 | 12 | 19 | 26 | 33 | 39 | 46 | 53 | 60 | 66 | 73 | 80 | 87
27% | 9 | 6 | 12 | 19 | 26 | 33 | 40 | 46 | 53 | 60 | 67 | 73 | 80 | 87
28% | 9 | 6 | 13 | 19 | 26 | 33 | 40 | 47 | 53 | 60 | 67 | 74 | 81 | 87
29% | 9 | 6 | 13 | 19 | 26 | 33 | 40 | 47 | 53 | 60 | 67 | 74 | 81 | 87
30% | 9 | 6 | 13 | 19 | 27 | 33 | 40 | 47 | 54 | 60 | 67 | 74 | 81 | 88
31% | 9 | 6 | 13 | 19 | 27 | 33 | 40 | 47 | 54 | 61 | 67 | 74 | 81 | 88
32% | 10 | 6 | 13 | 20 | 27 | 33 | 40 | 47 | 54 | 61 | 67 | 74 | 81 | 88
33% | 10 | 6 | 13 | 20 | 27 | 33 | 40 | 47 | 54 | 61 | 68 | 74 | 81 | 88
34% | 10 | 6 | 13 | 20 | 27 | 33 | 40 | 47 | 54 | 61 | 68 | 75 | 82 | 88
35% | 10 | 6 | 13 | 20 | 27 | 33 | 40 | 47.65 | 54 | 61 | 68 | 75 | 82 | 88
36% | 10 | 6 | 13 | 20 | 27 | 34 | 41 | 48 | 54 | 61 | 68 | 75 | 82 | 89
37% | 10 | 6 | 13 | 20 | 27 | 34 | 41 | 48 | 54 | 61 | 68 | 75 | 82 | 89
38% | 10 | 6 | 13 | 20 | 27 | 34 | 41 | 48 | 55 | 61 | 68 | 75 | 82 | 89
39% | 10 | 7 | 13 | 20 | 27 | 34 | 41 | 48 | 55 | 62 | 68 | 75 | 82 | 89
40% | 10 | 7 | 13 | 20 | 27 | 34 | 41 | 48 | 55 | 62 | 68 | 76 | 83 | 89
41% | 10 | 7 | 13 | 20 | 27 | 34 | 41 | 48 | 55 | 62 | 69 | 76 | 83 | 89
42% | 10 | 7 | 13 | 20 | 28 | 34 | 41 | 48 | 55 | 62 | 69 | 76 | 83 | 90
43% | 10 | 7 | 14 | 21 | 28 | 34 | 41 | 48 | 55 | 62 | 69 | 76 | 83 | 90
44% | 10 | 7 | 14 | 21 | 28 | 34 | 41 | 49 | 55 | 62 | 69 | 76 | 83 | 90
45% | 10 | 7 | 14 | 21 | 28 | 34 | 42 | 49 | 55 | 62 | 69 | 76 | 83 | 90
46% | 10 | 7 | 14 | 21 | 28 | 35 | 42 | 49 | 55 | 63 | 69 | 76 | 83 | 90
47% | 10 | 7 | 14 | 21 | 28 | 35 | 42 | 49 | 56 | 63 | 69 | 76 | 83 | 90
48% | 10 | 7 | 14 | 21 | 28 | 35 | 42 | 49 | 56 | 63 | 70 | 76.52 | 84 | 90.52
49% | 10 | 7 | 14 | 21 | 28 | 35 | 42 | 49 | 56 | 63 | 70 | 77 | 84 | 91
50% | 10 | 7 | 14 | 21 | 28 | 35 | 42 | 49 | 56 | 63 | 70 | 77 | 84 | 91
51% | 10 | 7 | 14 | 21 | 28 | 35 | 42 | 49 | 56 | 63 | 70 | 77 | 84 | 91
52% | 10 | 7 | 14 | 21 | 29 | 35 | 42 | 49 | 56 | 63 | 70 | 77 | 84 | 91
53% | 10 | 7 | 14 | 21 | 29 | 35 | 42 | 49 | 56 | 63 | 70 | 77 | 84 | 91
54% | 11 | 7 | 14 | 21 | 29 | 35 | 42 | 49 | 57 | 64 | 70 | 77 | 84 | 92
55% | 11 | 7 | 14 | 21 | 29 | 35 | 43 | 49 | 57 | 64 | 71 | 77 | 85 | 92
56% | 11 | 7 | 14 | 22 | 29 | 36 | 43 | 50 | 57 | 64 | 71 | 77.44 | 85 | 92
57% | 11 | 7 | 14 | 22 | 29 | 36 | 43 | 50 | 57 | 64 | 71 | 78 | 85 | 92
58% | 11 | 7 | 15 | 22 | 29 | 36 | 43 | 50 | 57 | 64 | 71 | 78 | 85 | 92
59% | 11 | 7 | 15 | 22 | 29 | 36 | 43 | 50 | 57 | 64 | 71 | 78 | 85 | 92
60% | 11 | 7 | 15 | 22 | 29 | 36 | 43 | 50 | 57 | 64 | 71 | 78 | 85 | 92.4
61% | 11 | 7 | 15 | 22 | 29 | 36 | 43 | 50 | 57 | 64 | 71 | 79 | 86 | 93
62% | 11 | 7 | 15 | 22 | 29 | 36 | 43 | 50 | 57 | 65 | 71 | 79 | 86 | 93
63% | 11 | 8 | 15 | 22 | 29 | 36 | 43 | 50 | 58 | 65 | 72 | 79 | 86 | 93
64% | 11 | 8 | 15 | 22 | 29.36 | 37 | 43 | 51 | 58 | 65 | 72 | 79 | 86 | 93
65% | 11 | 8 | 15 | 22 | 30 | 37 | 44 | 51 | 58 | 65 | 72 | 79 | 86 | 93
66% | 11 | 8 | 15 | 22 | 30 | 37 | 44 | 51 | 58 | 65 | 72 | 79 | 86 | 94
67% | 11 | 8 | 15 | 22 | 30 | 37 | 44 | 51 | 58 | 65 | 72 | 79.33 | 86 | 94
68% | 11 | 8 | 15 | 22 | 30 | 37 | 44 | 51 | 58 | 65 | 72 | 80 | 87 | 94
69% | 12 | 8 | 15 | 23 | 30 | 37 | 44 | 51 | 58 | 65 | 73 | 80 | 87 | 94
70% | 12 | 8 | 15 | 23 | 30 | 37 | 44 | 51 | 58 | 65 | 73 | 80 | 87 | 94
71% | 12 | 8 | 15 | 23 | 30 | 37 | 44 | 51 | 59 | 66 | 73 | 80 | 87 | 94
72% | 12 | 8 | 15 | 23 | 30 | 37 | 44 | 52 | 59 | 66 | 73 | 80 | 87 | 95
73% | 12 | 8 | 15 | 23 | 30.27 | 37 | 45 | 52 | 59 | 66 | 73 | 81 | 87 | 95
74% | 12 | 8 | 15.26 | 23 | 31 | 37 | 45 | 52 | 59 | 66 | 73 | 81 | 88 | 95
75% | 12 | 8 | 16 | 23 | 31 | 38 | 45 | 52 | 59 | 66 | 73 | 81 | 88 | 95
76% | 12 | 8 | 16 | 23 | 31 | 38 | 45 | 52 | 59 | 66 | 74 | 81 | 88 | 95
77% | 12 | 8 | 16 | 23 | 31 | 38 | 45 | 52 | 59 | 66 | 74 | 81 | 88.23 | 96
78% | 12 | 8 | 16 | 23 | 31 | 38 | 45 | 52 | 60 | 67 | 74 | 81 | 89 | 96
79% | 12 | 8 | 16 | 24 | 31 | 38 | 45 | 53 | 60 | 67 | 74 | 82 | 89 | 96
80% | 12 | 8 | 16 | 24 | 31 | 38 | 45 | 53 | 60 | 67 | 75 | 82 | 89 | 96
81% | 12 | 8 | 16 | 24 | 31 | 38 | 45 | 53 | 60 | 67 | 75 | 82 | 89 | 97
82% | 13 | 9 | 16 | 24 | 31 | 38 | 46 | 53 | 60 | 67 | 75 | 82 | 89 | 97
83% | 13 | 9 | 16 | 24 | 31 | 38.17 | 46 | 53 | 61 | 68 | 75 | 82 | 90 | 97
84% | 13 | 9 | 16.16 | 24 | 32 | 39 | 46 | 54 | 61 | 68 | 75 | 82.16 | 90 | 97
85% | 13 | 9 | 17 | 24 | 32 | 39 | 46 | 54 | 61 | 68 | 75 | 83 | 90 | 97
86% | 13 | 9 | 17 | 24 | 32 | 39 | 46.14 | 54 | 61 | 69 | 75 | 83 | 90 | 98
87% | 13 | 9 | 17 | 24 | 32 | 39 | 47 | 54 | 61 | 69 | 76 | 83 | 90 | 98
88% | 13 | 9 | 17 | 24 | 32 | 39.12 | 47 | 55 | 61 | 69 | 76 | 83 | 91 | 98
89% | 13 | 9 | 17 | 25 | 32 | 40 | 47 | 55 | 62 | 69 | 76 | 84 | 91 | 99
90% | 13 | 9 | 17 | 25 | 32 | 40 | 47 | 55 | 62 | 69.1 | 77 | 84 | 92 | 99
91% | 13 | 9 | 17 | 25 | 32 | 40 | 47.09 | 55 | 62 | 70 | 77 | 85 | 92 | 99
92% | 13.08 | 9 | 17 | 25 | 33 | 40 | 48 | 55 | 63 | 70 | 78 | 85 | 93 | 100
93% | 14 | 10 | 17 | 25 | 33 | 40.07 | 48 | 55.07 | 63 | 70.07 | 78 | 85.07 | 93 | 101
94% | 14 | 10 | 18 | 25 | 33 | 41 | 48 | 56 | 64 | 71 | 79 | 86 | 94 | 101
95% | 14 | 10 | 18 | 25 | 33 | 41 | 49 | 56 | 64 | 72 | 79.05 | 87 | 94 | 101.05
96% | 14 | 10 | 18 | 26 | 34 | 42 | 49.04 | 57 | 65 | 73 | 81 | 88 | 95 | 102
97% | 15 | 10 | 18 | 26 | 34 | 42 | 50 | 57 | 65 | 74 | 81.03 | 89 | 96 | 103
98% | 15 | 10 | 19 | 27 | 34 | 43 | 50 | 58 | 66 | 74.02 | 82.02 | 89.02 | 97 | 104
99% | 15 | 11 | 19.01 | 27.01 | 36.01 | 44 | 52 | 60 | 68 | 77 | 83.01 | 90.01 | 98.01 | 106
100% | 16 | 12 | 22 | 30 | 40 | 46 | 55 | 64 | 70 | 80 | 89 | 97 | 105 | 111